## G702
APPLICATION AND CERTIFICATION FOR PAYMENT | [5 empty] | AIA DOCUMENT G702 |  |  | PAGE 1 OF | 3
TO CONTRACTOR: |  |  |  | PROJECT: | Hunters Landing |  | APPLICATION #: | 13 |  | Distribution to:
Makers Line | [6 empty] | Invoice #14702 |  |  |  | OWNER
537 W 600 S, Ste 400 | [10 empty] | ARCHITECT
Salt Lake City, UT 84101 | [6 empty] | PERIOD TO: | 2023-03-31 |  | X | CONTRACTOR
FROM SUB-CONTRACTOR: |  |  |  | VIA ARCHITECT: | [6 empty] | CONST. MGR.
B&M Plumbing & Heating | [10 empty] | Lender
PO Box 1374 | [6 empty] | PROJECT #: | 21-10004
Riverton, UT 84065
CONTRACT FOR: | [6 empty] | CONTRACT DATE: | 2022-03-18
CONTRACTOR'S APPLICATION FOR PAYMENT | [5 empty] | The undersigned Contractor certifies that to the best of the Contractor's knowledge,
Application is made for payment, as shown below, in connection with the Contract. | [5 empty] | information and belief the Work covered by this Application for Payment has been
Continuation Sheet, AIA Document G703, is attached. | [5 empty] | completed in accordance with the Contract Documents, that all amounts have been paid by
the Contractor for Work for which previous Certificates for Payment were issued and
payments received from the Owner, and that current payment shown herein is now due.
1. ORIGINAL CONTRACT SUM |  |  |  | $ | 1638000
2. NET CHANGE BY CHANGE ORDERS |  |  |  | $ | -114343.5 | CONTRACTOR:
3. CONTRACT SUM TO DATE |  |  |  | $ | 1523656.5
4. TOTAL COMPLETED & STORED TO DATE (Column G on G703) |  |  |  | $ | 1380624.5
[6 empty] | By: |  |  |  | Date:
5. RETAINAGE: | [5 empty] | State of: |  |  | County of:
| 5% | (Column K on G703) | of Completed Work $ | 69031.23 |  | Subscribed and sworn to before me this |  |  | day of
Notary Public:
My Commission expires:
6. TOTAL EARNED LESS RETAINAGE |  |  |  | $ | 1311593.27
ARCHITECT'S CERTIFICATE FOR PAYMENT
In accordance with the Contract Documents, based on on-site observations and the data
7. LESS PREVIOUS CERTIFICATES FOR PAYMENT (Line 6 from prior Certificate) |  |  |  | $ | 1249349.27 | comprising the application, the Architect certifies to the Owner that to the best of the
8. CURRENT PAYMENT DUE |  |  |  | $ | 62244 | Architect's knowledge, information and belief the Work has progressed as indicated,
9. BALANCE TO FINISH, INCLUDING RETAINAGE |  |  |  | $ | 212063.23 | the quality of the Work is in accordance with the Contract Documents, and the Contractor
is entitled to payment of the AMOUNT CERTIFIED.
[6 empty] | AMOUNT CERTIFIED . . . . . . . . .. . . . . .$ |  |  | 62244
CHANGE ORDER SUMMARY |  |  |  | ADDITIONS | DEDUCTIONS | (Attach explanation if amount certified differs from the amount applied. Initial all figures on this
Total changes approved in previous months |  |  |  | 0 | 0 | Application and onthe Continuation Sheet that are changed to conform with the amount certified.)
ARCHITECT:
Total approved this Month |  |  |  | 0 | 0 | By: |  |  |  | Date:
|  |  |  | 0 | 0
TOTALS | [5 empty] | This Certificate is not negotiable. The AMOUNT CERTIFIED is payable only to the
Contractor named herein. Issuance, payment and acceptance of payment are without
NET CHANGES by Change Order |  |  |  | 0 |  | prejudice to any rights of the Owner or Contractor under this Contract.
AIA DOCUMENT G702 · APPLICATION AND CERTIFICATION FOR PAYMENT · 1992 EDITION · AIA · ©1992 | [5 empty] | THE AMERICAN INSTITUTE OF ARCHITECTS, 1735 NEW YORK AVE., N.W., WASHINGTON, DC 20006-5292
Users may obtain validation of this document by requesting a completed AIA Document D401 - Certification of Document's Authenticity from the Licensee.

## G703
CONTINUATION SHEET |  |  |  | AIA DOCUMENT G703 |  |  |  | PAGE 2 |  | /WGPD
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [6 empty] | APPLICATION #: | 13 |  | /wir.{d 25}~{r 6}/cf~~{L 6}~
Contractor's signed certification is attached. | [6 empty] | APPLICATION DATE: | 2023-03-15 |  | /wgpe
In tabulations below, amounts are stated to the nearest dollar. | [6 empty] | PERIOD TO: | 2023-03-31 |  | /ru.{d 26}
Use Column I on Contracts where variable retainage for line items may apply. | [6 empty] | ARCHITECT'S PROJECT #: | 21-10004 |  | {L 5}
{L 9}
A | B | C | D | E | F | G |  | H | I | /ru.{d 26}~
ITEM | DESCRIPTION OF WORK | SCHEDULED | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
# |  | VALUE | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | COMPLETE | TO FINISH
|  |  | APPLICATION |  | STORED | AND STORED
[6 empty] | TO DATE |  |  | 5%
1 | 22-0050 - Plumbing April | 49140 | 49140 |  |  | 49140 | 100% | 0 | 2457
2 | 22-0050 - Plumbing May | 49140 | 49140 |  |  | 49140 | 100% | 0 | 2457
3 | 22-0050 - Plumbing June | 103800 | 103800 |  |  | 103800 | 100% | 0 | 5190
4 | 22-0050 - Plumbing July | 163800 | 163800 |  |  | 163800 | 100% | 0 | 8190
5 | 22-0050 - Plumbing August | 163800 | 163800 |  |  | 163800 | 100% | 0 | 8190
6 | 22-0050 - Plumbing September | 163800 | 163800 |  |  | 163800 | 100% | 0 | 8190
7 | 22-0050 - Plumbing October | 163800 | 163800 |  |  | 163800 | 100% | 0 | 8190
8 | 22-0050 - Plumbing November | 163800 | 163800 |  |  | 163800 | 100% | 0 | 8190
| 22-0050 Plumbing November extra | 13192 | 13192 |  |  | 13192 | 100% | 0 | 659.6
9 | 22-0050 - Plumbing December | 163800 | 163800 |  |  | 163800 | 100% | 0 | 8190
10 | 22-0050 - Plumbing January | 65520 | 65520 |  |  | 65520 | 100% | 0 | 3276
11 | 22-0050 - Plumbing February | 65520 | 65520 |  |  | 65520 | 100% | 0 | 3276
12 | 22-0050 - Plumbing March | 65520 |  | 65520 |  | 65520 | 100% | 0 | 3276
| April | 65520 |  |  |  | 0 | 0% | 65520 | 0
| May | 65520 |  |  |  | 0 | 0% | 65520 | 0
| June | 65520 |  |  |  | 0 | 0% | 65520 | 0
13 | 22-0050 - Plumbing July | 46808 |  |  |  | 0 | 0% | 46808 | 0
| TOTALS | 1638000 | 1329112 | 65520 | 0 | 1394632 | 85.14% | 243368 | 69731.6

## CO 703
CONTINUATION SHEET |  |  |  | AIA DOCUMENT G703 |  |  |  | PAGE 3 |  | /WGPD
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [6 empty] | APPLICATION NO: | 13 |  | /wir.{d 25}~{r 6}/cf~~{L 6}~
Contractor's signed certification is attached. | [6 empty] | APPLICATION DATE: |  |  | /wgpe
In tabulations below, amounts are stated to the nearest dollar. | [6 empty] | PERIOD TO: | 2023-03-31 |  | /ru.{d 26}
Use Column I on Contracts where variable retainage for line items may apply. | [6 empty] | ARCHITECT'S PROJECT NO: | 21-10004 |  | {L 5}
{L 9}
A | B | C | D | E | F | G |  | H | I | /ru.{d 26}~
ITEM | DESCRIPTION OF WORK | CHANGE ORDER AMOUNT | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
# |  |  | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | COMPLETE | TO FINISH
|  |  | APPLICATION |  | STORED | AND STORED
[6 empty] | TO DATE |  |  | 5%
1 | Change Orders | -83925 | -16784 |  |  | -16784 | 20% | -67141 | -839.2
2 | Change Order Gas Line | -48000 | -9600 |  |  | -9600 | 20% | -38400 | -480
3 | Change order roof drains | 12376.5 | 12376.5 |  |  | 12376.5 | 100% | 0 | 618.83
4 | #8 change order | 5205 |  |  |  | 0 | 0% | 5205 | 0
5 | [5 empty] | 0 | #DIV/0! | 0 | 0
6 | [5 empty] | 0 | #DIV/0! | 0 | 0
7 | [5 empty] | 0 | #DIV/0! | 0 | 0
8 | [5 empty] | 0 | #DIV/0! | 0 | 0
9 | [5 empty] | 0 | #DIV/0! | 0 | 0
10 | [5 empty] | 0 | #DIV/0! | 0 | 0
11 | [5 empty] | 0 | #DIV/0! | 0 | 0
12 | [5 empty] | 0 | #DIV/0! | 0 | 0
13 | [5 empty] | 0 | #DIV/0! | 0 | 0
14 | [5 empty] | 0 | #DIV/0! | 0 | 0
15 | [5 empty] | 0 | #DIV/0! | 0 | 0
16 | [5 empty] | 0 | #DIV/0! | 0 | 0
17 | [5 empty] | 0 | #DIV/0! | 0 | 0
18 | [5 empty] | 0 | #DIV/0! | 0 | 0
19 | [5 empty] | 0 | #DIV/0! | 0 | 0
20 | [5 empty] | 0 | #DIV/0! | 0 | 0
21 | [5 empty] | 0 | #DIV/0! | 0 | 0
22 | [5 empty] | 0 | #DIV/0! | 0 | 0
23 | [5 empty] | 0 | #DIV/0! | 0 | 0
24 | [5 empty] | 0 | #DIV/0! | 0 | 0
25 | [5 empty] | 0 | #DIV/0! | 0 | 0
| TOTALS | -114343.5 | -14007.5 | 0 | 0 | -14007.5 | 12.25% | -100336 | -700.37
Grand Total
| Grand Total | 1523656.5 | 1315104.5 | 65520 | 0 | 1380624.5 | 90.61% | 143032 | 69031.23