## Table 1
CONTINUATION SHEET |  |  |  |  | AIA DOCUMENT G703 | [6 empty] | PAGE 2
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [9 empty] | APPLICATION #: |  |  | 0
Contractor's signed certification is attached. | [9 empty] | APPLICATION DATE: |  |  | 01/00/00
In tabulations below, amounts are stated to the nearest dollar. | [9 empty] | PERIOD TO: |  |  | 01/00/00
Use Column I on Contracts where variable retainage for line items may apply. ARCHITECT'S PROJECT #: 22-10004
A | B | C |  |  |  | D | E | F | G |  |  | H |  | I
ITEM |  | SCHEDULED VALUE |  |  |  | WORK COMPLETED |  | MATERIALS | TOTAL |  | % | BALANCE |  | RETAINAGE
# | DESCRIPTION OF WORK | ORIGINAL | CHANGE ORDERS | CURRENT |  | FROM PREVIOUS APPLICATION | THIS PERIOD | PRESENTLY STORED | COMPLETED AND STORED |  | COMPLETE | TO FINISH
[9 empty] | TO DATE |  |  |  |  | 5%
1 | 01-0010 - Overhead | 238113 | 0 | 238113 |  | 193468.81 |  |  | 193468.81 |  | 81.25% | 44644.19 |  | 9673.44
2 | 01-0020 - General Conditions | 877090 | 0 | 877090 |  | 712635.62 |  |  | 712635.62 |  | 81.25% | 164454.38 |  | 35631.78
3 | 01-0030 - General Requirements | 293535 | 5950 | 299485 |  | 243331.56 |  |  | 243331.56 |  | 81.25% | 56153.44 |  | 12166.58
4 | 01-0040 - Mobilization | 32100 | -950 | 31150 |  | 31150 |  |  | 31150 |  | 100% | 0 |  | 1557.5
5 | 01-0750 - Final Clean Up | 60443 |  | 60443 |  | 0 |  |  | 0 |  | 0% | 60443 |  | 0
6 | 01-1470 - Temporary Weather Protection | 155000 |  | 155000 |  | 150896.59 |  |  | 150896.59 |  | 97.35% | 4103.41 |  | 7544.83
7 | 01-0670 - Equipment Rental | 0 | 45000 | 45000 |  | 0 |  |  | 0 |  | 0% | 45000 |  | 0
8 | 01-1130 - Security | 0 | -7000 | -7000 |  | 0 |  |  | 0 |  | 0% | -7000 |  | 0
9 | 01-1390 - Termporary Power - Billing | 0 | -1143 | -1143 |  | 0 |  |  | 0 |  | 0% | -1143 |  | 0
10 | 01-1430 - Temporary Toilets | 0 | 7000 | 7000 |  | 0 |  |  | 0 |  | 0% | 7000 |  | 0
11 | 01-1470 - Temporary Weather Protection | 0 | 0 | -0.01 |  | -0.01 |  |  | -0.01 |  | 100% | 0 |  | 0
12 | 02-0150 - Erosion Control SWPPP | 15000 | 0 | 15000 |  | 9600 |  |  | 9600 |  | 64% | 5400 |  | 480
13 | 02-0290 - On-Site Demolition | 9800 | 0 | 9800 |  | 9800 |  |  | 9800 |  | 100% | 0 |  | 490
14 | 03-0020 - Cast In Place Concrete | 454250 | 9015 | 463265 |  | 463266 |  |  | 463266 |  | 100% | -1 |  | 23163.3
15 | 03-0230 - Concrete Insulation | 31370 | -31370 | 0 |  | 0 |  |  | 0 |  | #DIV/0! | 0 |  | 0
16 | 03-0330 - Gypsum Concrete | 104850 | 0 | 104850 |  | 0 |  |  | 0 |  | 0% | 104850 |  | 0
17 | 03-0350 - Anchor Bolts | 23250 | 0 | 23250 |  | 23250 |  |  | 23250 |  | 100% | 0 |  | 1162.5
18 | 03-0600 - Concree Curb & Sidewalk | 181300 | 0 | 181300 |  | 28596.09 |  |  | 28596.09 |  | 15.77% | 152703.91 |  | 1429.8
19 | 04-0030 - Masonry | 437750 | 51350 | 489100 |  | 195145 |  |  | 195145 |  | 39.9% | 293955 |  | 9757.25
20 | 05-0090 - Metal Framing | 440000 | -10334 | 429666 |  | 256273.05 | 112474.11 |  | 368747.16 |  | 85.82% | 60918.84 |  | 18437.358
21 | 06-0010 - Arch Wood Work (Cabinetry) | 466669 | 0 | 466669 |  | 340269.91 |  |  | 340269.91 |  | 72.91% | 126399.09 |  | 17013.4955
22 | 06-0030 - Countertops | 228576 | 35944 | 264520 |  | 133289.5 |  |  | 133289.5 |  | 50.39% | 131230.5 |  | 6664.475
23 | 06-0090 - Finish Carpentry - Interiors | 344663 | -11935 | 332728 |  | 4000 |  |  | 4000 |  | 1.202% | 328728 |  | 200
24 | 06-0170 - Rough Carpentry | 3365403 | 632755.04 | 3998158.04 |  | 3999588.04 |  |  | 3999588.04 |  | 100% | -1430 |  | 199979.402
25 | 07-0050 - Bituminous Dampproofing | 5000 | 0 | 5000 |  | 5000 |  |  | 5000 |  | 100% | 0 |  | 250
26 | 07-0110 - Caulking & Sealants | 49250 | -46612 | 2638 |  | 0 |  |  | 0 |  | 0% | 2638 |  | 0
27 | 07-0130 - Stucco/Siding | 580570 | 89215 | 669785 |  | 58849.6 |  |  | 58849.6 |  | 8.786% | 610935.4 |  | 2942.48
28 | 07-0170 - Deck Coating | 89000 | 0 | 89000 |  | 0 |  |  | 0 |  | 0% | 89000 |  | 0
29 | 07-0230 - Insulation - Interiors | 254695 | 41805 | 296500 |  | 34165 |  |  | 34165 |  | 11.52% | 262335 |  | 1708.25
30 | 07-0250 - Membrane Roofing | 248130 | 96016.41 | 344146.41 |  | 314883.49 |  |  | 314883.49 |  | 91.5% | 29262.92 |  | 15744.1745
31 | 07-0310 - Soffit & Fascia | 48300 | 17535 | 65835 |  | 0 |  |  | 0 |  | 0% | 65835 |  | 0
32 | 07-0350 - Roof Specialist & Accessories | 1670 | 0 | 1670 |  | 1670 |  |  | 1670 |  | 100% | 0 |  | 83.5
33 | 08-0010 - Access Doors Overhead | 57250 | 0 | 57250 |  | 37212 | 15138.06 |  | 52350.06 |  | 91.44% | 4899.94 |  | 2617.503
34 | 08-0170 - Entrance & Storefronts | 69340 | 48032.1 | 117372.1 |  | 112241.5 |  |  | 112241.5 |  | 95.63% | 5130.6 |  | 5612.075
35 | 08-0260 - Doors & Frames | 871450 | -7680 | 863770 |  | 537222.6 | 113163.288 |  | 650385.888 |  | 75.3% | 213384.112 |  | 32519.2944
36 | 08-0290 - Mirrors | 27585 | 0 | 27585 |  | 21285 |  |  | 21285 |  | 77.16% | 6300 |  | 1064.25
37 | 08-0300 - Windows | 106109 | 27466.08 | 133575.08 |  | 124937.65 | 2229.6645 |  | 127167.3145 |  | 95.2% | 6407.7655 |  | 6358.3657
38 | 08-0320 - Spcl Door - Ext (Fire Rated Doors) Smoke | 33992 | 0 | 33992 |  | 27193.6 |  |  | 27193.6 |  | 80% | 6798.4 |  | 1359.68
CONTINUATION SHEET |  |  |  |  | AIA DOCUMENT G703 | [6 empty] | PAGE 2
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [9 empty] | APPLICATION #: |  |  | 0
Contractor's signed certification is attached. | [9 empty] | APPLICATION DATE: |  |  | 01/00/00
In tabulations below, amounts are stated to the nearest dollar. | [9 empty] | PERIOD TO: |  |  | 01/00/00
Use Column I on Contracts where variable retainage for line items may apply. ARCHITECT'S PROJECT #: 22-10004
A | B | C |  |  |  | D | E | F | G |  |  | H |  | I
ITEM |  | SCHEDULED VALUE |  |  |  | WORK COMPLETED |  | MATERIALS | TOTAL |  | % | BALANCE |  | RETAINAGE
# | DESCRIPTION OF WORK | ORIGINAL | CHANGE ORDERS | CURRENT |  | FROM PREVIOUS APPLICATION | THIS PERIOD | PRESENTLY STORED | COMPLETED AND STORED |  | COMPLETE | TO FINISH
[9 empty] | TO DATE |  |  |  |  | 5%
39 | 09-0050 - Ceramic Tile | 7414 | 0 | 7414 |  | 0 |  |  | 0 |  | 0% | 7414 |  | 0
40 | 09-0130 - Flooring | 424508 | 0 | 424508 |  | 129000 |  |  | 129000 |  | 30.39% | 295508 |  | 6450
41 | 09-0190 - Painting - Site Improvements | 415951 | -7000 | 408951 |  | 4015 |  |  | 4015 |  | 0.9818% | 404936 |  | 200.75
42 | 09-0250 - Gypsum Board Install | 1352896 | 0 | 1352896 |  | 71900 | 296769.7215 |  | 368669.7215 |  | 27.25% | 984226.2785 |  | 18433.4861
43 | 10-0150 - Fire Extinguisher Cabinets | 6700 | 0 | 6700 |  | 5905 |  |  | 5905 |  | 88.13% | 795 |  | 295.25
44 | 10-0250 - Knox Boxes | 350 | 0 | 350 |  | 0 |  |  | 0 |  | 0% | 350 |  | 0
45 | 10-0310 - Postal Specialities | 28500 | 0 | 28500 |  | 0 |  |  | 0 |  | 0% | 28500 |  | 0
46 | 10-0330 - Signage-Inter/Exter Code | 31238 | 0 | 31238 |  | 15619.14 |  |  | 15619.14 |  | 50% | 15618.86 |  | 780.957
47 | 10-0370 - Toilet & Bath Accessories | 33575 | -33575 | 0 |  | 0 |  |  | 0 |  | 100% | 0 |  | 0
48 | 11-0110 - Residential Appliances | 561094 | -61641 | 499453 |  | 0 |  |  | 0 |  | 0% | 499453 |  | 0
49 | 12-0010 - Blinds | 42565 | 0 | 42565 |  | 0 |  |  | 0 |  | 0% | 42565 |  | 0
50 | 13-0010 - Carports | 108689 | 43996.02 | 152685.02 |  | 0 |  |  | 0 |  | 0% | 152685.02 |  | 0
51 | 13-0030 - Swimming Pools | 236400 | 0 | 236400 |  | 23640 |  |  | 23640 |  | 10% | 212760 |  | 1182
52 | 14-0010 - Chutes (Waste & Recycling) | 19195 | 1090 | 20285 |  | 14930 |  |  | 14930 |  | 73.6% | 5355 |  | 746.5
53 | 14-0050 - Elevators | 226650 | 53608 | 280258 |  | 140129 | 96626.334 |  | 236755.334 |  | 84.48% | 43502.666 |  | 11837.7667
54 | 21-0020 - Wet Pipe Sprinkler Systems | 311952 | 7107.84 | 319059.84 |  | 272267.48 |  |  | 272267.48 |  | 85.33% | 46792.36 |  | 13613.374
55 | 22-0010 - Plumbingg Fixture Accessories | 89200 | -16957 | 72243 |  | 72243 |  |  | 72243 |  | 100% | 0 |  | 3612.15
56 | 22-0050 - Plumbing Systems | 1638000 | -100828.5 | 1537171.5 |  | 1249584.5 | 65356.2 |  | 1314940.7 |  | 85.54% | 222230.8 |  | 65747.035
| 23-0090 - HVAC | 2013439 | -467269 | 1546170 |  | 1136567 | 19950 |  | 1156517 |  | 74.8% | 389653 |  | 57825.85
57 | 26-0010 - Basic Electrical Materials | 1552213 | 72461.7 | 1624674.7 |  | 1007417.26 | 143427.711 |  | 1150844.971 |  | 70.84% | 473829.729 |  | 57542.2485
58 | 26-0090 - Temp Power & Usage | 15000 | -7500 | 7500 |  | 7500 |  |  | 7500 |  | 100% | 0 |  | 375
59 | 26-0130 - Electric Car Charging Allowance | 18000 | 0 | 18000 |  | 0 |  |  | 0 |  | 0% | 18000 |  | 0
60 | 31-0100 - Earthwork | 1041238 | 140042.72 | 1181280.72 |  | 1082476.72 |  |  | 1082476.72 |  | 91.64% | 98804 |  | 54123.836
61 | 31-0200 - Earth Moving | 91951 | -77256.22 | 14694.78 |  | 17240.81 |  |  | 17240.81 |  | 117.3% | -2546.03 |  | 862.0405
62 | 32-0200 - Asphalt Paving | 170414 | -21969.02 | 148444.98 |  | 0 |  |  | 0 |  | 0% | 148444.98 |  | 0
63 | 32-0300 - Fencing | 76736 | 12093 | 88829 |  | 0 |  |  | 0 |  | 0% | 88829 |  | 0
64 | 32-0700 - Landscaping & Planting | 137413 | 0 | 137413 |  | 0 |  |  | 0 |  | 0% | 137413 |  | 0
| SUBTOTALS | 20852784 | 526463.17 | 21379247.16 |  | 13319655.51 | 865135.089 | 0 | 14184790.599 |  | 66.35% | 7194456.561 |  | 709239.527
| GC-0010 - Contingency | 561532 | -526464.17 | 35067.83 |  | 0 |  |  | 0 |  | 0% | 35067.83 |  | 0
| GC-0020 - Profit | 893302 | 0 | 893302 |  | 550274.03 |  |  | 550274.03 |  | 61.6% | 343027.97 |  | 0
| GC-0040 - Insurance | 257161 | 0 | 257161 |  | 257161 |  |  | 257161 |  | 100% | 0 |  | 0
| GC-0060 - Development Fee | 1028648 | 0 | 1028648 |  | 390886.24 |  |  | 390886.24 |  | 38% | 637761.76 |  | 0
| GRAND TOTALS | 23593427 | -1 | 23593425.99 |  | 14517976.78 | 823938.18 | 0 | 15341914.96 |  | 65.03% | 8251511.03 |  | 707179.68