## Sheet1
Hunters Landing Budget Tracking
[5 empty] | Draw 1 | Draw 2 | Draw 3 | Draw 4 | Draw 5 | Draw 6 | Billed to Date | Remaining
07-0130 | Stucco/ Siding | REPLACE TYVEK ENTIRE EXTERIOR |  | 45000 | [6 empty] | 0
02-0290 | On-Site Demolition | DEMO BRICK |  | 30000 | [6 empty] | 0
02-0290 | On-Site Demolition | 8 LOADS OF BRICK TO THE DUMP |  | 8000 | [6 empty] | 0
04-1930 | Masonry | BUY NEW BRICK, RE-INSTALL BRICK |  | 110000 | [6 empty] | 0
02-0290 | On-Site Demolition | DEMO ALL WINDOWS & EXT DOORS |  | 35000 | [6 empty] | 0
08-0300 | Windows | REPLACE BROKEN WINDOWS |  | 15000 | [6 empty] | 0
02-0290 | On-Site Demolition | DEMO 100% OF EXISTING FRAMING & LUMBER |  | 170000 | Draw 1: 80802.65; Draw 4: 144249.95 | 225052.6
02-0290 | On-Site Demolition | 50 LOADS TO THE DUMP, EXTERIOR WALLS (GUESS) |  | 50000 | Draw 5: 34120 | 34120
02-0290 | On-Site Demolition | REMOVE ALL ELECTRICIAL FROM EXTERIOR WALLS |  | 10000 | [6 empty] | 0
02-0290 | On-Site Demolition | REMOVE ALL SPRINKLERS FROM EXTERIOR WALLS & DECKS |  | 30000 | Draw 6: 4000 | 4000
06-0170 | Rough Carpentry | NEW LUMBER TO REBUILD COMPLETE EXTERIORS |  | 270000 | Draw 3: 14534.2; Draw 5: 103785.27; Draw 6: 3987.43 | 122306.9
06-0170 | Rough Carpentry | NEW FRAMING OF COMPLETE EXTERIORS (AND INTERIOR ISSUES) |  | 1200000 |  |  | 201669.64 | 317608.99 | 302190.2 | 847500.95 | 1668969.78
07-0250 | Membrane Roofing | LIFT & FIX ROOF. FINISH WEST TPO PART |  | 72500 | [6 empty] | 0
02-0290 | On-Site Demolition | REMOVE SHEETROCK FROM BUILDING |  | 45000 | Draw 2: 10000 | 10000
06-0170 | Rough Carpentry | NEW HARDWARE FOR RE-FRAME |  | 25000 | [6 empty] | 0
26-0010 | Basic Electrical Materials | RE-INSTALL ALL ELECTRICIAL IN EXTERIOR WALLS |  | 20000 | [6 empty] | 0
21-0020 | Wet Pipe Sprinkler Systems | RE-INSTALL ALL SPRINKLERS TO ALL DECKS |  | 30000 | [6 empty] | 0
08-0300 | Windows | RE-INSTALL ALL EXTERIOR WINDOWS & FLASHING (200) |  | 40000 | [6 empty] | 0
08-0260 | Doors & Frames | RE-INSTALL 170 EXTERIOR DOORS |  | 17000 | [6 empty] | 0
02-0290 | On-Site Demolition | ALL SHORING MATERIALS |  | 50000 | Draw 2: 2541.34 | 2541.34
02-0290 | On-Site Demolition | ALL SHORING LABOR | 3 MONTHS OF MOVING AROUND | 90000 | [6 empty] | 0
02-0290 | On-Site Demolition | ALL SHORING ENGINEERING |  | 12000 | 14454.04 | 533.75 | 3389.26 | 2203.75 |  |  | 20580.8
|  | GENERAL CONDITIONS FOR 3 MONTH FIX TIME PERIOD | [8 empty] | 0
01-0340 | General Conditions | TOILETS |  | 3000 | 340.03 | 415.03 |  | 999.26 |  | 2494.97 | 4249.29
01-0340 | General Conditions | SECURITY |  | 3000 | [6 empty] | 0
26-0090 | Temp Power & Usage | TEMP POWER |  | 3000 |  | 519.16 | 11.13 | 295.96 |  | 206.01 | 1032.26
01-1470 | Temporary Weather Protection | WINTER CONDITIONS |  | 15000 | [6 empty] | 0
01-2010 | Overhead | OVERHEAD & SUPERVISION |  | 70000 | 25000 | 20000 | 20000 | 25000 | 26365.15 | 25000 | 141365.15
01-0340 | General Conditions | TRAILER |  | 4000 | [6 empty] | 0
01-0340 | General Conditions | FENCING |  | 3000 | Draw 2: 510.39; Draw 6: 707.86 | 1218.25
01-0340 | General Conditions | SAFETY |  | 500 | [6 empty] | 0
GC-0020 | Profit | BUILDERS PROFIT | 6% | 153510 | [6 empty] | 0
01-0750 | General Requirements | RENTAL EQUIPMENT |  | 25000 | [6 empty] | 0
01-0930 | Final Clean Up | CLEAN UP & GENERAL LABOR |  | 15000 | [6 empty] | 0
GC-0040 | Insurance | GL INSURANCE (DIFFERENT FROM BUILDERS RISK) |  | 12500 | [6 empty] | 0
02-0150 | Erosion Control SWPPP | SWPPP |  | 10000 | Draw 5: 605; Draw 6: 430 | 1035
|  | Contract Subtotal |  |  | 120596.72 | 34519.67 | 239604.23 | 490357.91 | 467065.62 | 884327.22 | 2236471.37
GC-0040 | Insurance | Insurance Payment |  |  | Draw 1: 105417
26-0010 | Basic Electrical Materials | Electrical work done under ML |  |  | Draw 1: 78072.18
01-0750 | General Requirements | Dumpster Charges under ML |  |  | Draw 1: 7630.41
09-0250 | Gypsum Board Install | Foundation Building Materials - Drywall Materials under ML |  |  | Draw 2: 96853.21
31-0100 | Earthwork | Triple BBB under ML - UDOT Permit & Rough cut in parking lot |  |  | Draw 2: 8998.17
14-0050 | Elevators | TK Elevator Payment |  |  | Draw 2: 4601.25
06-0090 | Finish Carpentry - Interiors | Wilcox Finish and Supply Under ML |  |  | Draw 2: 37120.44
31-0100 | Earthwork | Track-out Materials & Time |  |  | Draw 2: 61154.15
22-0050 | Plumbing Systems | Plumbing Deposit |  |  | Draw 3: 205000
02-0150 | Erosion Control SWPPP | Previous SWPPP Charges |  |  | Draw 4: 11725
22-0050 | Plumbing Systems | Plumbing Redo |  |  | Draw 5: 87565
22-0050 | Plumbing Systems | Replace Cracked Tubs |  |  | Draw 6: 34646
|  | Out of Scope Subtotal |  |  | 191119.59 | 208727.22 | 205000 | 11725 | 87565 | 0 | 704136.81
|  | Total |  | 2692010 | 311716.31 | 243246.89 | 444604.23 | 502082.91 | 554630.62 | 884327.22 | 2940608.18
THESE NUMBERS DO NOT REFLECT ANY STORAGE OF MATERIALSFOR THE LAST YEAR FROM ANY TRADES
THESE NUMBERS DO NOT REFLECT ANY BIDS IN THE ORGINAL COST BREAKDOWN BY MAKERS LINE
THESE NUMBERS DO NOT INCLUDE ANY OLD OR NEW CHANGE ORDERS FROM ALL CONTRACTORS
THESE NUMBERS DO NOT INCLUDE REPLACING THE SHEETROCK, OR STORING THE SHEETROCK, SOME
OF THE OLD SHEETROCK WILL NEED TO BE THROWN AWAY DUE TO GETTING WET AND MOLD PRESENT
THESE NUMBERS DO NOT INCLUDE ANY FRAMING ISSUES NOT YET KNOWN, INCLUDING FIXING ALL
OF THE STAIRWELLS WHICH HAVE ISSUES.
THESE NUMBERS DO NOT REFLECT ANY HVAC OR PLUMBING ISSUES THAT MIGHT ARISE DURING THE
DEMO AND FIX ON THE BUILDING.
|  |  | Grand Total | 2692010

## Sheet2
2024-04-22
455
2025-07-21