## New Budget
Hunter's Landing Continuation Sheet
Rich Development
|  | Scheduled Value |  |  | 2024-08-29 | 2024-09-11 | [8 empty] | Retainage
# | DESCRIPTION OF WORK | Rich Development | Change Orders/Reallocation | Total | Draw 20 | Draw 21 | Draw 22 | Draw 23 | Draw 24 | Draw 25 | Draw 26 | TOTAL COMPLETED AND STORED TO DATE | Percent Complete | BALANCE TO FINISH | Value 5%
EXCAVATION/SITE | Survey | 5500 |  | 5500 |  |  | 1340 |  |  |  |  | 1340 | 24.36% | 4160
EXCAVATION/SITE | Excavation | 364814.62 |  | 364814.62 |  | 11270 | [5 empty] | 11270 | 3.089% | 353544.62
EXCAVATION/SITE | Concrete | 208293.28 |  | 208293.28 |  |  | 51841.53 | 16487.1 |  |  |  | 68328.63 | 32.8% | 139964.65
EXCAVATION/SITE | 12th UDOT | 17550 |  | 17550 | [7 empty] | 0 | 0% | 17550
EXCAVATION/SITE | All Fencing | 44475 |  | 44475 | [7 empty] | 0 | 0% | 44475 |  | 7973.68
EXCAVATION/SITE | Track out Pad entire building | 49700 |  | 49700 | 37020 | 12680 | [5 empty] | 49700 | 100% | 0 |  | 12490.22
FRAME/ROOF | Turnkey Frame/Garage | 43755 |  | 43755 |  |  | 16365.04 |  |  |  |  | 16365.04 | 37.4% | 27389.96
FRAME/ROOF | Garage Roof | 12500 |  | 12500 | [7 empty] | 0 | 0% | 12500
FRAME/ROOF | Roofing L&M | 63244 |  | 63244 |  |  |  | 30100.75 |  |  |  | 30100.75 | 47.59% | 33143.25
FRAME/ROOF | Deck Coatings | 97940 |  | 97940 | [7 empty] | 0 | 0% | 97940
FRAME/ROOF | Structural Steel-Parking | 84577 |  | 84577 | [7 empty] | 0 | 0% | 84577
FRAME/ROOF | All other Steel Features | 623901.14 | -221107.65 | 402793.49 | 15311.37 | 4548.58 | 13218.11 |  |  |  |  | 33078.06 | 8.212% | 369715.43
FRAME/ROOF | Garage Door For Trash | 4500 |  | 4500 | [7 empty] | 0 | 0% | 4500
FRAME/ROOF | Store Front Labor | 7500 | 5053.48 | 12553.48 |  | 7500 | 5053.48 |  |  |  |  | 12553.48 | 100% | 0
FRAME/ROOF | Elevator | 70150 |  | 70150 | [7 empty] | 0 | 0% | 70150
FRAME/ROOF | HM Door Labor | 52475 |  | 52475 |  |  | 1500 |  |  |  |  | 1500 | 2.859% | 50975
MEP TRADES | Plumbing | 524500 |  | 524500 | 60000 |  | 124504.85 | 45610.81 |  |  |  | 230115.66 | 43.87% | 294384.34
MEP TRADES | HVAC | 1244900 |  | 1244900 |  |  | 204250 | 199500 |  |  |  | 403750 | 32.43% | 841150
MEP TRADES | Electric | 434737.1 |  | 434737.1 |  | 77050.11 |  | 51300 |  |  |  | 128350.11 | 29.52% | 306386.99
MEP TRADES | 3 Electric Car Station | 37500 |  | 37500 | [7 empty] | 0 | 0% | 37500
MEP TRADES | Sprinkler System | 168681 |  | 168681 |  | 30210.79 | 44259.74 | 15466 |  |  |  | 89936.53 | 53.32% | 78744.47
MEP TRADES | Fire Caulk | 14750 |  | 14750 | [7 empty] | 0 | 0% | 14750
FINISHES | Gypcrete | 152486 |  | 152486 |  |  |  | 15200 |  |  |  | 15200 | 9.968% | 137286
FINISHES | Insulation | 222919 |  | 222919 |  | 92390.22 |  | 117346.28 |  |  |  | 209736.5 | 94.09% | 13182.5
FINISHES | Sheetrock | 1467345 |  | 1467345 |  |  | 526379.97 | 233987.48 |  |  |  | 760367.45 | 51.82% | 706977.55
FINISHES | Finish Materials Misc | 25000 |  | 25000 |  |  | 15339.63 | 5402.93 |  |  |  | 20742.56 | 82.97% | 4257.44
FINISHES | Finish Labor | 189135 |  | 189135 |  |  | 13552 | 65952.64 |  |  |  | 79504.64 | 42.04% | 109630.36
FINISHES | Interior Paint | 303668.8 |  | 303668.8 |  |  |  | 16999.73 |  |  |  | 16999.73 | 5.598% | 286669.07
FINISHES | Equipment Cabinets | 6000 |  | 6000 | [7 empty] | 0 | 0% | 6000
FINISHES | Garage Doors | 14081.4 |  | 14081.4 | [7 empty] | 0 | 0% | 14081.4
FINISHES | Floor Prep | 10000 |  | 10000 | [7 empty] | 0 | 0% | 10000
FINISHES | Hardware & Install Labor | 65000 |  | 65000 | [7 empty] | 0 | 0% | 65000
FINISHES | Fire Extinguishers | 7850 |  | 7850 | [7 empty] | 0 | 0% | 7850
FINISHES | Mirrors | 24750 |  | 24750 | [7 empty] | 0 | 0% | 24750
FINISHES | Flooring,Wall Tile M&L | 340975 |  | 340975 |  |  |  | 99384 |  |  |  | 99384 | 29.15% | 241591
EXTERIORS & MISC | Brick | 342000 |  | 342000 |  |  | 95000 | 95000 |  |  |  | 190000 | 55.56% | 152000
EXTERIORS & MISC | Stucco EFIS,Soffit,Fascia | 437274.1 |  | 437274.1 |  |  | 62353.62 |  |  |  |  | 62353.62 | 14.26% | 374920.48
EXTERIORS & MISC | Gutter | 10245 |  | 10245 | [7 empty] | 0 | 0% | 10245
EXTERIORS & MISC | Plaster Foundation | 4250 |  | 4250 | [7 empty] | 0 | 0% | 4250
EXTERIORS & MISC | Roof Hatch | 1600 |  | 1600 | [7 empty] | 0 | 0% | 1600
EXTERIORS & MISC | Trash Chute | 37850 |  | 37850 | [7 empty] | 0 | 0% | 37850
EXTERIORS & MISC | Pool | 257092 |  | 257092 | [7 empty] | 0 | 0% | 257092
EXTERIORS & MISC | Knox box & Fire Lids | 2450 |  | 2450 | [7 empty] | 0 | 0% | 2450
ALLOWANCES | Landscape | 184000 |  | 184000 | [7 empty] | 0 | 0% | 184000
ALLOWANCES | Appliances | 517942.26 |  | 517942.26 | [7 empty] | 0 | 0% | 517942.26
ALLOWANCES | Signage | 15000 |  | 15000 | [7 empty] | 0 | 0% | 15000
ALLOWANCES | All Amenities | 25000 |  | 25000 | [7 empty] | 0 | 0% | 25000
ALLOWANCES | Garden Shed & Pad | 8000 |  | 8000 | [7 empty] | 0 | 0% | 8000
ALLOWANCES | Blinds | 42500 |  | 42500 | [7 empty] | 0 | 0% | 42500
GENERAL | Contingency | 250000 | -23738.74 | 226261.26 | 72500 | 55251.03 | [5 empty] | 127751.03 | 51.1% | 122248.97
GENERAL | Equipment | 25000 |  | 25000 | 10000 | 15000 | [5 empty] | 25000 | 100% | 0
GENERAL | Honey Bucket | 7000 |  | 7000 |  | 362.35 | 2098.2 |  |  |  |  | 2460.55 | 35.15% | 4539.45
GENERAL | Dumpster | 25000 |  | 25000 |  |  | 8951.43 | 4698.26 |  |  |  | 13649.69 | 54.6% | 11350.31
GENERAL | Temp Fence | 6000 |  | 6000 | [7 empty] | 0 | 0% | 6000
GENERAL | Clean-up Labor | 30000 |  | 30000 |  | 3400 |  | 405 |  |  |  | 3805 | 12.68% | 26195
GENERAL | Final Clean | 50000 |  | 50000 | [7 empty] | 0 | 0% | 50000
GENERAL | Street Sweeping | 5000 |  | 5000 | [7 empty] | 0 | 0% | 5000
GENERAL | Conc Wash Out | 5000 |  | 5000 | [7 empty] | 0 | 0% | 5000
GENERAL | SWPPP/split w/cu inspections | 3500 |  | 3500 | 450 | 450 | 940 | 450 |  |  |  | 2290 | 65.43% | 1210
GENERAL | Temp Power | 7500 |  | 7500 | 216.17 | 122.62 | 3037.71 | 152.71 |  |  |  | 3529.21 | 47.06% | 3970.79
GENERAL | Office Trailer | 15000 |  | 15000 |  |  | 100 | 2096.73 |  |  |  | 2196.73 | 14.64% | 12803.27
GENERAL | Security Cameras | 30000 |  | 30000 |  | 5641.15 | 1128.23 | 1128.23 |  |  |  | 7897.61 | 26.33% | 22102.39
GENERAL | Special Inspections | 15000 |  | 15000 | 5742.5 | 4661.18 | [5 empty] | 10403.68 | 69.36% | 4596.32
GENERAL | Saftey | 10000 |  | 10000 | [7 empty] | 0 | 0% | 10000
GENERAL | General Conditions | 30000 |  | 30000 |  | 779.31 | [5 empty] | 779.31 | 2.598% | 29220.69
GENERAL | Insurance Not Builders | 25000 |  | 25000 |  | 19.98 | [5 empty] | 19.98 | 0.07992% | 24980.02
GENERAL | Site Supervision | 240000 |  | 240000 | 25000 | 20000 | 41500 | 29000 |  |  |  | 115500 | 48.12% | 124500
GENERAL | Construction Profit | 6583.94 |  | 6583.94 | [7 empty] | 0 | 0% | 6583.94
GENERAL | Exterior Wall Project | 483915.5 | 239792.91 | 723708.41 | 204487 | 279428.5 | 216054.17 | 23738.74 |  |  |  | 723708.41 | 100% | 0
| TOTALS | 10159856.14 | 0 | 10159856.14 | 430727.04 | 620765.82 | 1448767.71 | 1069407.39 | 0 | 0 | 0 | 3569667.96 | 35.14% | 6590188.18 | 0
GENERAL | 1st MTG IR | 494000 |  | 494000 |  | 163759.91 | [5 empty] | 163759.91 | 33.15% | 330240.09
GENERAL | 2nd MTG IR | 550497.32 |  | 550497.32 | [7 empty] | 0 | 0% | 550497.32
GENERAL | Inspections | 3500 |  | 3500 |  | 800 | [5 empty] | 800 | 22.86% | 2700
| TOTALS | 11207853.46 | 0 | 11207853.46 | 430727.04 | 785325.73 | 1448767.71 | 1069407.39 | 0 | 0 | 0 | 3734227.87 | 33.32% | 7473625.59 | 0
0
Cash
|  | Loan | [9 empty] | -3401612.51
Original Contract Sum
Net change by approved change orders
Contract sum to date
Total completed and stored to date
Retainage
Total earned less retainage
Less previous certificates for payment
Current Payment Due
Balance to finish with retainage