## Cost To Complete
Hunter's Landing Continuation Sheet
Rich Development
Scheduled Value
Item # | # | DESCRIPTION OF WORK | Rich Development | Change Orders/Reallocation | Total | Amount Paid to Date | Retention held to Date | Contract cost to complete including retention | Change Order cost to complete including retention | TOTAL COST TO COMPLETE | DIFFERENCE BETWEEN SCHEDULED VALUE AND COST TO COMPLETE
NOTES
001 | EXCAVATION/SITE | Survey | 5500 | 515 | 6015 | 6015 | 0 | 750 |  | 750 | -750 | Fencing & Pond surveys
002 | EXCAVATION/SITE | Excavation | 364814.62 |  | 364814.62 | 284961.84 | 26859.91 | 86839 | 15535 | 129233.91 | -49381.13
003 | EXCAVATION/SITE | Concrete | 208293.28 |  | 208293.28 | 127580.19 | 3614.11 | 85568.91 |  | 89183.02 | -8469.93
004 | EXCAVATION/SITE | 12th UDOT | 17550 |  | 17550 | 0 |  | 49414 | 69495 | 118909 | -101359
005 | EXCAVATION/SITE | All Fencing | 44475 |  | 44475 | 0 |  | 44475 | 7559.31 | 52034.31 | -7559.31
006 | EXCAVATION/SITE | Track out Pad entire building | 49700 |  | 49700 | 49700 |  |  |  | 0 | 0
007 | FRAME/ROOF | Turnkey Frame/Garage | 43755 | -20000 | 23755 | 16365.04 | 851.75 |  |  | 851.75 | 6538.21
008 | FRAME/ROOF | Garage Roof | 12500 |  | 12500 | 0 |  | 12500 |  | 12500 | 0
009 | FRAME/ROOF | Roofing L&M | 63244 |  | 63244 | 50372.23 | 4242.8 | 30744.18 |  | 34986.98 | -22115.21
010 | FRAME/ROOF | Deck Coatings | 97940 |  | 97940 | 80613.2 | 5309.72 | 5761 | 10598.4 | 21669.12 | -4342.32 | Decks lvl 2-5 done, Urbane needs to bill the rest of their contract amount, My Roof has a bill for the rest of the amentities deck change order
011 | FRAME/ROOF | Structural Steel-Parking | 84577 | -24000 | 60577 | 0 | 17699.18 |  |  | 17699.18 | 42877.82
012 | FRAME/ROOF | All other Steel Features | 623901.14 | -221107.65 | 402793.49 | 250237.61 |  |  |  | 0 | 152555.88
013 | FRAME/ROOF | Garage Door For Trash | 4500 |  | 4500 | 0 |  |  |  | 0 | 4500
014 | FRAME/ROOF | Store Front Labor | 7500 | 5053.48 | 12553.48 | 12553.48 |  |  |  | 0 | 0
015 | FRAME/ROOF | Elevator | 70150 |  | 70150 | 0 |  |  |  | 0 | 70150
016 | FRAME/ROOF | HM Door Labor | 52475 | -19908.96 | 32566.04 | 32480.8 |  |  |  | 0 | 85.24
017 | MEP TRADES | Plumbing | 524500 |  | 524500 | 381460.72 | 2200 | 67280 |  | 69480 | 73559.28
018 | MEP TRADES | HVAC | 1244900 |  | 1244900 | 934132.15 |  |  |  | 0 | 310767.85
019 | MEP TRADES | Electric | 434737.1 |  | 434737.1 | 129850.11 |  |  |  | 0 | 304886.99
020 | MEP TRADES | 3 Electric Car Station | 37500 |  | 37500 | 0 |  |  |  | 0 | 37500
021 | MEP TRADES | Sprinkler System | 168681 |  | 168681 | 91342.53 |  |  |  | 0 | 77338.47
022 | MEP TRADES | Fire Caulk | 14750 |  | 14750 | 3515.03 |  |  |  | 0 | 11234.97
023 | FINISHES | Gypcrete | 152486 |  | 152486 | 141181.97 |  |  |  | 0 | 11304.03
024 | FINISHES | Insulation | 222919 | -25000 | 197919 | 184045.4 | 9686.6 |  |  | 9686.6 | 4187
025 | FINISHES | Sheetrock | 1467345 |  | 1467345 | 1126879.14 | 55246.44 | 357781.56 |  | 413028 | -72562.14 | Cabinets/Countertops were taken out of this category because there was no category funded for them
026 | FINISHES | Finish Materials Misc | 25000 | 146985.68 | 171985.68 | 170079.85 |  |  |  | 0 | 1905.83
027 | FINISHES | Finish Labor | 189135 | -50313.72 | 138821.28 | 135233.66 |  |  |  | 0 | 3587.62
028 | FINISHES | Interior Paint | 303668.8 |  | 303668.8 | 136304.72 |  |  |  | 0 | 167364.08
029 | FINISHES | Equipment Cabinets | 6000 |  | 6000 | 0 |  |  |  | 0 | 6000
030 | FINISHES | Garage Doors | 14081.4 |  | 14081.4 | 0 |  |  |  | 0 | 14081.4
031 | FINISHES | Floor Prep | 10000 |  | 10000 | 0 |  |  |  | 0 | 10000
032 | FINISHES | Hardware & Install Labor | 65000 |  | 65000 | 15682.52 |  |  |  | 0 | 49317.48
033 | FINISHES | Fire Extinguishers | 7850 |  | 7850 | 0 |  |  |  | 0 | 7850
034 | FINISHES | Mirrors | 24750 | -15000 | 9750 | 0 |  |  |  | 0 | 9750
035 | FINISHES | Flooring,Wall Tile M&L | 340975 |  | 340975 | 172071.22 |  |  |  | 0 | 168903.78
036 | EXTERIORS & MISC | Brick | 342000 | 9500 | 351500 | 351500 |  |  |  | 0 | 0
037 | EXTERIORS & MISC | Stucco EFIS,Soffit,Fascia | 437274.1 |  | 437274.1 | 383782.04 | 20188.3 | 195638.61 |  | 215826.91 | -162334.85
038 | EXTERIORS & MISC | Gutter | 10245 |  | 10245 | 0 |  |  |  | 0 | 10245
039 | EXTERIORS & MISC | Plaster Foundation | 4250 |  | 4250 | 0 |  |  |  | 0 | 4250
040 | EXTERIORS & MISC | Roof Hatch | 1600 |  | 1600 | 0 |  |  |  | 0 | 1600
041 | EXTERIORS & MISC | Trash Chute | 37850 |  | 37850 | 0 |  |  |  | 0 | 37850
042 | EXTERIORS & MISC | Pool | 257092 |  | 257092 | 0 |  | 257092 |  | 257092 | 0
043 | EXTERIORS & MISC | Knox box & Fire Lids | 2450 |  | 2450 | 0 |  | 2450 |  | 2450 | 0
044 | ALLOWANCES | Landscape | 184000 | -15000 | 169000 | 0 |  | 169000 |  | 169000 | 0
045 | ALLOWANCES | Appliances | 517942.26 |  | 517942.26 | 520418.99 |  |  |  | 0 | -2476.73
046 | ALLOWANCES | Signage | 15000 |  | 15000 | 0 |  | 15000 | 20000 | 35000 | -20000 | Owner provided sign? CO?
047 | ALLOWANCES | All Amenities | 25000 |  | 25000 | 7222.64 |  |  |  | 0 | 17777.36
048 | ALLOWANCES | Garden Shed & Pad | 8000 |  | 8000 | 0 |  | 8000 |  | 8000 | 0 | Allowance & Owner provided. Need to find exact cost
049 | ALLOWANCES | Blinds | 42500 |  | 42500 | 26645.75 | 1402.41 | 17943.84 |  | 19346.25 | -3492
050 | GENERAL | Contingency | 250000 | -43882.07 | 206117.93 | 166495.25 |  |  |  | 0 | 39622.68
051 | GENERAL | Equipment | 25000 |  | 25000 | 25000 |  |  |  | 0 | 0
052 | GENERAL | Honey Bucket | 7000 |  | 7000 | 6856.9 |  | 3500 |  | 3500 | -3356.9
053 | GENERAL | Dumpster | 25000 | 815.83 | 25815.83 | 25815.83 |  | 20000 |  | 20000 | -20000
054 | GENERAL | Temp Fence | 6000 |  | 6000 | 0 |  |  |  | 0 | 6000
055 | GENERAL | Clean-up Labor | 30000 |  | 30000 | 14395 |  | 15605 |  | 15605 | 0
056 | GENERAL | Final Clean | 50000 |  | 50000 | 0 |  | 50000 |  | 50000 | 0
057 | GENERAL | Street Sweeping | 5000 |  | 5000 | 0 |  | 5000 |  | 5000 | 0
058 | GENERAL | Conc Wash Out | 5000 |  | 5000 | 0 |  |  |  | 0 | 5000
059 | GENERAL | SWPPP/split w/cu inspections | 3500 | 140 | 3640 | 3640 |  | 3000 |  | 3000 | -3000
060 | GENERAL | Temp Power | 7500 |  | 7500 | 4958.13 |  | 2541.87 |  | 2541.87 | 0
061 | GENERAL | Office Trailer | 15000 |  | 15000 | 6462.81 |  | 8537.19 |  | 8537.19 | 0
062 | GENERAL | Security Cameras | 30000 |  | 30000 | 12423.09 |  | 10000 |  | 10000 | 7576.91 | Do we need a change order for the building security system?
063 | GENERAL | Special Inspections | 15000 |  | 15000 | 14393.68 |  | 606.32 |  | 606.32 | 0
064 | GENERAL | Saftey | 10000 | -5000 | 5000 | 0 |  |  |  | 0 | 5000
065 | GENERAL | General Conditions | 30000 |  | 30000 | 3914.39 |  | 26085.61 |  | 26085.61 | 0
066 | GENERAL | Insurance Not Builders | 25000 |  | 25000 | 19.98 |  |  |  | 0 | 24980.02
067 | GENERAL | Site Supervision | 240000 |  | 240000 | 183225 |  | 87500 |  | 87500 | -30725
068 | GENERAL | Construction Profit | 6583.94 |  | 6583.94 | 0 |  | 606582 |  | 606582 | -599998.06
069 | GENERAL | Exterior Wall Project | 483915.5 | 276202.41 | 760117.91 | 760117.91 |  |  |  | 0 | -1.1642e-10
|  | TOTALS | 10159856.14 | 0 | 10159856.14 | 7049945.8 | 147301.22 | 2245196.09 | 123187.71 | 2515685.02 | 594225.32

## Continuation Sheet
Hunter's Landing Continuation Sheet
Rich Development
|  |  | Scheduled Value |  |  | 2024-08-29 | 2024-09-11 | [9 empty] | Retainage |  | COST TO COMPLETE
Item # | # | DESCRIPTION OF WORK | Rich Development | Change Orders/Reallocation | Total | Draw 20 | Draw 21 | Draw 22 | Draw 23 | Draw 24 | Draw 25 | Draw 26 | Draw 27 | TOTAL COMPLETED AND STORED TO DATE | Percent Complete | BALANCE TO FINISH | Value 5% |  | Contract Amount | Retention | CO Amount for cost to complete | Project CO | CO #
001 | EXCAVATION/SITE | Survey | 5500 | 515 | 6015 |  |  | 1340 |  | 4675 |  |  |  | 6015 | 100% | 0 |  |  | 750 |  | 0
002 | EXCAVATION/SITE | Excavation | 364814.62 |  | 364814.62 |  | 11270 |  |  | 273691.84 |  |  | 97255.3 | 382217.14 | 104.8% | -17402.52 |  |  | 97255.3 | 38228.61
003 | EXCAVATION/SITE | Concrete | 208293.28 |  | 208293.28 |  |  | 51841.53 | 16487.1 | 35355.61 |  | 23895.95 | 50216.38 | 177796.57 | 85.36% | 30496.71 |  |  | 80713.09 | 3988.61
004 | EXCAVATION/SITE | 12th UDOT | 17550 |  | 17550 | [8 empty] | 0 | 0% | 17550 |  |  | 17550 |  | 91495
005 | EXCAVATION/SITE | All Fencing | 44475 |  | 44475 | [7 empty] | 10035.61 | 10035.61 | 22.56% | 34439.39 |  |  | 34439.39 | 119 | 7560.31
006 | EXCAVATION/SITE | Track out Pad entire building | 49700 |  | 49700 | 37020 | 12680 | [6 empty] | 49700 | 100% | 0 |  |  | 0 |  |  | 61154.15
007 | FRAME/ROOF | Turnkey Frame/Garage | 43755 | -20000 | 23755 |  |  | 16365.04 | [5 empty] | 16365.04 | 68.89% | 7389.96 |  |  | 0 | 851.75
008 | FRAME/ROOF | Garage Roof | 12500 |  | 12500 | [8 empty] | 0 | 0% | 12500
009 | FRAME/ROOF | Roofing L&M | 63244 |  | 63244 |  |  |  | 30100.75 |  |  | 20271.48 | 41081.98 | 91454.21 | 144.6% | -28210.21
010 | FRAME/ROOF | Deck Coatings | 97940 |  | 97940 |  |  |  |  | 80613.2 |  |  | 10068.48 | 90681.68 | 92.59% | 7258.32 |  |  |  |  | 32000 |  |  | Amenities Deck
011 | FRAME/ROOF | Structural Steel-Parking | 84577 | -24000 | 60577 | [7 empty] | 5079.4 | 5079.4 | 8.385% | 55497.6 |  |  | 55497.6 | 17699.18 | 3550
012 | FRAME/ROOF | All other Steel Features | 623901.14 | -221107.65 | 402793.49 | 15311.37 | 4548.58 | 13218.11 |  | 217159.55 |  |  | 115752.27 | 365989.88 | 90.86% | 36803.61 |  |  | 36803.61
013 | FRAME/ROOF | Garage Door For Trash | 4500 |  | 4500 | [8 empty] | 0 | 0% | 4500 |  |  | 4500
014 | FRAME/ROOF | Store Front Labor | 7500 | 5053.48 | 12553.48 |  | 7500 | 5053.48 | [5 empty] | 12553.48 | 100% | 0 |  |  | 0
015 | FRAME/ROOF | Elevator | 70150 |  | 70150 | [7 empty] | 18316.72 | 18316.72 | 26.11% | 51833.28 |  |  | 51833.28
016 | FRAME/ROOF | HM Door Labor | 52475 | -19908.96 | 32566.04 |  |  | 1500 |  |  | 20015.96 | 10964.84 | 39584.35 | 72065.15 | 221.3% | -39499.11 |  |  |  |  | 17364.5
017 | MEP TRADES | Plumbing | 524500 |  | 524500 | 60000 |  | 124504.85 | 45610.81 | 72610.06 | 38780 | 39955 | 60080 | 441540.72 | 84.18% | 82959.28 |  |  | 82959.28 |  |  |  |  | Needs to match
018 | MEP TRADES | HVAC | 1244900 |  | 1244900 |  |  | 204250 | 199500 | 309673.4 | 135208.75 | 85500 | 162938.3 | 1097070.45 | 88.13% | 147829.55 |  |  | 147829.55
019 | MEP TRADES | Electric | 434737.1 |  | 434737.1 |  | 77050.11 |  | 51300 | 1500 |  |  | 118750 | 248600.11 | 57.18% | 186136.99 |  |  | 186136.99
020 | MEP TRADES | 3 Electric Car Station | 37500 |  | 37500 | [8 empty] | 0 | 0% | 37500 |  |  | 37500
021 | MEP TRADES | Sprinkler System | 168681 |  | 168681 |  | 30210.79 | 44259.74 | 15466 |  | 1406 |  | 1406 | 92748.53 | 54.98% | 75932.47 |  |  | 75932.47
022 | MEP TRADES | Fire Caulk | 14750 |  | 14750 |  |  |  |  | 423.37 |  | 3091.66 | 9000 | 12515.03 | 84.85% | 2234.97 |  |  | 2234.97
023 | FINISHES | Gypcrete | 152486 |  | 152486 |  | 92390.22 |  | 15200 | 20900 | 12458.92 | 232.83 | 3135 | 144316.97 | 94.64% | 8169.03 |  |  | 8169.03
024 | FINISHES | Insulation | 222919 | -25000 | 197919 |  |  |  | 117346.28 | 1433.31 | 52303.94 | 12961.87 |  | 184045.4 | 92.99% | 13873.6 |  |  | 13873.6
025 | FINISHES | Sheetrock | 1467345 |  | 1467345 |  |  | 526379.97 | 233987.48 | 131595 |  | 234916.69 | 137042.6 | 1263921.74 | 86.14% | 203423.26 |  |  | 203423.26
026 | FINISHES | Finish Materials Misc | 25000 | 146985.68 | 171985.68 |  |  | 15339.63 | 5402.93 | 54571.16 | 19713.68 | 75052.45 | 29350.8 | 199430.65 | 116% | -27444.97 |  |  |  |  | 30000 | Door rebuild
027 | FINISHES | Finish Labor | 189135 | -50313.72 | 138821.28 |  |  | 13552 | 65952.64 | 16798.35 |  | 38930.67 | 23257.27 | 158490.93 | 114.2% | -19669.65 |  |  | -19669.65 |  | 31000 | Door rebuild
028 | FINISHES | Interior Paint | 303668.8 |  | 303668.8 |  |  |  | 16999.73 |  | 28686.67 | 90618.32 | 169506.27 | 305810.99 | 100.7% | -2142.19 |  |  | -2142.19
029 | FINISHES | Equipment Cabinets | 6000 |  | 6000 | [8 empty] | 0 | 0% | 6000 |  |  | 6000
030 | FINISHES | Garage Doors | 14081.4 |  | 14081.4 | [7 empty] | 15818.11 | 15818.11 | 112.3% | -1736.71 |  |  | -1736.71 |  | 3000
031 | FINISHES | Floor Prep | 10000 |  | 10000 | [7 empty] | 3673.39 | 3673.39 | 36.73% | 6326.61 |  |  | 6326.61
032 | FINISHES | Hardware & Install Labor | 65000 |  | 65000 | [5 empty] | 6806.48 | 8876.04 | 859.58 | 16542.1 | 25.45% | 48457.9 |  |  | 48457.9 |  | 19065.45 | Door rebuild
033 | FINISHES | Fire Extinguishers | 7850 |  | 7850 | [7 empty] | 4811.75 | 4811.75 | 61.3% | 3038.25 |  |  | 3038.25
034 | FINISHES | Mirrors | 24750 | -15000 | 9750 | [7 empty] | 6051.5 | 6051.5 | 62.07% | 3698.5 |  |  | 3698.5
035 | FINISHES | Flooring,Wall Tile M&L | 340975 |  | 340975 |  |  |  | 99384 | 13764.08 | 17929.49 | 40993.65 | 86933.77 | 259004.99 | 75.96% | 81970.01 |  |  | 81970.01
036 | EXTERIORS & MISC | Brick | 342000 | 9500 | 351500 |  |  | 95000 | 95000 | 66500 |  | 95000 | 81429.33 | 432929.33 | 123.2% | -81429.33 |  |  |  |  | 98500 | Difference between budget & contract amount
037 | EXTERIORS & MISC | Stucco EFIS,Soffit,Fascia | 437274.1 |  | 437274.1 |  |  | 62353.62 |  |  | 135571.74 | 185856.68 | 185856.68 | 569638.72 | 130.3% | -132364.62 |  |  | -132364.62
038 | EXTERIORS & MISC | Gutter | 10245 |  | 10245 | [8 empty] | 0 | 0% | 10245 |  |  | 10245
039 | EXTERIORS & MISC | Plaster Foundation | 4250 |  | 4250 | [8 empty] | 0 | 0% | 4250 |  |  | 4250
040 | EXTERIORS & MISC | Roof Hatch | 1600 |  | 1600 | [8 empty] | 0 | 0% | 1600 |  |  | 1600
041 | EXTERIORS & MISC | Trash Chute | 37850 |  | 37850 | [8 empty] | 0 | 0% | 37850 |  |  | 37850
042 | EXTERIORS & MISC | Pool | 257092 |  | 257092 | [7 empty] | 138008.97 | 138008.97 | 53.68% | 119083.03 |  |  | 119083.03
043 | EXTERIORS & MISC | Knox box & Fire Lids | 2450 |  | 2450 | [7 empty] | 1272.3 | 1272.3 | 51.93% | 1177.7 |  |  | 1177.7
044 | ALLOWANCES | Landscape | 184000 | -15000 | 169000 | [7 empty] | 78001.63 | 78001.63 | 46.15% | 90998.37 |  |  | 90998.37
045 | ALLOWANCES | Appliances | 517942.26 |  | 517942.26 | [6 empty] | 520418.99 |  | 520418.99 | 100.5% | -2476.73 |  |  | -2476.73 |  | 3000
046 | ALLOWANCES | Signage | 15000 |  | 15000 | [7 empty] | 4956 | 4956 | 33.04% | 10044 |  |  | 10044
047 | ALLOWANCES | All Amenities | 25000 |  | 25000 | [6 empty] | 7222.64 |  | 7222.64 | 28.89% | 17777.36 |  |  | 17777.36
048 | ALLOWANCES | Garden Shed & Pad | 8000 |  | 8000 | [8 empty] | 0 | 0% | 8000 |  |  | 8000
049 | ALLOWANCES | Blinds | 42500 |  | 42500 | [5 empty] | 26645.75 |  | 17046.65 | 43692.4 | 102.8% | -1192.4 |  |  | -1192.4
050 | GENERAL | Contingency | 250000 | -43882.07 | 206117.93 | 72500 | 55251.03 |  |  |  | 2663.35 | 36080.87 | 175 | 166670.25 | 80.86% | 39447.68
051 | GENERAL | Equipment | 25000 |  | 25000 | 10000 | 15000 | [6 empty] | 25000 | 100% | 0 |  |  | 0
052 | GENERAL | Honey Bucket | 7000 |  | 7000 |  | 362.35 | 2098.2 |  | 2178.18 | 739.39 | 1478.78 | 1478.78 | 8335.68 | 119.1% | -1335.68 |  |  | -1335.68 |  | 1500
053 | GENERAL | Dumpster | 25000 | 815.83 | 25815.83 |  |  | 8951.43 | 4698.26 | 3953.04 | 4758.94 | 3454.16 | 17562.37 | 43378.2 | 168% | -17562.37 |  |  |  |  | 2500
054 | GENERAL | Temp Fence | 6000 |  | 6000 | [8 empty] | 0 | 0% | 6000 |  |  | 6000
055 | GENERAL | Clean-up Labor | 30000 |  | 30000 |  | 3400 |  | 405 | 6300 | 4110 | 180 | 9865 | 24260 | 80.87% | 5740 |  |  | 5740
056 | GENERAL | Final Clean | 50000 |  | 50000 | [8 empty] | 0 | 0% | 50000 |  |  | 50000
057 | GENERAL | Street Sweeping | 5000 |  | 5000 | [8 empty] | 0 | 0% | 5000 |  |  | 5000
058 | GENERAL | Conc Wash Out | 5000 |  | 5000 | [8 empty] | 0 | 0% | 5000 |  |  | 5000
059 | GENERAL | SWPPP/split w/cu inspections | 3500 | 140 | 3640 | 450 | 450 | 940 | 450 | 450 | 450 | 450 | 1650 | 5290 | 145.3% | -1650 |  |  | 1500
060 | GENERAL | Temp Power | 7500 |  | 7500 | 216.17 | 122.62 | 3037.71 | 152.71 | 68.62 | 368.53 | 991.77 | 838.76 | 5796.89 | 77.29% | 1703.11 |  |  | 1703.11
061 | GENERAL | Office Trailer | 15000 |  | 15000 |  |  | 100 | 2146.73 | 4216.08 |  |  | 538.58 | 7001.39 | 46.68% | 7998.61 |  |  | 7998.61
062 | GENERAL | Security Cameras | 30000 |  | 30000 |  | 5641.15 | 1128.23 | 1128.23 |  | 4525.48 |  | 3928.23 | 16351.32 | 54.5% | 13648.68 |  |  | 5000
063 | GENERAL | Special Inspections | 15000 |  | 15000 | 5742.5 | 4661.18 |  |  | 3490 | 500 |  |  | 14393.68 | 95.96% | 606.32 |  |  | 0
064 | GENERAL | Saftey | 10000 | -5000 | 5000 | [8 empty] | 0 | 0% | 5000 |  |  | 5000
065 | GENERAL | General Conditions | 30000 |  | 30000 |  | 779.31 |  |  | 3135.08 |  |  | 8469.08 | 12383.47 | 41.28% | 17616.53 |  |  | 17616.53
066 | GENERAL | Insurance Not Builders | 25000 |  | 25000 |  | 19.98 | [6 empty] | 19.98 | 0.07992% | 24980.02 |  |  | 0
067 | GENERAL | Site Supervision | 240000 |  | 240000 | 25000 | 20000 | 41500 | 29000 | 23375 | 22175 | 22175 | 60525 | 243750 | 101.6% | -3750 |  |  | -3750
068 | GENERAL | Construction Profit | 6583.94 |  | 6583.94 | [8 empty] | 0 | 0% | 6583.94 |  |  | 606582.94
069 | GENERAL | Exterior Wall Project | 483915.5 | 276202.41 | 760117.91 | 204487 | 279428.5 | 216054.17 | 23738.74 | 18672.5 |  | 17737 | 74243.72 | 834361.63 | 109.8% | -74243.72 |  | SCS | 200000 |  | 201701 | Plumbing fixes
|  | TOTALS | 10159856.14 | 0 | 10159856.14 | 430727.04 | 620765.82 | 1448767.71 | 1069457.39 | 1367102.43 | 535818.07 | 1577307.34 | 1905850.91 | 8955796.71 | 88.15% | 1204059.43 | 0
| GENERAL | 1st MTG IR | 494000 |  | 494000 |  | 163759.91 | [6 empty] | 163759.91 | 33.15% | 330240.09
| GENERAL | 2nd MTG IR | 550497.32 |  | 550497.32 | [8 empty] | 0 | 0% | 550497.32
| GENERAL | Inspections | 3500 |  | 3500 |  | 800 | [6 empty] | 800 | 22.86% | 2700
|  | TOTALS | 11207853.46 | 0 | 11207853.46 | 430727.04 | 785325.73 | 1448767.71 | 1069457.39 | 1367102.43 | 535818.07 | 1577307.34 |  | 9120356.62 | 81.37% | 2087496.84 | 0
3483158.25
Cash
|  |  | Loan | [10 empty] | -8787741.26
|  |  | Original Contract Sum | [14 empty] | TOTAL | 2340391.36 |  | 542236.26
Net change by approved change orders
|  |  | Contract sum to date | [14 empty] | GRAND TOTAL | 2882627.62
Total completed and stored to date
Retainage
Total earned less retainage
Less previous certificates for payment
Current Payment Due
Balance to finish with retainage

## Future Costs
Subs
| Fortified | Corbin
Ignore first CO | Fox and Hound
Will cost a bit more | Landscaping
Go with contract amount | TK
Look into rubber base | Poulson | Corbin
| Cleaners | Corbin
Add paint bills into cost & do a deduct on fox & hound | PPC
My Roof
Lara and Sons
Korey
Sunrise Elite
Douggie Fresh
Select Specialties
Toilets
Dumpsters
Shed
Security Cameras
Lock up at night security
Equipment For cabients
Pool
Exterior Building Sign
Canopies
Foundation Plaster?
Shower Solutions
Garage Doors
Parking lot signs
street sweeping
Finish labor
TST
Storefront Fixes
Bronco Fence
Urbane
Dixon Security
TK Elevator Storage
Abrams