## New Budget
Hunter's Landing Continuation Sheet
Rich Development
|  |  | Scheduled Value |  |  | 2024-08-29 | 2024-09-11 | [9 empty] | Retainage
Item # | # | DESCRIPTION OF WORK | Rich Development | Change Orders/Reallocation | Total | Draw 20 | Draw 21 | Draw 22 | Draw 23 | Draw 24 | Draw 25 | Draw 26 | Draw 27 | TOTAL COMPLETED AND STORED TO DATE | Percent Complete | BALANCE TO FINISH | Value 5%
001 | EXCAVATION/SITE | Survey | 5500 | 515 | 6015 |  |  | 1340 |  | 4675 |  |  |  | 6015 | 100% | 0
002 | EXCAVATION/SITE | Excavation | 364814.62 |  | 364814.62 |  | 11270 |  |  | 273691.84 |  |  | 97255.3 | 382217.14 | 104.8% | -17402.52 |  | 126 | -1867.52 | Kap | Invoice 10535 & 16405 should be in UDOT
003 | EXCAVATION/SITE | Concrete | 208293.28 |  | 208293.28 |  |  | 51841.53 | 16487.1 | 35355.61 |  | 23895.95 | 50216.38 | 177796.57 | 85.36% | 30496.71
004 | EXCAVATION/SITE | 12th UDOT | 17550 |  | 17550 | [7 empty] | 15535 | 15535 | 88.52% | 2015
005 | EXCAVATION/SITE | All Fencing | 44475 |  | 44475 | [7 empty] | 10035.61 | 10035.61 | 22.56% | 34439.39
006 | EXCAVATION/SITE | Track out Pad entire building | 49700 |  | 49700 | 37020 | 12680 | [6 empty] | 49700 | 100% | 0
007 | FRAME/ROOF | Turnkey Frame/Garage | 43755 | -20000 | 23755 |  |  | 16365.04 | [5 empty] | 16365.04 | 68.89% | 7389.96
008 | FRAME/ROOF | Garage Roof | 12500 |  | 12500 | [8 empty] | 0 | 0% | 12500
009 | FRAME/ROOF | Roofing L&M | 63244 |  | 63244 |  |  |  | 30100.75 |  |  | 20271.48 | 41081.98 | 91454.21 | 144.6% | -28210.21 |  | 208 | -28210.21 | Perkes Roofing | Why is this over by so much?
010 | FRAME/ROOF | Deck Coatings | 97940 |  | 97940 |  |  |  |  | 80613.2 |  |  | 10068.48 | 90681.68 | 92.59% | 7258.32
011 | FRAME/ROOF | Structural Steel-Parking | 84577 | -24000 | 60577 | [7 empty] | 5079.4 | 5079.4 | 8.385% | 55497.6
012 | FRAME/ROOF | All other Steel Features | 623901.14 | -221107.65 | 402793.49 | 15311.37 | 4548.58 | 13218.11 |  | 217159.55 |  |  | 115752.27 | 365989.88 | 90.86% | 36803.61
013 | FRAME/ROOF | Garage Door For Trash | 4500 |  | 4500 | [8 empty] | 0 | 0% | 4500
014 | FRAME/ROOF | Store Front Labor | 7500 | 5053.48 | 12553.48 |  | 7500 | 5053.48 | [5 empty] | 12553.48 | 100% | 0
015 | FRAME/ROOF | Elevator | 70150 |  | 70150 | [7 empty] | 18316.72 | 18316.72 | 26.11% | 51833.28
016 | FRAME/ROOF | HM Door Labor | 52475 | -19908.96 | 32566.04 |  |  | 1500 |  |  | 20015.96 | 10964.84 | 39584.35 | 72065.15 | 221.3% | -39499.11 |  | 106-111 | -39499.11 | Fortified Doorworks
017 | MEP TRADES | Plumbing | 524500 |  | 524500 | 60000 |  | 124504.85 | 45610.81 | 72610.06 | 38780 | 39955 | 60080 | 441540.72 | 84.18% | 82959.28
018 | MEP TRADES | HVAC | 1244900 |  | 1244900 |  |  | 204250 | 199500 | 309673.4 | 135208.75 | 85500 | 162938.3 | 1097070.45 | 88.13% | 147829.55
019 | MEP TRADES | Electric | 434737.1 |  | 434737.1 |  | 77050.11 |  | 51300 | 1500 |  |  | 118750 | 248600.11 | 57.18% | 186136.99
020 | MEP TRADES | 3 Electric Car Station | 37500 |  | 37500 | [8 empty] | 0 | 0% | 37500
021 | MEP TRADES | Sprinkler System | 168681 |  | 168681 |  | 30210.79 | 44259.74 | 15466 |  | 1406 |  | 1406 | 92748.53 | 54.98% | 75932.47
022 | MEP TRADES | Fire Caulk | 14750 |  | 14750 |  |  |  |  | 423.37 |  | 3091.66 | 9000 | 12515.03 | 84.85% | 2234.97
023 | FINISHES | Gypcrete | 152486 |  | 152486 |  | 92390.22 |  | 15200 | 20900 | 12458.92 | 232.83 | 3135 | 144316.97 | 94.64% | 8169.03
024 | FINISHES | Insulation | 222919 | -25000 | 197919 |  |  |  | 117346.28 | 1433.31 | 52303.94 | 12961.87 |  | 184045.4 | 92.99% | 13873.6
025 | FINISHES | Sheetrock | 1467345 |  | 1467345 |  |  | 526379.97 | 233987.48 | 131595 |  | 234916.69 | 137042.6 | 1263921.74 | 86.14% | 203423.26
026 | FINISHES | Finish Materials Misc | 25000 | 146985.68 | 171985.68 |  |  | 15339.63 | 5402.93 | 54571.16 | 19713.68 | 75052.45 | 29350.8 | 199430.65 | 116% | -27444.97 |  | 2025-10-22 | -27444.97 | BFS
027 | FINISHES | Finish Labor | 189135 | -50313.72 | 138821.28 |  |  | 13552 | 65952.64 | 16798.35 |  | 38930.67 | 23257.27 | 158490.93 | 114.2% | -19669.65 |  | 255 | -19669.65 | South Peak(door installer)
028 | FINISHES | Interior Paint | 303668.8 |  | 303668.8 |  |  |  | 16999.73 |  | 28686.67 | 90618.32 | 169506.27 | 305810.99 | 100.7% | -2142.19 |  | 188 | -2142.19 | Performance Painting | category is less than contract
029 | FINISHES | Equipment Cabinets | 6000 |  | 6000 | [8 empty] | 0 | 0% | 6000
030 | FINISHES | Garage Doors | 14081.4 |  | 14081.4 | [7 empty] | 15818.11 | 15818.11 | 112.3% | -1736.71 |  | 26 | -1736.71 | Overhead Doors
031 | FINISHES | Floor Prep | 10000 |  | 10000 | [7 empty] | 3673.39 | 3673.39 | 36.73% | 6326.61
032 | FINISHES | Hardware & Install Labor | 65000 |  | 65000 | [5 empty] | 6806.48 | 8876.04 | 859.58 | 16542.1 | 25.45% | 48457.9
033 | FINISHES | Fire Extinguishers | 7850 |  | 7850 | [7 empty] | 4811.75 | 4811.75 | 61.3% | 3038.25
034 | FINISHES | Mirrors | 24750 | -15000 | 9750 | [7 empty] | 6051.5 | 6051.5 | 62.07% | 3698.5
035 | FINISHES | Flooring,Wall Tile M&L | 340975 |  | 340975 |  |  |  | 99384 | 13764.08 | 17929.49 | 40993.65 | 86933.77 | 259004.99 | 75.96% | 81970.01
036 | EXTERIORS & MISC | Brick | 342000 | 9500 | 351500 |  |  | 95000 | 95000 | 66500 |  | 95000 | 81429.33 | 432929.33 | 123.2% | -81429.33 |  | 150 | -81429.33 | MC Siding | Originally 450K
037 | EXTERIORS & MISC | Stucco EFIS,Soffit,Fascia | 437274.1 |  | 437274.1 |  |  | 62353.62 |  |  | 135571.74 | 185856.68 | 185856.68 | 569638.72 | 130.3% | -132364.62 |  | 139 | -132364.62 | Lara and Sons - Exteriors | Originally 587k | CO for Hardi Fine Sand - Did we sign a CO for $12,130.32?
038 | EXTERIORS & MISC | Gutter | 10245 |  | 10245 | [8 empty] | 0 | 0% | 10245
039 | EXTERIORS & MISC | Plaster Foundation | 4250 |  | 4250 | [8 empty] | 0 | 0% | 4250
040 | EXTERIORS & MISC | Roof Hatch | 1600 |  | 1600 | [8 empty] | 0 | 0% | 1600
041 | EXTERIORS & MISC | Trash Chute | 37850 |  | 37850 | [8 empty] | 0 | 0% | 37850
042 | EXTERIORS & MISC | Pool | 257092 |  | 257092 | [7 empty] | 138008.97 | 138008.97 | 53.68% | 119083.03
043 | EXTERIORS & MISC | Knox box & Fire Lids | 2450 |  | 2450 | [7 empty] | 1272.3 | 1272.3 | 51.93% | 1177.7
044 | ALLOWANCES | Landscape | 184000 | -15000 | 169000 | [7 empty] | 78001.63 | 78001.63 | 46.15% | 90998.37
045 | ALLOWANCES | Appliances | 517942.26 |  | 517942.26 | [6 empty] | 520418.99 |  | 520418.99 | 100.5% | -2476.73 |  |  | -2476.73 | GE Appliances | Allowance
046 | ALLOWANCES | Signage | 15000 |  | 15000 | [7 empty] | 4956 | 4956 | 33.04% | 10044
047 | ALLOWANCES | All Amenities | 25000 |  | 25000 | [6 empty] | 7222.64 |  | 7222.64 | 28.89% | 17777.36
048 | ALLOWANCES | Garden Shed & Pad | 8000 |  | 8000 | [8 empty] | 0 | 0% | 8000
049 | ALLOWANCES | Blinds | 42500 |  | 42500 | [5 empty] | 26645.75 |  | 17046.65 | 43692.4 | 102.8% | -1192.4 |  |  | -1192.4 | Next Day Blinds | Allowance
050 | GENERAL | Contingency | 250000 | -43882.07 | 206117.93 | 72500 | 55251.03 |  |  |  | 2663.35 | 36080.87 | 175 | 166670.25 | 80.86% | 39447.68
051 | GENERAL | Equipment | 25000 |  | 25000 | 10000 | 15000 | [6 empty] | 25000 | 100% | 0
052 | GENERAL | Honey Bucket | 7000 |  | 7000 |  | 362.35 | 2098.2 |  | 2178.18 | 739.39 | 1478.78 | 1478.78 | 8335.68 | 119.1% | -1335.68 |  |  | -1335.68 | Honey Bucket
053 | GENERAL | Dumpster | 25000 | 815.83 | 25815.83 |  |  | 8951.43 | 4698.26 | 3953.04 | 4758.94 | 3454.16 | 17562.37 | 43378.2 | 168% | -17562.37 |  |  | -17562.37 | United Site Services & Republic Services
054 | GENERAL | Temp Fence | 6000 |  | 6000 | [8 empty] | 0 | 0% | 6000
055 | GENERAL | Clean-up Labor | 30000 |  | 30000 |  | 3400 |  | 405 | 6300 | 4110 | 180 | 9865 | 24260 | 80.87% | 5740
056 | GENERAL | Final Clean | 50000 |  | 50000 | [8 empty] | 0 | 0% | 50000
057 | GENERAL | Street Sweeping | 5000 |  | 5000 | [8 empty] | 0 | 0% | 5000
058 | GENERAL | Conc Wash Out | 5000 |  | 5000 | [8 empty] | 0 | 0% | 5000
059 | GENERAL | SWPPP/split w/cu inspections | 3500 | 140 | 3640 | 450 | 450 | 940 | 450 | 450 | 450 | 450 | 1650 | 5290 | 145.3% | -1650 |  | 87 | -1650 | Cearley | Over on time
060 | GENERAL | Temp Power | 7500 |  | 7500 | 216.17 | 122.62 | 3037.71 | 152.71 | 68.62 | 368.53 | 991.77 | 838.76 | 5796.89 | 77.29% | 1703.11
061 | GENERAL | Office Trailer | 15000 |  | 15000 |  |  | 100 | 2146.73 | 4216.08 |  |  | 538.58 | 7001.39 | 46.68% | 7998.61
062 | GENERAL | Security Cameras | 30000 |  | 30000 |  | 5641.15 | 1128.23 | 1128.23 |  | 4525.48 |  | 3928.23 | 16351.32 | 54.5% | 13648.68
063 | GENERAL | Special Inspections | 15000 |  | 15000 | 5742.5 | 4661.18 |  |  | 3490 | 500 |  |  | 14393.68 | 95.96% | 606.32
064 | GENERAL | Saftey | 10000 | -5000 | 5000 | [8 empty] | 0 | 0% | 5000
065 | GENERAL | General Conditions | 30000 |  | 30000 |  | 779.31 |  |  | 3135.08 |  |  | 8469.08 | 12383.47 | 41.28% | 17616.53
066 | GENERAL | Insurance Not Builders | 25000 |  | 25000 |  | 19.98 | [6 empty] | 19.98 | 0.07992% | 24980.02
067 | GENERAL | Site Supervision | 240000 |  | 240000 | 25000 | 20000 | 41500 | 29000 | 23375 | 22175 | 22175 | 60525 | 243750 | 101.6% | -3750 |  |  | -3750 | Rich Development | Why is this over?
068 | GENERAL | Construction Profit | 6583.94 |  | 6583.94 | [8 empty] | 0 | 0% | 6583.94
069 | GENERAL | Exterior Wall Project | 483915.5 | 276202.41 | 760117.91 | 204487 | 279428.5 | 216054.17 | 23738.74 | 18672.5 |  | 17737 | 74243.72 | 834361.63 | 109.8% | -74243.72 |  |  | -74243.72 | Metro Porcelain & Fiberglass, Kap moving materials, Webb Windows, RP Framing, | Almost all related to windows
|  | TOTALS | 10159856.14 | 0 | 10159856.14 | 430727.04 | 620765.82 | 1448767.71 | 1069457.39 | 1367102.43 | 535818.07 | 1577307.34 | 1921385.91 | 8971331.71 | 88.3% | 1188524.43 | 0
| GENERAL | 1st MTG IR | 494000 |  | 494000 |  | 163759.91 | [6 empty] | 163759.91 | 33.15% | 330240.09
| GENERAL | 2nd MTG IR | 550497.32 |  | 550497.32 | [8 empty] | 0 | 0% | 550497.32
| GENERAL | Inspections | 3500 |  | 3500 |  | 800 | [6 empty] | 800 | 22.86% | 2700
|  | TOTALS | 11207853.46 | 0 | 11207853.46 | 430727.04 | 785325.73 | 1448767.71 | 1069457.39 | 1367102.43 | 535818.07 | 1577307.34 |  | 9135891.62 | 81.51% | 2071961.84 | 0
3498693.25
Cash
|  |  | Loan | [10 empty] | -8803276.26
Original Contract Sum
Net change by approved change orders
Contract sum to date
Total completed and stored to date
Retainage
Total earned less retainage
Less previous certificates for payment
Current Payment Due
Balance to finish with retainage