## Sheet 1 (hidden)
HUNTERS LANDING PAYMENTS |  |  |  | Demo |  | NOT DEMO (OLD BILLS) | CO's | Extra demo
mostly Makers Line old bills
DRAW 1
Rich Dev |  | toilet |  | 340.03
Rich Dev |  | permit to city |  |  |  | 1843.04
Boardwalk |  | demo draw |  | 80802.65
Epic |  | shoring eng | [5 empty] | 12620
Rich Dev |  | Nov-Dec super |  | 25000
Fox |  | draw | old bills |  |  | 78072.18
Atlas |  | old dumpster bills |  |  |  | 7630.41
DRAW 2
Sepect specialties |  | old bills |  |  |  | 29365.25
Foundation Building |  | old bills |  |  |  | 96853.21
Triple BBB |  | old bills |  |  |  | 8998.17
TK |  | old bills |  |  |  | 4601.25
Wilcox |  | old bills |  |  |  | 37120.44
Rich Dev |  | GC's |  | 22708.06
Keith Kap |  | track out pad, |  |  |  | 61154.15
SCS |  | Cabinets |  |  |  | 82535.5
Rich Dev |  | demo, move rock, lumber |  | 40990.84
DRAW 3 (Feb)
Boardwalk |  | demo framing |  | 201669.64
Epic |  | framing fix's | [5 empty] | 3389.26
RMP |  | power bill |  | 11.13
Rich Dev |  | lumber |  | 14534.2
Elite plumbing (pre-pay finish materials) |  | plumbing from bid |  |  |  | 205000
Rich Dev |  | GC's |  | 20000
Draw 4 (April)
Boardwalk |  | demo-framing |  | 317608.99
Rich Dev |  | lumber |  | 34419.09
Rich Dev |  | RMP bill |  | 273.57
Kap |  | dumpsters, shoring |  | 86278.52
RMP |  | 2nd power bill |  | 22.39
Epic |  | framing fix's | [5 empty] | 2023.75
Honey Bucket |  |  |  | 999.26
Rich Dev |  | Peak fastners hardware |  | 19001.02
Rich Dev |  | GC's |  | 26272.83
Silverleaf |  | Old SWPPP bills |  |  |  | 11725
Draw 5 (May)
Boardwalk |  | demo-framing |  | 302190.2
Rich Dev |  | peak-FRT |  | 103785.27
Rich Dev |  | GC's |  | 26365.15
Kap |  | dumpster |  | 34120
Elite | [5 empty] | 68440 | 19125
CEARLEY SWPPP |  |  |  | 605
draw 6 (June)
BOARDWALK |  | DEMO, FRAMING, SHORING |  | 643399.5
BOARDWALK |  | FRT MATERIALS |  | 204106.45
RICH DEV GC'S |  | TOILET, FENCE, SUPERVISION |  | 26672.04
ELITE PLUMBING |  | REPLACE CRACKED TUBS |  |  |  |  | 34646
CEARLEY SWPPP |  |  |  | 450
DELTA DEMO |  | DEMO SPRINKLERS |  | 4000
draw 7 (July)
Peak Fasteners |  | Framing hardware |  | 12332.97
Elite plumbing |  | testing & repairs & fire collars |  |  |  |  | 14680.67
Elite plumbing |  | plumbing draw |  |  |  | 7000
Boardwalk |  | framing & demo draw |  | 346987
TST |  | fire sprinklers draw |  |  |  | 123873
Keith Kap & Sons |  | Demo haul off |  | 37020
Cearley SWPPP |  |  |  | 450
CMT testing |  | city required inspections |  |  |  |  | 2430
Salmon HVAC |  | hvac draw |  |  |  | 52500
Epic |  | shoring engineering |  |  |  |  | 3312.5
Fox & Hound Elec |  | Elec draw (old invoices) |  |  |  | 26767.75
Rich Dev GC's |  | demo materials, power, supervision
draw 8 (August)
Rich Development
BFS | 75883922-00 | Simpson 150' 16GA Coil Strap |  | 188.78
| 75898716-00 | Simpson 20" HVY Twist Strap |  | 209.67
| 75911676-00 | Simpson 25' 16GA Coil Strap , Simpson 20" HVY Twist Strap |  | 380.86
Epic Engineering | 20241735 | Shoring Plan | [5 empty] | 102.5
| 20241558 | Shoring Plan | [5 empty] | 986.25
| 20240958 | Shoring Plan | [5 empty] | 3572.43
LVT | AR292963 | Security |  | 1128.23
| AR305106 | Security |  | 1128.23
| AR317565 | Security |  | 1128.23
Boardwalk | 0408 | Framing Labor & Material |  | 252088.92
| 0407 | Framing Labor & Material |  | 108751.67
Evolution | 10207 | Store front pull out and reinstall |  | 9179.42 | Retention
| 10207 | Balance Original Job |  |  | Retention | 4874.08
| 994 | Store front pull out and reinstall |  | 9179.41 | Retention
Fox & Hound | 35170 | Wire removal from exterior walls |  | 6136.05 | Retention
| 35217 | Rewire Units & Ser |  |  | Retention | 48041.21
Keith Kap & Sons Excavating | 16095 | Debris Haul Off |  | 23950
Peak Fasteners, Inc. | 282760 | Hardware |  | 989.35
| 282757 | Hardware |  | 963.98
| 282758 | Hardware |  | 2291.07
| 282759 | Hardware |  | 304.18
draw 9 (Sept/Oct)
Rich Development Inc
CMT | 118349 | Nailing Inspections |  | 1340
Peak Fasteners | 281417 | Hardware |  | 352.1
| 281418 | Hardware |  | 310.68
| 281782 | Hardware |  | 2916.45
| 284506 | Hardware |  | 523.7
| 286212 | Hardware |  | 1048.15
| 286633 | Hardware |  | 786.03
Wheelright Lumber | 2405-126496 | Lumber |  | 204.53
| 2405-126548 | Tvek |  | 89.44
Boardwalk | 0434 | Framing Labor & Material |  | 98198.01
| 0435 | Framing Labor & Material |  | 37611.1
| 0476 | Framing Labor & Material |  | 49995
Elite Plumbing | 1055 | Testing T&M |  |  |  |  | 38067.11
| 1057 | Testing T&M |  |  |  |  | 44634.04
Evolution | 10227 | Cutting Down Aluminium Frame |  | 5053.48
Lara & Sons | 1876 | Window Install |  | 28373.32
draw 10 (Nov)
Boardwalk | 0499 | Framing Labor & Materials |  | 12925
Elite Plumbing | 1058 | Testing T&M |  |  |  |  | 37930.81
draw 11 (Dec)
Boardwalk | 0523 | Framing Labor & Materials |  | 18672.5
Elite Plumbing | 1059 | Testing T&M |  |  |  |  | 12285.06
draw 13 (Feb)
RP Framing | 1027 | Framing Fixes |  |  |  |  | 4507
| 1030 | Framing Fixes |  |  |  |  | 13230
draw 13 (March)
RP Framing | 1032 | Framing Fixes |  |  |  |  | 2895
TOTAL SO FAR |  |  |  | 3309813.34 |  | 956394.64 | 227743.19 | 22694.19 | 4516645.36
Retention Not Paid
Evolution | Original ML Storefront Glass | [6 empty] | 3710.2
| Change Orders – Makers Line | [6 empty] | 2158.41
| Change Order – Pull out and Reinstall Storefront | [6 empty] | 966.25
Fox & Hound | Wire removal from exterior walls | [6 empty] | 322.95
| Re-wire units & re-pull SER | [6 empty] | 2528.49
TOTAL | [7 empty] | 9686.3

## Revised Version
HUNTERS LANDING PAYMENTS | INVOICE # |  | Demo | T&M Outside of Demo | Engineering | NOT DEMO (OLD BILLS) | Track-out | Notes
|  |  |  | Items fixed due to Maker's Line issues |  | mostly Makers Line old bills
DRAW 1 (Jan) | INVOICE #
Rich Dev |  | toilet | 340.03
Rich Dev |  | permit to city | 1843.04
Boardwalk |  | demo draw | 80802.65
Epic |  | shoring eng | 12620 |  |  |  |  | Has a line item in original contract
Rich Dev |  | Nov-Dec super | 25000
Fox |  | draw |  |  |  | 78072.18 |  | Bill from 6/16/2023
Atlas |  | Dumpster |  |  |  | 4104.02 |  | Bills from 08/31/2023 & 09/30/2023
|  | Dumpster | 3526.09
DRAW 2 (Feb)
Select specialties |  | Postal Specialties, Fire Protection, Facility Chutes |  |  |  | 29365.25 |  | Bills from 11/21/2022, 2/17/2023, & 4/12/2023
Foundation Building |  | Foundation Building Materials |  |  |  | 96853.21 |  | Previous amount fro Maker's Line. In an email from Kyle Wilson
Triple BBB |  | Rough Grade Parking Lot, UDOT |  |  |  | 8998.17 |  | Bill from 1/8/2024
TK Elevator |  | Partial of previous amount |  |  |  | 4601.25 |  | Previous amount fro Maker's Line. In an email from Kyle Wilson
Wilcox |  | Material and Transport Fee |  |  |  | 37120.44 |  | Previous amount fro Maker's Line. In an email from Kyle Wilson
Rich Dev |  | GC's | 22708.06
Keith Kap |  | track out pad, |  |  |  |  | 61154.15
SCS |  | Cabinets |  |  |  | 82535.5 |  | Bill from 10/03/2023
Rich Dev |  | demo, move rock, lumber | 40990.84
DRAW 3 (Mar)
Boardwalk |  | demo framing | 201669.64
Epic |  | framing fix's |  |  | 3389.26 |  |  | Not included in original demo number
RMP |  | power bill | 11.13
Rich Dev |  | lumber | 14534.2
Rich Dev |  | GC's | 20000
Draw 4 (April)
Boardwalk |  | demo-framing | 317608.99
Rich Dev |  | lumber | 34419.09
Kap |  | dumpsters, shoring | 86278.52
RMP |  | 2nd power bill | 22.39
Epic |  | framing fix's |  |  | 2203.75 |  |  | Not included in original demo number
Rich Dev |  | Peak fastners hardware | 23552.34
Rich Dev |  | GC's | 26272.83
Silverleaf |  | Old SWPPP bills |  |  |  | 11725 |  | Old bill from Maker's Line
Draw 5 (May)
Boardwalk |  | demo-framing | 302190.2
Rich Dev |  | peak-FRT | 103785.27
Rich Dev |  | GC's | 26365.15
Kap |  | dumpster | 34120
Elite | 1046 | Laundry Floor Drains |  | 19125 |  |  |  | Interior pipe fixes
CEARLEY SWPPP |  | SWPPP | 605
draw 6 (June)
BOARDWALK |  | DEMO, FRAMING, SHORING | 643394.5
BOARDWALK |  | FRT MATERIALS | 204106.45
BMC |  | FRT MATERIALS | 3987.43
RICH DEV GC'S |  | TOILET, FENCE, SUPERVISION | 26672.04
UNITED RENTALS |  |  | 1736.8
ELITE PLUMBING |  | REPLACE CRACKED TUBS |  | 34646 |  |  |  | Interior fixes from previous damage
CEARLEY SWPPP |  |  | 430
DELTA DEMO |  | DEMO SPRINKLERS | 4000
draw 7 (July)
Peak Fasteners |  | Framing hardware | 12332.97
Boardwalk |  | framing & demo draw | 346987
Keith Kap & Sons |  | Demo haul off | 37020
Cearley SWPPP |  | SWPPP | 450
CMT testing |  | city required inspections |  | 2430
Epic |  | shoring engineering |  |  | 3312.5
Rich Dev GC's |  | demo materials, power, supervision | 28194.57
draw 8 (August)
Rich Development
BFS | 75883922-00 | Simpson 150' 16GA Coil Strap | 188.78
| 75898716-00 | Simpson 20" HVY Twist Strap | 209.67
| 75911676-00 | Simpson 25' 16GA Coil Strap , Simpson 20" HVY Twist Strap | 380.86
Epic Engineering | 20241735 | Shoring Plan |  |  | 102.5 |  |  | Not included in original demo number
| 20241558 | Shoring Plan |  |  | 986.25 |  |  | Not included in original demo number
| 20240958 | Shoring Plan |  |  | 3572.43 |  |  | Not included in original demo number
LVT | AR292963 | Security | 1128.23
| AR305106 | Security | 1128.23
| AR317565 | Security | 1128.23
Boardwalk | 0408 | Framing Labor & Material | 252088.92
| 0407 | Framing Labor & Material | 108751.67
Evolution | 10207 | Store front pull out and reinstall | 9179.42
| 10207 | Balance Original Job |  |  |  | 4874.08 |  | Unpaid balance from Maker's Line
| 994 | Store front pull out and reinstall | 9179.41
Fox & Hound | 35170 | Wire removal from exterior walls | 6136.05
| 35217 | Rewire Units & Ser |  | 48041.21 |  |  |  | Interior Fixes
Keith Kap & Sons Excavating | 16095 | Debris Haul Off | 23950
Peak Fasteners, Inc. | 282760 | Hardware | 989.35
| 282757 | Hardware | 963.98
| 282758 | Hardware | 2291.07
| 282759 | Hardware | 304.18
draw 9 (Sept/Oct) (22)
Rich Development Inc
CMT | 118349 | Nailing Inspections | 1340
Peak Fasteners | 281417 | Hardware | 352.1
| 281418 | Hardware | 310.68
| 281782 | Hardware | 2916.45
| 284506 | Hardware | 523.7
| 286212 | Hardware | 1048.15
| 286633 | Hardware | 786.03
Wheelright Lumber | 2405-126496 | Lumber | 204.53
| 2405-126548 | Tvek | 89.44
Boardwalk | 0434 | Framing Labor & Material | 98198.01
| 0435 | Framing Labor & Material | 37611.1
| 0476 | Framing Labor & Material | 49995
Elite Plumbing | 1055 | Testing T&M |  | 38067.11 |  |  |  | Interior pipe fixes
| 1057 | Testing T&M |  | 44634.04 |  |  |  | Interior pipe fixes
Evolution | 10227 | Cutting Down Aluminium Frame | 5053.48
Lara & Sons | 1876 | Window Install | 28373.32
draw 10 (Nov)
Boardwalk | 0499 | Framing Labor & Materials |  | 12925 |  |  |  | Interior Framing Fixes
Elite Plumbing | 1058 | Testing T&M |  | 37930.81 |  |  |  | Interior pipe fixes
draw 11 (Dec)
Boardwalk | 0523 | Framing Labor & Materials |  | 18672.5 |  |  |  | Interior Framing Fixes
Elite Plumbing | 1059 | Testing T&M |  | 12285.06 |  |  |  | Interior pipe fixes
draw 13 (Feb)
RP Framing | 1027 | Framing Fixes |  | 4507 |  |  |  | Interior Framing Fixes
| 1030 | Framing Fixes |  | 13230 |  |  |  | Interior Framing Fixes
draw 13 (March)
RP Framing | 1032 | Framing Fixes |  | 2895 |  |  |  | Interior Framing Fixes
TOTAL SO FAR |  |  | 3333377.26 | 289388.73 | 13566.69 | 358249.1 | 61154.15 |  | 4055735.93
Retention Not Paid
Evolution |  | Original ML Storefront Glass |  |  |  |  | 3710.2
|  | Change Orders – Makers Line |  |  |  |  | 2158.41
|  | Change Order – Pull out and Reinstall Storefront |  |  |  |  | 966.25
Fox & Hound |  | Wire removal from exterior walls |  |  |  |  | 322.95
|  | Re-wire units & re-pull SER |  |  |  |  | 2528.49
TOTAL | [6 empty] | 9686.3