## Sheet1
HUNTERS LANDING PAYMENTS |  | Demo | Not demo (old bills) | CO's | Extra demo
[6 empty] | Boardwalk demo-framing | RFT Lumber Hardware
DRAW 1 | [5 empty] | 80802.65 | 40990.84
Rich Dev | toilet | 340.03 |  |  |  | 201669.64 | 14534.2
Rich Dev | permit to city |  | 1843.04 |  |  | 317608.99 | 34419.09
Boardwalk | demo draw | 80802.65 |  |  |  | 302190.2 | 103785.27
Epic | shoring eng | 12620 |  |  |  | 643399.5 | 204106.45
Rich Dev | Nov-Dec super | 25000
Fox | draw |  | 78072.18
Atlas | old dumpster bills |  | 7630.41
DRAW 2 | [5 empty] | 1545670.98 | 397835.85
Sepect specialties | old bills |  | 29365.25
Foundation Building | old bills |  | 96853.21
Triple BBB | old bills |  | 8998.17
TK | old bills |  | 4601.25
Wilcox | old bills |  | 37120.44
Rich Dev | GC's | 22708.06
Keith Kap | track out pad, |  | 61154.15
SCS | Cabinets |  | 82535.5
Rich Dev | demo, move rock, lumber | 40990.84
DRAW 3 (Feb)
Boardwalk | demo framing | 201669.64
Epic | framing fix's |  |  |  | 3389.26
RMP | power bill | 11.13
Rich Dev | lumber | 14534.2
Elite plumbing | plumbing from bid |  | 205000
Rich Dev | GC's | 20000
Draw 4 (April)
Boardwalk | demo-framing | 317608.99
Rich Dev | lumber | 34419.09
Rich Dev | RMP bill | 273.57
Kap | dumpsters, shoring | 86278.52
RMP | 2nd power bill | 22.39
Epic | framing fix's |  |  |  | 2023.75
Honey Bucket |  | 999.26
Rich Dev | Peak fastners hardware | 19001.02
Rich Dev | GC's | 26272.83
Silverleaf | Old SWPPP bills |  | 11725
Draw 5 (May)
Boardwalk | demo-framing | 302190.2
Rich Dev | peak-FRT | 103785.27
Rich Dev | GC's | 26365.15
Kap | dumpster | 34120
Elite |  |  | 68440 | 19125
CEARLEY SWPPP |  | 605
draw 6 (June)
BOARDWALK | DEMO, FRAMING, SHORING | 643399.5
BOARDWALK | FRT MATERIALS | 204106.45
RICH DEV GC'S | TOILET, FENCE, SUPERVISION | 26672.04
ELITE PLUMBING | REPLACE CRACKED TUBS |  |  | 34646
CEARLEY SWPPP |  | 450
DELTA DEMO | DEMO SPRINKLERS | 4000
TOTAL SO FAR |  | 2249245.83 | 693338.6 | 53771 | 5413.01 | 3001768.44