## Sheet 1 (hidden)
HUNTERS LANDING PAYMENTS |  |  |  | Demo |  | NOT DEMO (OLD BILLS) | CO's | Extra demo
mostly Makers Line old bills
DRAW 1
Rich Dev |  | toilet |  | 340.03
Rich Dev |  | permit to city |  |  |  | 1843.04
Boardwalk |  | demo draw |  | 80802.65
Epic |  | shoring eng | [5 empty] | 12620
Rich Dev |  | Nov-Dec super |  | 25000
Fox |  | draw | old bills |  |  | 78072.18
Atlas |  | old dumpster bills |  |  |  | 7630.41
DRAW 2
Sepect specialties |  | old bills |  |  |  | 29365.25
Foundation Building |  | old bills |  |  |  | 96853.21
Triple BBB |  | old bills |  |  |  | 8998.17
TK |  | old bills |  |  |  | 4601.25
Wilcox |  | old bills |  |  |  | 37120.44
Rich Dev |  | GC's |  | 22708.06
Keith Kap |  | track out pad, |  |  |  | 61154.15
SCS |  | Cabinets |  |  |  | 82535.5
Rich Dev |  | demo, move rock, lumber |  | 40990.84
DRAW 3 (Feb)
Boardwalk |  | demo framing |  | 201669.64
Epic |  | framing fix's | [5 empty] | 3389.26
RMP |  | power bill |  | 11.13
Rich Dev |  | lumber |  | 14534.2
Elite plumbing (pre-pay finish materials) |  | plumbing from bid |  |  |  | 205000
Rich Dev |  | GC's |  | 20000
Draw 4 (April)
Boardwalk |  | demo-framing |  | 317608.99
Rich Dev |  | lumber |  | 34419.09
Rich Dev |  | RMP bill |  | 273.57
Kap |  | dumpsters, shoring |  | 86278.52
RMP |  | 2nd power bill |  | 22.39
Epic |  | framing fix's | [5 empty] | 2023.75
Honey Bucket |  |  |  | 999.26
Rich Dev |  | Peak fastners hardware |  | 19001.02
Rich Dev |  | GC's |  | 26272.83
Silverleaf |  | Old SWPPP bills |  |  |  | 11725
Draw 5 (May)
Boardwalk |  | demo-framing |  | 302190.2
Rich Dev |  | peak-FRT |  | 103785.27
Rich Dev |  | GC's |  | 26365.15
Kap |  | dumpster |  | 34120
Elite | [5 empty] | 68440 | 19125
CEARLEY SWPPP |  |  |  | 605
draw 6 (June)
BOARDWALK |  | DEMO, FRAMING, SHORING |  | 643399.5
BOARDWALK |  | FRT MATERIALS |  | 204106.45
RICH DEV GC'S |  | TOILET, FENCE, SUPERVISION |  | 26672.04
ELITE PLUMBING |  | REPLACE CRACKED TUBS |  |  |  |  | 34646
CEARLEY SWPPP |  |  |  | 450
DELTA DEMO |  | DEMO SPRINKLERS |  | 4000
draw 7 (July)
Peak Fasteners |  | Framing hardware |  | 12332.97
Elite plumbing |  | testing & repairs & fire collars |  |  |  |  | 14680.67
Elite plumbing |  | plumbing draw |  |  |  | 7000
Boardwalk |  | framing & demo draw |  | 346987
TST |  | fire sprinklers draw |  |  |  | 123873
Keith Kap & Sons |  | Demo haul off |  | 37020
Cearley SWPPP |  |  |  | 450
CMT testing |  | city required inspections |  |  |  |  | 2430
Salmon HVAC |  | hvac draw |  |  |  | 52500
Epic |  | shoring engineering |  |  |  |  | 3312.5
Fox & Hound Elec |  | Elec draw (old invoices) |  |  |  | 26767.75
Rich Dev GC's |  | demo materials, power, supervision
draw 8 (August)
Rich Development
BFS | 75883922-00 | Simpson 150' 16GA Coil Strap |  | 188.78
| 75898716-00 | Simpson 20" HVY Twist Strap |  | 209.67
| 75911676-00 | Simpson 25' 16GA Coil Strap , Simpson 20" HVY Twist Strap |  | 380.86
Epic Engineering | 20241735 | Shoring Plan | [5 empty] | 102.5
| 20241558 | Shoring Plan | [5 empty] | 986.25
| 20240958 | Shoring Plan | [5 empty] | 3572.43
LVT | AR292963 | Security |  | 1128.23
| AR305106 | Security |  | 1128.23
| AR317565 | Security |  | 1128.23
Boardwalk | 0408 | Framing Labor & Material |  | 252088.92
| 0407 | Framing Labor & Material |  | 108751.67
Evolution | 10207 | Store front pull out and reinstall |  | 9179.42 | Retention
| 10207 | Balance Original Job |  |  | Retention | 4874.08
| 994 | Store front pull out and reinstall |  | 9179.41 | Retention
Fox & Hound | 35170 | Wire removal from exterior walls |  | 6136.05 | Retention
| 35217 | Rewire Units & Ser |  |  | Retention | 48041.21
Keith Kap & Sons Excavating | 16095 | Debris Haul Off |  | 23950
Peak Fasteners, Inc. | 282760 | Hardware |  | 989.35
| 282757 | Hardware |  | 963.98
| 282758 | Hardware |  | 2291.07
| 282759 | Hardware |  | 304.18
draw 9 (Sept/Oct)
Rich Development Inc
CMT | 118349 | Nailing Inspections |  | 1340
Peak Fasteners | 281417 | Hardware |  | 352.1
| 281418 | Hardware |  | 310.68
| 281782 | Hardware |  | 2916.45
| 284506 | Hardware |  | 523.7
| 286212 | Hardware |  | 1048.15
| 286633 | Hardware |  | 786.03
Wheelright Lumber | 2405-126496 | Lumber |  | 204.53
| 2405-126548 | Tvek |  | 89.44
Boardwalk | 0434 | Framing Labor & Material |  | 98198.01
| 0435 | Framing Labor & Material |  | 37611.1
| 0476 | Framing Labor & Material |  | 49995
Elite Plumbing | 1055 | Testing T&M |  |  |  |  | 38067.11
| 1057 | Testing T&M |  |  |  |  | 44634.04
Evolution | 10227 | Cutting Down Aluminium Frame |  | 5053.48
Lara & Sons | 1876 | Window Install |  | 28373.32
draw 10 (Nov)
Boardwalk | 0499 | Framing Labor & Materials |  | 12925
Elite Plumbing | 1058 | Testing T&M |  |  |  |  | 37930.81
draw 11 (Dec)
Boardwalk | 0523 | Framing Labor & Materials |  | 18672.5
Elite Plumbing | 1059 | Testing T&M |  |  |  |  | 12285.06
draw 13 (Feb)
RP Framing | 1027 | Framing Fixes |  |  |  |  | 4507
| 1030 | Framing Fixes |  |  |  |  | 13230
draw 13 (March)
RP Framing | 1032 | Framing Fixes |  |  |  |  | 2895
TOTAL SO FAR |  |  |  | 3309813.34 |  | 956394.64 | 227743.19 | 22694.19 | 4516645.36
Retention Not Paid
Evolution | Original ML Storefront Glass | [6 empty] | 3710.2
| Change Orders – Makers Line | [6 empty] | 2158.41
| Change Order – Pull out and Reinstall Storefront | [6 empty] | 966.25
Fox & Hound | Wire removal from exterior walls | [6 empty] | 322.95
| Re-wire units & re-pull SER | [6 empty] | 2528.49
TOTAL | [7 empty] | 9686.3

## Revised Version
HUNTERS LANDING PAYMENTS |  | Demo | T&M Outside of Demo | Extra demo | NOT DEMO (OLD BILLS) | Change Orders | Notes
|  |  | Items fixed due to Maker's Line issues |  | mostly Makers Line old bills
DRAW 1
Rich Dev | toilet | 340.03
Rich Dev | permit to city | 1843.04
Boardwalk | demo draw | 80802.65
Epic | shoring eng |  |  | 12620 |  |  | Not included in original demo number
Rich Dev | Nov-Dec super | 25000
Fox | draw |  |  |  | 78072.18 |  | Old Bills
Atlas | old dumpster bills |  |  |  | 7630.41
| Insurance |  |  |  | 105417
311725.31
DRAW 2
Select specialties | old bills |  |  |  | 29365.25
Foundation Building | old bills |  |  |  | 96853.21
Triple BBB | old bills |  |  |  | 8998.17
TK ? | old bills |  |  |  | 4601.25
Wilcox | old bills |  |  |  | 37120.44
Rich Dev | GC's | 22708.06
Keith Kap | track out pad, |  |  |  |  | 61154.15 |  | Not part of fixing ML work
SCS | Cabinets |  |  |  | 82535.5 |  |  | I don't see this in the draw.
Rich Dev | demo, move rock, lumber | 40990.84
384326.87
DRAW 3 (Feb)
Boardwalk | demo framing | 201669.64
Epic | framing fix's |  |  | 3389.26 |  |  | Not included in original demo number
RMP | power bill | 11.13
Rich Dev | lumber | 14534.2
Rich Dev | GC's | 20000
[7 empty] | 239604.23 | 205000 | 444604.23
Draw 4 (April)
Boardwalk | demo-framing | 317608.99
Rich Dev | lumber | 34419.09
Rich Dev | RMP bill | 273.57
Kap | dumpsters, shoring | 86278.52
RMP | 2nd power bill | 22.39
Epic | framing fix's |  |  | 2023.75 |  |  | Not included in original demo number
Honey Bucket |  | 999.26
Rich Dev | Peak fastners hardware | 19001.02
Rich Dev | GC's | 26272.83
Silverleaf | Old SWPPP bills |  |  |  | 11725
[7 empty] | 498624.42 | 502082.91 | 3458.49
Draw 5 (May)
Boardwalk | demo-framing | 302190.2
Rich Dev | peak-FRT | 103785.27
Rich Dev | GC's | 26365.15
Kap | dumpster | 34120
Elite |  |  | 19125 |  | 68440 |  | Interior pipe fixes
CEARLEY SWPPP |  | 605
554630.62
draw 6 (June)
BOARDWALK | DEMO, FRAMING, SHORING | 643399.5
BOARDWALK | FRT MATERIALS | 204106.45
RICH DEV GC'S | TOILET, FENCE, SUPERVISION | 26672.04
ELITE PLUMBING | REPLACE CRACKED TUBS |  | 34646 |  |  |  | Interior pipe fixes | Cracked Tubs
CEARLEY SWPPP |  | 450
DELTA DEMO | DEMO SPRINKLERS | 4000
[7 empty] | 913273.99 | 918973.22 | 5699.23
draw 7 (July)
Peak Fasteners | Framing hardware | 12332.97
Elite plumbing | testing & repairs & fire collars |  | 14680.67 |  |  |  | Interior pipe fixes
Elite plumbing | plumbing draw |  |  |  | 7000
Boardwalk | framing & demo draw | 346987
TST | fire sprinklers draw |  |  |  | 123873
Keith Kap & Sons | Demo haul off | 37020
Cearley SWPPP |  | 450
CMT testing | city required inspections |  | 2430
Salmon HVAC | hvac draw |  |  |  | 52500
Epic | shoring engineering |  |  | 3312.5
Fox & Hound Elec | Elec draw (old invoices) |  |  |  | 26767.75
Rich Dev GC's | demo materials, power, supervision
[7 empty] | 627353.89 | 183373
draw 8 (August)
Rich Development
BFS | Simpson 150' 16GA Coil Strap | 188.78
| Simpson 20" HVY Twist Strap | 209.67
| Simpson 25' 16GA Coil Strap , Simpson 20" HVY Twist Strap | 380.86
Epic Engineering | Shoring Plan |  |  | 102.5 |  |  | Not included in original demo number
| Shoring Plan |  |  | 986.25 |  |  | Not included in original demo number
| Shoring Plan |  |  | 3572.43 |  |  | Not included in original demo number
LVT | Security | 1128.23
| Security | 1128.23
| Security | 1128.23
Boardwalk | Framing Labor & Material | 252088.92
| Framing Labor & Material | 108751.67
Evolution | Store front pull out and reinstall | 9179.42
| Balance Original Job |  |  |  | 4874.08 |  | Unpaid balance from Maker's Line
| Store front pull out and reinstall | 9179.41
Fox & Hound | Wire removal from exterior walls | 6136.05
| Rewire Units & Ser |  | 48041.21 |  |  |  |  | What is this?
Keith Kap & Sons Excavating | Debris Haul Off | 23950
Peak Fasteners, Inc. | Hardware | 989.35
| Hardware | 963.98
| Hardware | 2291.07
| Hardware | 304.18
475574.52
draw 9 (Sept/Oct)
Rich Development Inc
CMT | Nailing Inspections | 1340
Peak Fasteners | Hardware | 352.1
| Hardware | 310.68
| Hardware | 2916.45
| Hardware | 523.7
| Hardware | 1048.15
| Hardware | 786.03
Wheelright Lumber | Lumber | 204.53
| Tvek | 89.44
Boardwalk | Framing Labor & Material | 98198.01
| Framing Labor & Material | 37611.1
| Framing Labor & Material | 49995
Elite Plumbing | Testing T&M |  | 38067.11 |  |  |  | Interior pipe fixes
| Testing T&M |  | 44634.04 |  |  |  | Interior pipe fixes
Evolution | Cutting Down Aluminium Frame | 5053.48
Lara & Sons | Window Install | 28373.32
309503.14
draw 10 (Nov)
Boardwalk | Framing Labor & Materials |  | 12925 |  |  |  | Interior Framing Fixes | How is this not in the original scope?
Elite Plumbing | Testing T&M |  | 37930.81 |  |  |  | Interior pipe fixes
draw 11 (Dec)
Boardwalk | Framing Labor & Materials |  | 18672.5 |  |  |  | Interior Framing Fixes | How is this not in the original scope?
Elite Plumbing | Testing T&M |  | 12285.06 |  |  |  | Interior pipe fixes
draw 13 (Feb)
RP Framing | Framing Fixes |  | 4507 |  |  |  | Interior Framing Fixes | How is this not in the original scope?
| Framing Fixes |  | 13230 |  |  |  | Interior Framing Fixes | How is this not in the original scope?
draw 13 (March)
RP Framing | Framing Fixes |  | 2895 |  |  |  | Interior Framing Fixes | How is this not in the original scope?
TOTAL SO FAR |  | 3309813.34 | 227743.19 | 22694.19 | 895240.49 |  |  | 4455491.21