## Sheet1
Hunters Landing Budget Tracking - Rich Development
Scheduled Value
[5 empty] | Draw 1 | Draw 2 | Draw 3 | Draw 4 | Draw 5 | Draw 6 | Billed to Date | Percent Complete | Remaining
07-0130 | Stucco/ Siding | REPLACE TYVEK ENTIRE EXTERIOR |  | 45000 | [6 empty] | 0 | 0% | 45000
02-0290 | On-Site Demolition |  |  | 30000 | [6 empty] | 0 | 0% | 30000
02-0290 | On-Site Demolition | DEMO BRICK |  | 8000 | [6 empty] | 0 | 0% | 8000
04-1930 | Masonry | 8 LOADS OF BRICK TO THE DUMP |  | 110000 | [6 empty] | 0 | 0% | 110000
02-0290 | On-Site Demolition | DEMO ALL WINDOWS & EXT DOORS |  | 35000 | [6 empty] | 0 | 0% | 35000
08-0300 | Windows | REPLACE BROKEN WINDOWS |  | 15000 | [6 empty] | 0 | 0% | 15000
02-0290 | On-Site Demolition | DEMO 100% OF EXISTING FRAMING & LUMBER |  | 170000 | Draw 1: 80802.65; Draw 4: 144249.95 | 225052.6 | 132.4% | -55052.6
02-0290 | On-Site Demolition | 50 LOADS TO THE DUMP, EXTERIOR WALLS (GUESS) |  | 50000 | Draw 5: 34120 | 34120 | 68.24% | 15880
02-0290 | On-Site Demolition | REMOVE ALL ELECTRICIAL FROM EXTERIOR WALLS |  | 10000 | [6 empty] | 0 | 0% | 10000
02-0290 | On-Site Demolition | REMOVE ALL SPRINKLERS FROM EXTERIOR WALLS & DECKS |  | 30000 | Draw 6: 4000 | 4000 | 13.33% | 26000
06-0170 | Rough Carpentry | NEW LUMBER TO REBUILD COMPLETE EXTERIORS |  | 270000 | Draw 3: 14534.2; Draw 5: 103785.27; Draw 6: 3987.43 | 122306.9 | 45.3% | 147693.1
06-0170 | Rough Carpentry | NEW FRAMING OF COMPLETE EXTERIORS (AND INTERIOR ISSUES) |  | 1200000 |  |  | 201669.64 | 317608.99 | 302190.2 | 847500.95 | 1668969.78 | 139.1% | -468969.78
07-0250 | Membrane Roofing | LIFT & FIX ROOF. FINISH WEST TPO PART |  | 72500 | [6 empty] | 0 | 0% | 72500
02-0290 | On-Site Demolition | REMOVE SHEETROCK FROM BUILDING |  | 45000 | Draw 2: 10000 | 10000 | 22.22% | 35000
06-0170 | Rough Carpentry | NEW HARDWARE FOR RE-FRAME |  | 25000 | [6 empty] | 0 | 0% | 25000
26-0010 | Basic Electrical Materials | RE-INSTALL ALL ELECTRICIAL IN EXTERIOR WALLS |  | 20000 | [6 empty] | 0 | 0% | 20000
21-0020 | Wet Pipe Sprinkler Systems | RE-INSTALL ALL SPRINKLERS TO ALL DECKS |  | 30000 | [6 empty] | 0 | 0% | 30000
08-0300 | Windows | RE-INSTALL ALL EXTERIOR WINDOWS & FLASHING (200) |  | 40000 | [6 empty] | 0 | 0% | 40000
08-0260 | Doors & Frames | RE-INSTALL 170 EXTERIOR DOORS |  | 17000 | [6 empty] | 0 | 0% | 17000
02-0290 | On-Site Demolition | ALL SHORING MATERIALS |  | 50000 | Draw 2: 2541.34 | 2541.34 | 5.083% | 47458.66
02-0290 | On-Site Demolition | ALL SHORING LABOR | 3 MONTHS OF MOVING AROUND | 90000 | [6 empty] | 0 | 0% | 90000
02-0290 | On-Site Demolition | ALL SHORING ENGINEERING |  | 12000 | 14454.04 | 533.75 | 3389.26 | 2203.75 |  |  | 20580.8 | 171.5% | -8580.8
|  | GENERAL CONDITIONS FOR 3 MONTH FIX TIME PERIOD | [8 empty] | 0
01-0340 | General Conditions | TOILETS |  | 3000 | 340.03 | 415.03 |  | 999.26 |  | 2494.97 | 4249.29 | 141.6% | -1249.29
01-0340 | General Conditions | SECURITY |  | 3000 | [6 empty] | 0 | 0% | 3000
26-0090 | Temp Power & Usage | TEMP POWER |  | 3000 |  | 519.16 | 11.13 | 295.96 |  | 206.01 | 1032.26 | 34.41% | 1967.74
01-1470 | Temporary Weather Protection | WINTER CONDITIONS |  | 15000 | [6 empty] | 0 | 0% | 15000
01-2010 | Overhead | OVERHEAD & SUPERVISION |  | 70000 | 25000 | 20000 | 20000 | 25000 | 26365.15 | 25000 | 141365.15 | 202% | -71365.15
01-0340 | General Conditions | TRAILER |  | 4000 | [6 empty] | 0 | 0% | 4000
01-0340 | General Conditions | FENCING |  | 3000 | Draw 2: 510.39; Draw 6: 707.86 | 1218.25 | 40.61% | 1781.75
01-0340 | General Conditions | SAFETY |  | 500 | [6 empty] | 0 | 0% | 500
GC-0020 | Profit | BUILDERS PROFIT | 6% | 153510 | [6 empty] | 0 | 0% | 153510
01-0750 | General Requirements | RENTAL EQUIPMENT |  | 25000 | [6 empty] | 0 | 0% | 25000
01-0930 | Final Clean Up | CLEAN UP & GENERAL LABOR |  | 15000 | [6 empty] | 0 | 0% | 15000
GC-0040 | Insurance | GL INSURANCE (DIFFERENT FROM BUILDERS RISK) |  | 12500 | [6 empty] | 0 | 0% | 12500
02-0150 | Erosion Control SWPPP | SWPPP |  | 10000 | Draw 5: 605; Draw 6: 430 | 1035 | 10.35% | 8965
|  | Contract Subtotal |  | 2692010 | 120596.72 | 34519.67 | 239604.23 | 490357.91 | 467065.62 | 884327.22 | 2236471.37 | 83.08% | 455538.63
GC-0040 | Insurance | Insurance Payment |  |  | Draw 1: 105417 |  |  | 0
26-0010 | Basic Electrical Materials | Electrical work done under ML |  |  | Draw 1: 78072.18 |  |  | 0
01-0750 | General Requirements | Dumpster Charges under ML |  |  | Draw 1: 7630.41 |  |  | 0
09-0250 | Gypsum Board Install | Foundation Building Materials - Drywall Materials under ML |  |  | Draw 2: 96853.21 |  |  | 0
31-0100 | Earthwork | Triple BBB under ML - UDOT Permit & Rough cut in parking lot |  |  | Draw 2: 8998.17 |  |  | 0
14-0050 | Elevators | TK Elevator Payment |  |  | Draw 2: 4601.25 |  |  | 0
06-0090 | Finish Carpentry - Interiors | Wilcox Finish and Supply Under ML |  |  | Draw 2: 37120.44 |  |  | 0
31-0100 | Earthwork | Track-out Materials & Time |  |  | Draw 2: 61154.15 |  |  | 0
22-0050 | Plumbing Systems | Plumbing Deposit |  |  | Draw 3: 205000 |  |  | 0
02-0150 | Erosion Control SWPPP | Previous SWPPP Charges |  |  | Draw 4: 11725 |  |  | 0
22-0050 | Plumbing Systems | Plumbing Redo |  |  | Draw 5: 87565 |  |  | 0
22-0050 | Plumbing Systems | Replace Cracked Tubs |  |  | Draw 6: 34646 |  |  | 0
|  | Out of Scope Subtotal |  |  | 191119.59 | 208727.22 | 205000 | 11725 | 87565 | 34646 | 738782.81
|  | TOTALS |  | 2692010 | 311716.31 | 243246.89 | 444604.23 | 502082.91 | 554630.62 | 918973.22 | 2975254.18
THESE NUMBERS DO NOT REFLECT ANY STORAGE OF MATERIALSFOR THE LAST YEAR FROM ANY TRADES
THESE NUMBERS DO NOT REFLECT ANY BIDS IN THE ORGINAL COST BREAKDOWN BY MAKERS LINE
THESE NUMBERS DO NOT INCLUDE ANY OLD OR NEW CHANGE ORDERS FROM ALL CONTRACTORS
THESE NUMBERS DO NOT INCLUDE REPLACING THE SHEETROCK, OR STORING THE SHEETROCK, SOME
OF THE OLD SHEETROCK WILL NEED TO BE THROWN AWAY DUE TO GETTING WET AND MOLD PRESENT
THESE NUMBERS DO NOT INCLUDE ANY FRAMING ISSUES NOT YET KNOWN, INCLUDING FIXING ALL
OF THE STAIRWELLS WHICH HAVE ISSUES.
THESE NUMBERS DO NOT REFLECT ANY HVAC OR PLUMBING ISSUES THAT MIGHT ARISE DURING THE
DEMO AND FIX ON THE BUILDING.
|  |  | Grand Total | 2692010

## Sheet2
2024-04-22
455
2025-07-21