## Arixa Updated SOV
Hunter's Landing North Continuation Sheet
Rich Development
RETAINAGE
# | Cost Code | DESCRIPTION OF WORK | Budget Amount | Contributed Costs (Partner/Self-Funded) | Reallocation (+/-) | Total | Retainage from Self-Funded | Draw 4 | Draw 5 | Draw 6 | Draw 7 | Draw 8 | TOTAL COMPLETED AND STORED TO DATE | PERCENT COMPLETE | BALANCE TO FINISH | Retainage
001 |  | Survey | 7000 | 0 |  | 7000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 7000
002 |  | Excavation of building and site, backfill, sewer & water connections, elec service, asphalt | 1197367.29 | 300000 |  | 897367.29 | 0 | 0 | 0 |  |  |  | 0 | 0% | 897367.29
003 |  | Footings & Foundations M&L & site M&L | 408552 | 216541.42 |  | 192010.58 | 4460.02 | 0 | 0 |  |  |  | 4460.02 | 2.323% | 187550.56 | 4460.02
004 |  | ALL FENCING | 44475 | 0 |  | 44475 | 0 | 0 | 0 |  |  |  | 0 | 0% | 44475
005 |  | TURNKEY FRAMING | 2063122 | 100000 |  | 1963122 | 0 | 0 | 0 |  |  |  | 0 | 0% | 1963122
006 |  | Roofing Labor and Materials | 235254.4 | 0 |  | 235254.4 | 0 | 0 | 0 |  |  |  | 0 | 0% | 235254.4
007 |  | DECK COATINGS | 72445 | 0 |  | 72445 | 0 | 0 | 0 |  |  |  | 0 | 0% | 72445
008 |  | Structural steel (Covered parking) | 35813.74 | 0 |  | 35813.74 | 0 | 0 | 0 |  |  |  | 0 | 0% | 35813.74
009 |  | ALL OTHER STEEL FEATURES | 196050 | 0 |  | 196050 | 0 | 0 | 0 |  |  |  | 0 | 0% | 196050
010 |  | Windows | 170000 | 0 |  | 170000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 170000
011 |  | Store Front L&M | 95488 | 0 |  | 95488 | 0 | 0 | 0 |  |  |  | 0 | 0% | 95488
012 |  | ELEVATOR | 255500 | 0 |  | 255500 | 0 | 0 | 0 |  |  |  | 0 | 0% | 255500
013 |  | HM door labor | 18575 | 0 |  | 18575 | 0 | 0 | 0 |  |  |  | 0 | 0% | 18575
014 |  | Plumbing | 1125000 | 338750 |  | 786250 | 11250 | 0 | 0 |  |  |  | 11250 | 1.431% | 775000 | 11250
015 |  | HVAC | 1395000 | 150000 |  | 1245000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 1245000
016 |  | Electric | 1186352 | 400000 |  | 786352 | 0 | 0 | 0 |  |  |  | 0 | 0% | 786352
017 |  | SPRINKLER SYSTEM | 156271 | 0 |  | 156271 | 0 | 0 | 0 |  |  |  | 0 | 0% | 156271
018 |  | FIRE CAULKING | 10000 | 0 |  | 10000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 10000
019 |  | GYPCRETE | 77757.03 | 0 |  | 77757.03 | 0 | 0 | 0 |  |  |  | 0 | 0% | 77757.03
020 |  | Insulation | 232552 | 2600.62 |  | 229951.38 | 136.88 | 0 | 0 |  |  |  | 136.88 | 0.05953% | 229814.5 | 136.88
021 |  | Sheetrock | 850750 | 0 |  | 850750 | 0 | 0 | 0 |  |  |  | 0 | 0% | 850750
022 |  | 2 layers of dens glass | 120000 | 0 |  | 120000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 120000
023 |  | FINISH MATERIALS MISC | 325000 | 0 |  | 325000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 325000
024 |  | Finish Labor | 95000 | 0 |  | 95000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 95000
025 |  | Interior Paint | 213852.35 | 213852.35 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% | 0
026 |  | CABINETS | 461324.15 | 261324.15 |  | 200000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 200000
027 |  | EQUIPMENT FOR CABINETS | 6000 | 0 |  | 6000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 6000
028 |  | unit entry doors | 125000 | 0 |  | 125000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 125000
029 |  | FLOOR PREP | 10000 | 0 |  | 10000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 10000
030 |  | Hardware labor | 47550 | 0 |  | 47550 | 0 | 0 | 0 |  |  |  | 0 | 0% | 47550
031 |  | Hardware & HM frames & doors | 58110.22 | 0 |  | 58110.22 | 0 | 0 | 0 |  |  |  | 0 | 0% | 58110.22
032 |  | FIRE EXTINGUSHERS | 7850 | 0 |  | 7850 | 0 | 0 | 0 |  |  |  | 0 | 0% | 7850
033 |  | MIRRORS | 34000 | 0 |  | 34000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 34000
034 |  | All flooring & wall tile M&L | 312858 | 0 |  | 312858 | 0 | 0 | 0 |  |  |  | 0 | 0% | 312858
035 |  | Brick, Stucco, Soffit & fascia | 748952 | 0 |  | 748952 | 0 | 0 | 0 |  |  |  | 0 | 0% | 748952
036 |  | GUTTER | 14500 | 0 |  | 14500 | 0 | 0 | 0 |  |  |  | 0 | 0% | 14500
037 |  | PLASTER FOUNDATION | 4250 | 0 |  | 4250 | 0 | 0 | 0 |  |  |  | 0 | 0% | 4250
038 |  | ROOF HATCH | 1600 | 0 |  | 1600 | 0 | 0 | 0 |  |  |  | 0 | 0% | 1600
039 |  | PICKLEBALL | 35000 | 0 |  | 35000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 35000
040 |  | 2 VAC STATIONS | 7500 | 0 |  | 7500 | 0 | 0 | 0 |  |  |  | 0 | 0% | 7500
041 |  | MAILBOXES | 16000 | 0 |  | 16000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 16000
042 |  | DOG WASH STATION | 5000 | 0 |  | 5000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 5000
043 |  | BLINDS | 25000 | 0 |  | 25000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 25000
044 |  | 2 FIRE PITS | 6000 | 0 |  | 6000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 6000
045 |  | CLUB HOUSE PERGULA | 30000 | 0 |  | 30000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 30000
046 |  | KNOX BOX & FIRE LIDS | 2450 | 0 |  | 2450 | 0 | 0 | 0 |  |  |  | 0 | 0% | 2450
047 |  | LANDSCAPE | 125000 | 0 |  | 125000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 125000
048 |  | APPLIANCES | 264800 | 0 |  | 264800 | 0 | 0 | 0 |  |  |  | 0 | 0% | 264800
049 |  | SIGNAGE | 7500 | 0 |  | 7500 | 0 | 0 | 0 |  |  |  | 0 | 0% | 7500
050 |  | EXTERIOR FFE | 10000 | 0 |  | 10000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 10000
051 |  | CONTINGENCY | 1243628.52 | 0 |  | 1243628.52 | 0 | 0 | 0 |  |  |  | 0 | 0% | 1243628.52
052 |  | EQUIPMENT | 25000 | 0 |  | 25000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 25000
053 |  | HONEY BUCKET | 7000 | 565.69 |  | 6434.31 | 0 | 0 | 0 |  |  |  | 0 | 0% | 6434.31
054 |  | DUMPSTER | 22000 | 0 |  | 22000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 22000
055 |  | TEMP FENCE | 25000 | 14030 |  | 10970 | 0 | 0 | 0 |  |  |  | 0 | 0% | 10970
056 |  | CLEAN-UP LABOR | 25000 | 0 |  | 25000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 25000
057 |  | FINAL CLEAN | 27000 | 0 |  | 27000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 27000
058 |  | STREET SWEEPING | 4000 | 0 |  | 4000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 4000
059 |  | CONC WASH OUT | 4000 | 0 |  | 4000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 4000
060 |  | SWPPP weekly inspection | 9000 | 0 |  | 9000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 9000
061 |  | TEMP POWER | 7500 | 0 |  | 7500 | 0 | 0 | 0 |  |  |  | 0 | 0% | 7500
062 |  | OFFICE TRAILER | 13500 | 0 |  | 13500 | 0 | 0 | 0 |  |  |  | 0 | 0% | 13500
063 |  | SECURITY CAMERAS | 35000 | 0 |  | 35000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 35000
064 |  | SPECIAL INSPECTIONS | 10000 | 4538 |  | 5462 | 0 | 0 | 0 |  |  |  | 0 | 0% | 5462
065 |  | SAFTEY | 7500 | 0 |  | 7500 | 0 | 0 | 0 |  |  |  | 0 | 0% | 7500
066 |  | GENERAL CONDITIONS | 30000 | 0 |  | 30000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 30000
067 |  | Insurance | 180000 | 171331 |  | 8669 | 0 | 0 | 0 |  |  |  | 0 | 0% | 8669
068 |  | SITE SUPERVISION, PM, SUPER | 260000 | 27000 |  | 233000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 233000
069 |  | Construction Profit | 667000 | 200000 |  | 467000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 467000
070 |  | Soft Cost | 588368.19 | 588368.19 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% | 0
071 |  | CM Fee | 765501.37 | 32517.84 |  | 732983.53 | 0 | 0 | 0 |  |  |  | 0 | 0% | 732983.53
072 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% | 0
073 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% | 0
074 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% | 0
075 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% | 0
076 | [5 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% | 0
174 |  | DRAW FEE | 12000 | 0 |  | 12000 | 0 | 0 | 0 |  |  |  | 0 | 0% | 12000
TOTALS |  |  | 16921419.26 | -3021419.26 | 0 | 13900000 | 15846.9 | 0 | 0 | 0 | 0 | 0 | 15846.9 | 0.114% | 13884153.1 | 15846.9
[5 empty] | 1 | Original Contract Sum
[5 empty] | 2 | Net change by approved change orders
[5 empty] | 3 | Contract sum to date
[5 empty] | 4 | Total completed and stored to date
[5 empty] | 5 | Retainage
[5 empty] | 6 | Total earned less retainage
[5 empty] | 7 | Less previous certificates for payment
[5 empty] | 8 | Current Payment Due
[5 empty] | 9 | Balance to finish with retainage

## Self-Funded Portion
Hunter's Landing North Continuation Sheet
Rich Development
|  |  |  | 2024-07-18 | 2024-08-01 | 2024-09-04 | [6 empty] | RETAINAGE
# | Cost Code | DESCRIPTION OF WORK | Total | Draw 1 | Draw 2 | Draw 3 | Draw 4 | Draw 5 |  | TOTAL COMPLETED AND STORED TO DATE | PERCENT COMPLETE | BALANCE TO FINISH | Retainage
001 |  | SURVEY | 7000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 7000
002 | 03300 | EXCAVATION | 1197367.29 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 1197367.29
003 | 06500 | CONCRETE WORK | 408552 | 109362.24 | 4467.24 | 107171.96 | 0 | 0 |  | 221001.44 | 54.09% | 187550.56 | 4460.02 | Footings & Foundations M&L & site M&L | 216541.42
004 |  | FENCING | 44475 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 44475
005 |  | FRAMING | 2063122 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 2063122
006 |  | ROOFING | 235254.4 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 235254.4
007 |  | DECK COATINGS | 72455 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 72455
008 |  | STEEL | 231863.74 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 231863.74
009 |  | WINDOWS | 172500 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 172500
010 |  | STORE FRONT DOORS & WINDOWS | 95488 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 95488
011 |  | ELEVATOR | 255500 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 255500
012 |  | HM DOORS & HARDWARE | 124235.22 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 124235.22
013 |  | PLUMBING | 1125000 | 0 | 225000 | 0 | 0 | 0 |  | 225000 | 20% | 900000 | 11250 | Plumbing | 213750
014 |  | ELEC | 1339237.49 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 1339237.49
015 |  | HVAC | 1395000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 1395000
016 |  | FIRE SPRINKLERS | 291076.09 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 291076.09
017 |  | CAULKING | 10000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 10000
018 |  | GYPCRETE | 77757.03 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 77757.03
019 |  | INSULATION | 232552 | 0 | 0 | 2737.5 | 0 | 0 |  | 2737.5 | 1.177% | 229814.5 | 136.88 | Insulation | 2600.62
020 |  | SHEETROCK & DENSGLASS | 970288.61 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 970288.61
021 |  | ROOF HATCH | 1600 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 1600
022 |  | FINISH MATERIALS & LABOR | 520000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 520000
023 |  | PAINTING | 213852.35 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 213852.35
024 |  | CABINETS & TOPS | 467314.15 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 467314.15
025 |  | FLOOR PREP | 10000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 10000
026 |  | FIRE EXTINGUSHERS | 7850 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 7850
027 |  | MIRRORS | 34000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 34000
028 |  | FLOORING | 312858 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 312858
029 |  | EXTERIORS | 891304 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 891304
030 |  | PICKLEBALL | 40000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 40000
031 |  | VAC STATIONS | 7500 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 7500
032 |  | MAILBOXES | 19250 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 19250
033 |  | DOG WASH STATION | 6800 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 6800
034 |  | BLINDS | 31500 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 31500
035 |  | FIREPITS | 8000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 8000
037 |  | PERGULA | 45278 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 45278
038 |  | KNOX BOX & LIDS | 2450 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 2450
039 |  | LANDSCAPE | 148000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 148000
040 |  | APPLIANCES | 364800 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 364800
041 |  | SIGNAGE | 10000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 10000
042 |  | EXTERIOR FFE | 25000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 25000
043 |  | EQUIPMENT, CLEAN UP, TOILET, | 110000 | 449.13 | 0 | 116.56 | 0 | 0 |  | 565.69 | 0.5143% | 109434.31
044 |  | TRAILER, TEMP POWER, SECURITY, TEMP FENCE | 88500 | 0 | 14030 | 0 | 0 | 0 |  | 14030 | 15.85% | 74470
045 |  | SWPPP, SPECIAL INSPECTIONS, SAFETY, WASH OUT | 23000 | 2525 | 450 | 1563 | 0 | 0 |  | 4538 | 19.73% | 18462
046 |  | GENERAL CONDITIONS | 30000 | 0 | 7500 | 0 | 0 | 0 |  | 7500 | 25% | 22500
047 |  | SITE SUPERVISION | 260000 | 15000 | 0 | 4500 | 0 | 0 |  | 19500 | 7.5% | 240500
048 |  | INSURANCE | 180000 | 171331 | 0 | 0 | 0 | 0 |  | 171331 | 95.18% | 8669
049 |  | CONSTRUCTION PROFIT | 639341.12 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 639341.12
TOTALS |  |  | 14846921.49 | 298667.37 | 251447.24 | 116089.02 |  |  |  | 666203.63 | 4.487% | 14180717.86 | 15846.9
|  |  |  | 295778.93 | 237308.8 | 117269
|  | 1 | Original Contract Sum | 14846921.49 | 14846921.49 | 14846921.49
|  | 2 | Net change by approved change orders | 0 | 0 | 22500
|  | 3 | Contract sum to date | 14846921.49 | 14846921.49 | 14869421.49
|  | 4 | Total completed and stored to date | 298667.37 | 550114.61 | 666203.63
|  | 5 | Retainage | 2888.44 | 14138.44 | 15846.9
|  | 6 | Total earned less retainage | 295778.93 | 535976.17 | 650356.73
|  | 7 | Less previous certificates for payment | 0 | 295778.93 | 533087.73 |  |  | 235254.4
|  | 8 | Current Payment Due | 295778.93 | 237308.8 | 117269 |  |  | 0
|  | 9 | Balance to finish with retainage | 14551142.56 | 14310945.32 | 14219064.76 |  |  | 0