## Sheet1
APPLICATION AND CERTIFICATE FOR PAYMENT
AIA DOCUMENT G702
TO OWNER: |  |  |  | HUNTERS LANDING NORTH LLC |  |  |  | PROJECT: | APPLICATION NUMBER: |  |  | Distribution to: | Distribution to:
[9 empty] | PERIOD TO: |  | X |  | OWNER
[9 empty] | PROJECT NO: |  |  |  | CONSTRUCTION
MANAGER
FROM |  |  |  | RICH DEVELOPMENT INC. |  |  |  |  | CONTRACT DATE: |  |  |  | ARCHITECT
CONTRACTOR: | [12 empty] | CONTRACTOR
CONTRACTOR'S APPLICATION FOR PAYMENT | [7 empty] | The undersigned Contractor certifies that to the best of the Contractor's knowledge,
Application is made for payment, as shown below, in accordance with the Contract. | [7 empty] | information and belief, the Work covered by this Application for Payment has been
Continuation Sheet, AIA Document G703, is attached. | [7 empty] | completed in accordance with the Contract Documents, that all amounts have been
1. | ORIGINAL CONTRACT SUM | [5 empty] | 14846921.49 | paid by the Contractor for Work for which previous Certificates for Payment were issued
and payments received from the Owner, and that current payment shown herein is now due.
2. | Net Change By Change Orders………………………. | [5 empty] | 22500 | CONTRACTOR:
3. | CONTRACT SUM TO DATE |  |  |  | (Line 1 +2)…… |  | 14869421.49
BY: _____________________________________________________ DATE___________
4. | TOTAL COMPLETED & STORED TO DATE………….. | [5 empty] | 298667.37
(Column G on G703)
State of:___________________________________ County of : __________________
5. | RETAINAGE: | [6 empty] | Subscribed and sworn before me this day of 20
| a. | 5% | of Completed Work |  | #REF! |  |  | Notary Public:
|  | (Columns D & E on G703) | [5 empty] | My Commission Expires:
| b. | 5% | of Stored Material |  | #REF!
|  | (Column F on G703) | [5 empty] | CERTIFICATE FOR PAYMENT
Total Retainage (Line 5a + 5b or
|  | Total in Column 1 of G703) |  |  |  |  | #REF! | In accordance with the Contract Documents, based on on-site observations
and the data comprising the above application, the Construction Manager
6. | TOTAL EARNED LESS RETAINAGE…………………… | [5 empty] | #REF! | certifies that to the best of his knowledge, information and belief the Work
| (Line 4 less Line 5 Total) | [6 empty] | has progressed as indicated, the quality of the Work is in accordance with
the Contract Documents, and the Contractor is entitled to payment of the
7. | LESS PREVIOUS CERTIFICATES FOR PAYMENT | [6 empty] | AMOUNT CERTIFIED.
| (Line 6 from prior Certificate) | [5 empty] | 0
[8 empty] | AMOUNT CERTIFIED……………………. |  | #REF!
8. | CURRENT PAYMENT DUE | [5 empty] | #REF! | (Attach explanation if amount certified differs from the amount applied for. Initial all figures on this
Application and on the Continuation Sheet that changed to conform to the amount certified.).
9. | BALANCE TO FINISH, INCLUDING RETAINAGE | [6 empty] | CONSTRUCTION MGR:
| (Line 3 less Line 6) |  |  |  | #REF! |  |  | By:___________________________________________Date:__________________
CHANGE ORDER SUMMARY |  |  |  |  | ADDITIONS |  | DEDUCTIONS | ARCHITECT:
Total changes approved in | [7 empty] | By:____________________________________________ Date: _________________
previous months by Owner |  |  |  |  | 0 |  | 0 | This certificate is not negotiable. The AMOUNT CERTIFIED is payable only
Total Approved this Month |  |  |  |  | 0 |  | 0 | to the Contractor named herein. Issuance, payment and acceptance of payment
|  | TOTALS |  |  | 0 | 0 | 0 | are without prejudice to any rights of the Owner or Contractor under this Contract.
NET CHANGES by Change Order | [6 empty] | 0

## Sheet2
CONTINUATION SHEET |  |  |  |  | HUNTERS LANDING NORTH
AIA Document G702, APPLICATION AND CERTIFICATE FOR PAYMENT, | [9 empty] | APPLICATION NO: | #REF!
containing Contractor's signed Certification is attached. | [9 empty] | APPLICATION DATE: | 7-9-224
[10 empty] | PERIOD TO: | #REF!
[10 empty] | ARCHITECT'S PROJECT NO: | #REF!
A |  |  | B | C | D | E | F | G |  | H | I
ITEM | Cost Code |  | DESCRIPTION OF WORK | SCHEDULED | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
NO. |  |  |  | VALUE | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | (G/C) | TO FINISH
[5 empty] | APPLICATION |  | STORED | AND STORED |  | (C-G)
[5 empty] | (D+E) |  | (NOT IN | TO DATE
[7 empty] | D OR E) | (D+E+F)
001 |  | 1 | SURVEY | 7000 | 0 | 0 | 0 | 0 | 0% | 7000 | 0
002 | 03300 | 2 | EXCAVATION | 1197367.29 | 0 | 0 | 0 | 0 | 0% | 1197367.29 | 0
003 | 06500 | 3 | CONCRETE WORK | 408552 | 109362.24 | 0 | 0 | 109362.24 | 26.77% | 299189.76 | 0
004 |  | 4 | FENCING | 44475 | 0 | 0 | 0 | 0 | 0% | 44475 | 0
005 |  | 5 | FRAMING | 2063122 | 0 | 0 | 0 | 0 | 0% | 2063122 | 0
006 |  | 6 | ROOFING | 235254.4 | 0 | 0 | 0 | 0 | 0% | 235254.4 | 0
007 |  | 7 | DECK COATINGS | 72455 | 0 | 0 | 0 | 0 | 0% | 72455 | 0
008 |  | 8 | STEEL | 231863.74 | 0 | 0 | 0 | 0 | 0% | 231863.74 | 0
009 |  | 9 | WINDOWS | 172500 | 0 | 0 | 0 | 0 | 0% | 172500 | 0
010 |  | 10 | STORE FRONT DOORS & WINDOWS | 95488 | 0 | 0 | 0 | 0 | 0% | 95488 | 0
011 |  | 11 | ELEVATOR | 255500 | 0 | 0 | 0 | 0 | 0% | 255500 | 0
012 |  | 12 | HM DOORS & HARDWARE | 124235.22 | 0 | 0 | 0 | 0 | 0% | 124235.22 | 0
013 |  | 13 | PLUMBING | 1125000 | 0 | 0 | 0 | 0 | 0% | 1125000 | 0
014 |  | 14 | ELEC | 1339237.49 | 0 | 0 | 0 | 0 | 0% | 1339237.49 | 0
015 |  | 15 | HVAC | 1395000 | 0 | 0 | 0 | 0 | 0% | 1395000 | 0
016 |  | 16 | FIRE SPRINKLERS | 291076.09 | 0 | 0 | 0 | 0 | 0% | 291076.09 | 0
017 |  | 17 | CAULKING | 10000 | 0 | 0 | 0 | 0 | 0% | 10000 | 0
018 |  | 18 | GYPCRETE | 77757.03 | 0 | 0 | 0 | 0 | 0% | 77757.03 | 0
019 |  | 19 | INSULATION | 232552 | 0 | 0 | 0 | 0 | 0% | 232552 | 0
020 |  | 20 | SHEETROCK & DENSGLASS | 970288.61 | 0 | 0 | 0 | 0 | 0% | 970288.61 | 0
021 |  | 21 | ROOF HATCH | 1600 | 0 | 0 | 0 | 0 | 0% | 1600 | 0
022 |  | 22 | FINISH MATERIALS & LABOR | 520000 | 0 | 0 | 0 | 0 | 0% | 520000 | 0
023 |  | 23 | PAINTING | 213852.35 | 0 | 0 | 0 | 0 | 0% | 213852.35 | 0
024 |  | 24 | CABINETS & TOPS | 467314.15 | 0 | 0 | 0 | 0 | 0% | 467314.15 | 0
025 |  | 25 | FLOOR PREP | 10000 | 0 | 0 | 0 | 0 | 0% | 10000 | 0
026 |  | 26 | FIRE EXTINGUSHERS | 7850 | 0 | 0 | 0 | 0 | 0% | 7850 | 0
027 |  | 27 | MIRRORS | 34000 | 0 | 0 | 0 | 0 | 0% | 34000 | 0
028 |  | 28 | FLOORING | 312858 | 0 | 0 | 0 | 0 | 0% | 312858 | 0
029 |  | 29 | EXTERIORS | 891304 | 0 | 0 | 0 | 0 | 0% | 891304 | 0
030 |  | 30 | PICKLEBALL | 40000 | 0 | 0 | 0 | 0 | 0% | 40000 | 0
031 |  | 31 | VAC STATIONS | 7500 | 0 | 0 | 0 | 0 | 0% | 7500 | 0
032 |  | 32 | MAILBOXES | 19250 | 0 | 0 | 0 | 0 | 0% | 19250 | 0
033 |  | 33 | DOG WASH STATION | 6800 | 0 | 0 | 0 | 0 | 0% | 6800 | 0
034 |  | 34 | BLINDS | 31500 | 0 | 0 | 0 | 0 | 0% | 31500 | 0
035 |  | 35 | FIREPITS | 8000 | 0 | 0 | 0 | 0 | 0% | 8000 | 0
037 |  | 36 | PERGULA | 45278 | 0 | 0 | 0 | 0 | 0% | 45278 | 0
038 |  | 37 | KNOX BOX & LIDS | 2450 | 0 | 0 | 0 | 0 | 0% | 2450 | 0
039 |  | 38 | LANDSCAPE | 148000 | 0 | 0 | 0 | 0 | 0% | 148000 | 0
040 |  | 39 | APPLIANCES | 364800 | 0 | 0 | 0 | 0 | 0% | 364800 | 0
041 |  | 40 | SIGNAGE | 10000 | 0 | 0 | 0 | 0 | 0% | 10000 | 0
042 |  | 41 | EXTERIOR FFE | 25000 | 0 | 0 | 0 | 0 | 0% | 25000 | 0
043 |  | 42 | EQUIPMENT, CLEAN UP, TOILET, | 110000 | 449.13 | 0 | 0 | 449.13 | 0.4083% | 109550.87 | 0
044 |  | 43 | TRAILER, TEMP POWER, SECURITY, TEMP FENCE | 88500 | 0 | 0 | 0 | 0 | 0% | 88500 | 0
045 |  | 44 | SWPPP, SPECIAL INSPECTIONS, SAFETY, WASH OUT | 23000 | 2525 | 0 | 0 | 2525 | 10.98% | 20475 | 0
046 |  | 45 | GENERAL CONDITIONS | 30000 | 0 | 0 | 0 | 0 | 0% | 30000 | 0
047 |  | 46 | SITE SUPERVISION | 260000 | 15000 | 0 | 0 | 15000 | 5.769% | 245000 | 0
048 |  | 47 | INSURANCE | 180000 | 171331 | 0 | 0 | 171331 | 95.18% | 8669 | 0
049 |  | 48 | CONSTRUCTION PROFIT | 639341.12 | 0 | 0 | 0 | 0 | 0% | 639341.12 | 0
Total Base Contract |  |  |  | 14846921.49 | 298667.37 | 0 | 0 | 298667.37 | 2.012% | 14548254.12 | 0
Extra Work
| 03300 |  | CO #1 EXTRA GRAVEL UNDER FOOTINGS | 22500 |  | 0 |  | 0 | 0% | 22500 | #REF!
[8 empty] | 0 | #DIV/0! | 0 | #REF!
[8 empty] | 0 | #DIV/0! | 0 | #REF!
[8 empty] | 0 | #DIV/0! | 0 | #REF!
[8 empty] | 0 | #DIV/0! | 0 | #REF!
[8 empty] | 0 | #DIV/0! | 0 | #REF!
[8 empty] | 0 | #DIV/0! | 0 | #REF!
[8 empty] | 0 | #DIV/0! | 0 | #REF!
Total Extra Work |  |  |  | 22500 | 0 | 0 | 0 | 0 | 0% | 22500 | #REF!
Grand Total |  |  |  | 14869421.49 | 298667.37 | 0 | 0 | 298667.37 | 2.009% | 14570754.12 | #REF!