## Product List (hidden)
ABATEMENT/REMEDIATION/ASBESTOS | 01u6S000018BAIdQAO | 01t6S00000BhEQIQA3
ADU | 01u6S00001842qmQAA | 01t6S00000BGzOMQA1
APPLIANCES | 01u6S000016ZYr8QAG | 01t6S00000BGmgVQAT
ARCHITECTURAL AND ENGINEERING | 01u6S000016ZYrpQAG | 01t6S00000BGmgXQAT
BATHROOM | 01u6S000018BAIeQAO | 01t6S00000BhEQJQA3
BUILDING CLEAN-UP | 01u6S000016ZYroQAG | 01t6S00000BGmhEQAT
CABINETS | 01u6S000016ZYrnQAG | 01t6S00000BGmgUQAT
COMPLETION AND INSPECTION | 01u6S000016ZYrlQAG | 01t6S00000BGmggQAD
CONCRETE | 01u6S000016ZYrkQAG | 01t6S00000BGmgxQAD
CONCRETE SUBFLOOR | 01u6S00001844JrQAI | 01t6S00000BH1bXQAT
CONCRETE WALL | 01u6S00001844JsQAI | 01t6S00000BH1bTQAT
CONTINGENCY | 01u6S000016ZYrjQAG | 01t6S00000BGmgfQAD
CURB & GUTTER | 01u6S000018BAIfQAO | 01t6S00000BhEQXQA3
DECKS/BALCONIES/PATIOS | 01u6S00001842qnQAA | 01t6S00000BGzO9QAL
DEMOLITION | 01u6S000016ZYriQAG | 01t6S00000BGmgmQAD
DRIVEWAY | 01u6S000016ZYrhQAG | 01t6S00000BGmhGQAT
DRY UTILITES | 01u6S000018BAIgQAO | 01t6S00000BhEQKQA3
DRYWALL | 01u6S000016ZYrgQAG | 01t6S00000BGmhBQAT
ELEVATOR | 01u6S000016ZYrfQAG | 01t6S00000BGmhAQAT
EXTERIOR PAINTING | 01u6S000016ZYrdQAG | 01t6S00000BGmhNQAT
EXTERIOR TRIM | 01u6S000016ZYrcQAG | 01t6S00000BGmhMQAT
EXTERIOR VENEER/STUCCO | 01u6S000016ZYrbQAG | 01t6S00000BGmh3QAD
FENCES | 01u6S00001844JtQAI | 01t6S00000BH1bcQAD
FIELD EQUIPMENT | 01u6S000016ZYraQAG | 01t6S00000BGmgdQAD
FINISH CARPENTRY/MILLWORK | 01u6S00001842qoQAA | 01t6S00000BGzOGQA1
FINISH ELECTRICAL | 01u6S000016ZYrZQAW | 01t6S00000BGmhIQAT
FINISH HARDWEAR | 01u6S00001842qpQAA | 01t6S00000BGzOFQA1
FINISH HVAC | 01u6S000016ZYrYQAW | 01t6S00000BGmhKQAT
FINISH PLUMBING | 01u6S000016ZYrXQAW | 01t6S00000BGmhHQAT
FINISH PLUMBING & ELECTRICAL | 01uRN000000K3o9YAC | 01tRN000001ORUj
FIRE SPRINKLERS | 01u6S000016ZYrWQAW | 01t6S00000BGmgzQAD
FIREPLACE | 01u6S00001842qqQAA | 01t6S00000BGzOAQA1
FIXTURES | 01u6S000018BAIhQAO | 01t6S00000BhEQcQAN
FLOORING | 01u6S000016ZYrVQAW | 01t6S00000BGmhOQAT
FOOTING AND FOUNDATIONS | 01u6S000016ZYrUQAW | 01t6S00000BGmgqQAD
FRAMING | 01u6S000016ZYrTQAW | 01t6S00000BGmgwQAD
GARAGE DOOR | 01u6S00001842qrQAA | 01t6S00000BGzOHQA1
GC FEE | 01u6S00001844JuQAI | 01t6S00000BH1bSQAT
GLASS/GLAZING | 01u6S00001842qsQAA | 01t6S00000BGzOEQA1
GRADING & EXCAVATION | 01u6S00001842qtQAA | 01t6S00000BGzO6QAL
HARDSCAPE | 01u6S000016ZYrSQAW | 01t6S00000BGmhDQAT
HARDWEAR | 01u6S00001842quQAA | 01t6S00000BGzO7QAL
HAULING/TRASH OUT/DUMPSTERS | 01u6S00001842qvQAA | 01t6S00000BGzO5QAL
INDIRECT CONSTRUCTION | 01u6S000016ZYrRQAW | 01t6S00000BGmgeQAD
INSULATION | 01u6S000016ZYrQQAW | 01t6S00000BGmh7QAD
INSURANCE | 01u6S000016ZYrPQAW | 01t6S00000BGmglQAD
INTERIOR DESIGN | 01u6S000016ZYrOQAW | 01t6S00000BGmgYQAT
INTERIOR DOORS | 01u6S00001842qwQAA | 01t6S00000BGzOCQA1
INTERIOR PAINTING | 01u6S00001842qxQAA | 01t6S00000BGzOBQA1
INTERIOR TRIM | 01u6S000016ZYrNQAW | 01t6S00000BGmhPQAT
INTERIOR/EXTERIOR PAINT | 01uRN000000K3kvYAC | 01tRN000001ONkV
KITCHEN | 01u6S000018BAIiQAO | 01t6S00000BhEQNQA3
LANDSCAPE/HARDSCAPE | 01uRN000000K3rNYAS | 01tRN000001OQs2
LANDSCAPING | 01u6S000016ZYrMQAW | 01t6S00000BGmhFQAT
LOW VOLTAGE | 01u6S00001842qyQAA | 01t6S00000BGzO8QAL
MASONRY | 01u6S000016ZYrLQAW | 01t6S00000BGmh5QAD
METALS AND GUTTER | 01u6S000016ZYrKQAW | 01t6S00000BGmh8QAD
MISCELLANEOUS | 01u6S000018BAIjQAO | 01t6S00000BhEQOQA3
ORNAMETAL IRON | 01u6S000016ZYrJQAW | 01t6S00000BGmhLQAT
OTHER | 01u6S00001844JvQAI | 01t6S00000BH1bhQAD
OVERHEAD | 01u6S000016ZYrIQAW | 01t6S00000BGmgiQAD
PERMITS AND FEES | 01u6S000016ZYrHQAW | 01t6S00000BGmgWQAT
POOL | 01u6S000016ZYrGQAW | 01t6S00000BGmhCQAT
PROJECT COMPLETION | 01uRN000000K3hhYAC | 01tRN000001OQdX
RETAINING WALLS | 01u6S000016ZYrFQAW | 01t6S00000BGmgoQAD
ROOFING | 01u6S000016ZYrEQAW | 01t6S00000BGmh4QAD
ROUGH ELECTRICAL | 01u6S000016ZYrDQAW | 01t6S00000BGmh1QAD
ROUGH HVAC | 01u6S000016ZYrCQAW | 01t6S00000BGmh2QAD
ROUGH MEP | 01uRN000000K3ubYAC | 01tRN000001OROH
ROUGH PLUMBING | 01u6S000016ZYrBQAW | 01t6S00000BGmh0QAD
ROUGH SHEET METAL | 01u6S000016ZYrAQAW | 01t6S00000BGmgyQAD
ROUGH STRUCTURE | 01u6S000016ZYr9QAG | 01t6S00000BGmguQAD
SEWER | 01u6S000018BAIkQAO | 01t6S00000BhEQSQA3
SHORING | 01u6S000016ZYrqQAG | 01t6S00000BGmgpQAD
SITE DRAINAGE | 01u6S000016ZYrrQAG | 01t6S00000BGmgsQAD
SITE WORK | 01u6S000016ZYrsQAG | 01t6S00000BGmgcQAD
SOFT COST | 01uRN000000K3xpYAC | 01tRN000001OO5T
SOLAR | 01u6S000016ZYrtQAG | 01t6S00000BGmhJQAT
SPECIALTIES | 01u6S00001842qzQAA | 01t6S00000BGzOIQA1
STAIRS | 01u6S000016ZYruQAG | 01t6S00000BGmh9QAD
STEEL | 01u6S000016ZYrvQAG | 01t6S00000BGmgvQAD
STONE & COUNTERTOPS | 01u6S000016ZYrwQAG | 01t6S00000BGmgTQAT
SUPERVISION & MANAGEMENT | 01u6S000016ZYrxQAG | 01t6S00000BGmgjQAD
TAXES | 01u6S000016ZYryQAG | 01t6S00000BGmgkQAD
TEMP FACLITIES | 01u6S000016ZYrzQAG | 01t6S00000BGmgaQAD
TEMP UTILITIES | 01u6S000016ZYs0QAG | 01t6S00000BGmgZQAT
TENANT IMPROVMENTS/COMMON AREA RENOVATIONS | 01u6S00001842r0QAA | 01t6S00000BGzOKQA1
TENNANT RELOCATION | 01u6S000018BAIlQAO | 01t6S00000BhEQDQA3
TERMITE PROTECTION | 01u6S000016ZYs1QAG | 01t6S00000BGmgtQAD
TILE | 01u6S00001842r1QAA | 01t6S00000BGzODQA1
UNIT | 01u6S00001842r2QAA | 01t6S00000BGzOLQA1
UTILITY CONNECTIONS | 01u6S000016ZYs2QAG | 01t6S00000BGmgbQAD
WALK THROUGH INSPECTION COSTS | 01u6S000016ZYs3QAG | 01t6S00000BGmghQAD
WATERPROOFING | 01u6S000016ZYs4QAG | 01t6S00000BGmgrQAD
WINDOW COVERINGS | 01u6S00001842r3QAA | 01t6S00000BGzOJQA1
WINDOWS AND DOORS | 01u6S000016ZYs5QAG | 01t6S00000BGmh6QAD

## Arixa SOV
Price Book Entry ID | Product ID | Product DO NOT MAP | Opportunity ID
[5 empty] | Property Address: | 1075 Century Drive, Ogden, UT 84404 | [11 empty] | Construction Loan Amount: | 16921419.26 |  |  | Expected Completion Date:
[5 empty] | Borrower Name: | Hunter's Landing North, LLC - Aubrey Palmer (PALMER AUBREY) | [7 empty] | Phone: | (801) 400-8452 |  |  | Remaining Balance Post Draw: | 13884153.1 |  |  | Draw Reimbursement % |  | 100%
[5 empty] | Draw Point Of Contact | - | [7 empty] | Phone: |  |  |  | Lock Box |  |  |  | Draw Fee Adjusted: |  | 500
[5 empty] | General Contractor: | [8 empty] | License: |  |  |  | Project Square Footage | 81227
[5 empty] | Inspectors Name: | [8 empty] | Phone: |  |  |  | Draw Processing Fee: | 500
|  |  |  | Item | Description | Budget | Pre-Funding | Approved | Reallocation | Revised Ready for Draw 1 | % | $ PSF | Balance | Draw #1 | Draw #2 | Draw #3 | Draw #4 | Draw #5 | Draw #6 | Draw #7 | Draw #8 | Draw #9 | Draw #10 | Draw #11 | Draw #12 | Draw #13 | Draw #14 | Draw #15 | Draw #16 | Draw #17 | Draw #18 | Draw #19 | Draw #20 | Draw #21 | Draw #22 | Draw #23 | Retainage | Costs-to-Date | %
|  |  |  | # |  | Amount | Costs-to-Date & Contributed costs | Current | (+/-) | Budget | Of | Of | Remaining | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) |  |  | Drawn
[7 empty] | (Non Reimbursable) | Budget |  |  | Revised | Revised
|  |  |  | 1 | Survey | 7000 | 0 | 7000 | 0 | 7000 | 0.05036% | 0.086178 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 2 | Excavation of building and site, backfill, sewer & water connections, elec service, asphalt | 1197367.29 | 300000 | 897367.29 | 0 | 897367.29 | 6.456% | 11.0476 | 897367.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 3 | Footings & Foundations M&L & site M&L | 408552 | 216541.42 | 192010.58 | 0 | 192010.58 | 1.381% | 2.3639 | 187550.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4460.02 | 4460.02 | 2.323%
|  |  |  | 4 | ALL FENCING | 44475 | 0 | 44475 | 0 | 44475 | 0.32% | 0.54754 | 44475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 5 | TURNKEY FRAMING, | 2063122 | 100000 | 1963122 | 0 | 1963122 | 14.12% | 24.1683 | 1963122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 6 | Roofing Labor and Materials | 235254.4 | 0 | 235254.4 | 0 | 235254.4 | 1.692% | 2.8963 | 235254.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 7 | DECK COATINGS | 72445 | 0 | 72445 | 0 | 72445 | 0.5212% | 0.89188 | 72445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 8 | Structural steel (Covered parking) | 35813.74 | 0 | 35813.74 | 0 | 35813.74 | 0.2577% | 0.44091 | 35813.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 9 | ALL OTHER STEEL FEATURES | 196050 | 0 | 196050 | 0 | 196050 | 1.41% | 2.4136 | 196050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 10 | Windows | 170000 | 0 | 170000 | 0 | 170000 | 1.223% | 2.0929 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 11 | Store Front L&M | 95488 | 0 | 95488 | 0 | 95488 | 0.687% | 1.1756 | 95488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 12 | ELEVATOR | 255500 | 0 | 255500 | 0 | 255500 | 1.838% | 3.1455 | 255500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 13 | HM door labor | 18575 | 0 | 18575 | 0 | 18575 | 0.1336% | 0.22868 | 18575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 14 | Plumbing | 1125000 | 338750 | 786250 | 0 | 786250 | 5.656% | 9.6797 | 775000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 11250 | 1.431%
|  |  |  | 15 | HVAC | 1395000 | 150000 | 1245000 | 0 | 1245000 | 8.957% | 15.3274 | 1245000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 16 | Electric | 1186352 | 400000 | 786352 | 0 | 786352 | 5.657% | 9.6809 | 786352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 17 | SPRINKLER SYSTEM | 156271 | 0 | 156271 | 0 | 156271 | 1.124% | 1.9239 | 156271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 18 | FIRE CAULKING | 10000 | 0 | 10000 | 0 | 10000 | 0.07194% | 0.12311 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 19 | GYPCRETE | 77757.03 | 0 | 77757.03 | 0 | 77757.03 | 0.5594% | 0.95728 | 77757.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 20 | Insulation | 232552 | 2600.62 | 229951.38 | 0 | 229951.38 | 1.654% | 2.831 | 229814.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.88 | 136.88 | 0.05953%
|  |  |  | 21 | Sheetrock | 850750 | 0 | 850750 | 0 | 850750 | 6.121% | 10.4737 | 850750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 22 | 2 layers of dens glass | 120000 | 0 | 120000 | 0 | 120000 | 0.8633% | 1.4773 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 23 | FINISH MATERIALS MISC | 325000 | 0 | 325000 | 0 | 325000 | 2.338% | 4.0011 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 24 | Finish Labor | 95000 | 0 | 95000 | 0 | 95000 | 0.6835% | 1.1696 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 25 | Interior Paint | 213852.35 | 213852.35 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 26 | CABINETS | 461324.15 | 261324.15 | 200000 | 0 | 200000 | 1.439% | 2.4622 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 27 | EQUIPMENT FOR CABINETS | 6000 | 0 | 6000 | 0 | 6000 | 0.04317% | 0.073867 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 28 | unit entry doors | 125000 | 0 | 125000 | 0 | 125000 | 0.8993% | 1.5389 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 29 | FLOOR PREP | 10000 | 0 | 10000 | 0 | 10000 | 0.07194% | 0.12311 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 30 | Hardware labor | 47550 | 0 | 47550 | 0 | 47550 | 0.3421% | 0.5854 | 47550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 31 | Hardware & HM frames & doors | 58110.22 | 0 | 58110.22 | 0 | 58110.22 | 0.4181% | 0.71541 | 58110.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 32 | FIRE EXTINGUSHERS | 7850 | 0 | 7850 | 0 | 7850 | 0.05647% | 0.096643 | 7850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 33 | MIRRORS | 34000 | 0 | 34000 | 0 | 34000 | 0.2446% | 0.41858 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 34 | All flooring & wall tile M&L | 312858 | 0 | 312858 | 0 | 312858 | 2.251% | 3.8517 | 312858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 35 | Brick, Stucco, Soffit & fascia | 748952 | 0 | 748952 | 0 | 748952 | 5.388% | 9.2205 | 748952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 36 | GUTTER | 14500 | 0 | 14500 | 0 | 14500 | 0.1043% | 0.17851 | 14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 36 | PLASTER FOUNDATION | 4250 | 0 | 4250 | 0 | 4250 | 0.03058% | 0.052323 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 37 | ROOF HATCH | 1600 | 0 | 1600 | 0 | 1600 | 0.01151% | 0.019698 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 38 | PICKLEBALL | 35000 | 0 | 35000 | 0 | 35000 | 0.2518% | 0.43089 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 39 | 2 VAC STATIONS | 7500 | 0 | 7500 | 0 | 7500 | 0.05396% | 0.092334 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 40 | MAILBOXES | 16000 | 0 | 16000 | 0 | 16000 | 0.1151% | 0.19698 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 41 | DOG WASH STATION | 5000 | 0 | 5000 | 0 | 5000 | 0.03597% | 0.061556 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 42 | BLINDS | 25000 | 0 | 25000 | 0 | 25000 | 0.1799% | 0.30778 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 43 | 2 FIRE PITS | 6000 | 0 | 6000 | 0 | 6000 | 0.04317% | 0.073867 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 44 | CLUB HOUSE PERGULA | 30000 | 0 | 30000 | 0 | 30000 | 0.2158% | 0.36934 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 45 | KNOX BOX & FIRE LIDS | 2450 | 0 | 2450 | 0 | 2450 | 0.01763% | 0.030162 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 46 | LANDSCAPE | 125000 | 0 | 125000 | 0 | 125000 | 0.8993% | 1.5389 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 47 | APPLIANCES | 264800 | 0 | 264800 | 0 | 264800 | 1.905% | 3.26 | 264800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 48 | SIGNAGE | 7500 | 0 | 7500 | 0 | 7500 | 0.05396% | 0.092334 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 49 | EXTERIOR FFE | 10000 | 0 | 10000 | 0 | 10000 | 0.07194% | 0.12311 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 50 | CONTINGENCY | 1243628.52 | 0 | 1243628.52 | 0 | 1243628.52 | 8.947% | 15.3105 | 1243628.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 51 | EQUIPMENT | 25000 | 0 | 25000 | 0 | 25000 | 0.1799% | 0.30778 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 53 | HONEY BUCKET | 7000 | 565.69 | 6434.31 | 0 | 6434.31 | 0.04629% | 0.079214 | 6434.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 54 | DUMPSTER | 22000 | 0 | 22000 | 0 | 22000 | 0.1583% | 0.27085 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 55 | TEMP FENCE | 25000 | 14030 | 10970 | 0 | 10970 | 0.07892% | 0.13505 | 10970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 56 | CLEAN-UP LABOR | 25000 | 0 | 25000 | 0 | 25000 | 0.1799% | 0.30778 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 57 | FINAL CLEAN | 27000 | 0 | 27000 | 0 | 27000 | 0.1942% | 0.3324 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 58 | STREET SWEEPING | 4000 | 0 | 4000 | 0 | 4000 | 0.02878% | 0.049245 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 59 | CONC WASH OUT | 4000 | 0 | 4000 | 0 | 4000 | 0.02878% | 0.049245 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 60 | SWPPP weekly inspection | 9000 | 0 | 9000 | 0 | 9000 | 0.06475% | 0.1108 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 61 | TEMP POWER | 7500 | 0 | 7500 | 0 | 7500 | 0.05396% | 0.092334 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 62 | OFFICE TRAILER | 13500 | 0 | 13500 | 0 | 13500 | 0.09712% | 0.1662 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 63 | SECURITY CAMERAS | 35000 | 0 | 35000 | 0 | 35000 | 0.2518% | 0.43089 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 64 | SPECIAL INSPECTIONS | 10000 | 4538 | 5462 | 0 | 5462 | 0.03929% | 0.067244 | 5462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 65 | SAFTEY | 7500 | 0 | 7500 | 0 | 7500 | 0.05396% | 0.092334 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 66 | GENERAL CONDITIONS | 30000 | 0 | 30000 | 0 | 30000 | 0.2158% | 0.36934 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 67 | Insurance | 180000 | 171331 | 8669 | 0 | 8669 | 0.06237% | 0.10673 | 8669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 68 | SITE SUPERVISION, PM, SUPER | 260000 | 27000 | 233000 | 0 | 233000 | 1.676% | 2.8685 | 233000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 69 | Construction Profit | 667000 | 200000 | 467000 | 0 | 467000 | 3.36% | 5.7493 | 467000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 70 | Soft Cost | 588368.19 | 588368.19 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 71 | CM Fee | 765501.37 | 32517.84 | 732983.53 | 0 | 732983.53 | 5.273% | 9.0239 | 732983.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 72 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 73 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 74 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 75 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 76 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 77 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 78 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 79 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 80 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 81 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 82 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 83 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 84 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 85 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 86 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 87 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 88 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 89 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 90 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 91 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 92 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 93 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 94 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 95 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 96 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 97 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 98 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 99 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 101 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 102 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 103 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 104 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 105 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 106 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 107 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 108 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 109 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 110 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 111 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 112 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 113 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 114 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 115 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 116 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 117 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 118 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 119 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 120 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 121 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 122 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 123 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 124 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 125 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 126 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 127 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 128 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 129 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 130 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 131 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 132 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 133 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 134 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 135 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 136 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 137 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 138 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 139 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 140 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 141 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 142 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 143 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 144 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 145 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 146 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 147 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 148 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 149 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 150 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 151 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 152 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 153 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 154 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 155 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 156 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 157 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 158 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 159 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 160 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 161 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 162 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 163 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 164 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 165 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 166 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 167 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 168 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 169 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 170 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 171 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 172 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 173 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 174 | DRAW FEE | 12000 | 0 | 12000 | 0 | 12000 | 0.08633% | 0.14773 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 175 | Total | 16921419.26 | 3021419.26 | 13900000 | 0 | 13900000 | 100% | 208.3226 | 13884153.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15846.9 | 0.114%
|  |  |  | 177 | Total Reimbursable | 16921419.26 |  | 13900000 |  | 13900000 | 100% | #DIV/0! | 13884153.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | #REF!
|  |  |  | 180 | Total Equity (Non Reimbursable) | 0 | 3021419.26 | 0 |  | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15846.9