## Product List (hidden)
ABATEMENT/REMEDIATION/ASBESTOS | 01u6S000018BAIdQAO | 01t6S00000BhEQIQA3
ADU | 01u6S00001842qmQAA | 01t6S00000BGzOMQA1
APPLIANCES | 01u6S000016ZYr8QAG | 01t6S00000BGmgVQAT
ARCHITECTURAL AND ENGINEERING | 01u6S000016ZYrpQAG | 01t6S00000BGmgXQAT
BATHROOM | 01u6S000018BAIeQAO | 01t6S00000BhEQJQA3
BUILDING CLEAN-UP | 01u6S000016ZYroQAG | 01t6S00000BGmhEQAT
CABINETS | 01u6S000016ZYrnQAG | 01t6S00000BGmgUQAT
COMPLETION AND INSPECTION | 01u6S000016ZYrlQAG | 01t6S00000BGmggQAD
CONCRETE | 01u6S000016ZYrkQAG | 01t6S00000BGmgxQAD
CONCRETE SUBFLOOR | 01u6S00001844JrQAI | 01t6S00000BH1bXQAT
CONCRETE WALL | 01u6S00001844JsQAI | 01t6S00000BH1bTQAT
CONTINGENCY | 01u6S000016ZYrjQAG | 01t6S00000BGmgfQAD
CURB & GUTTER | 01u6S000018BAIfQAO | 01t6S00000BhEQXQA3
DECKS/BALCONIES/PATIOS | 01u6S00001842qnQAA | 01t6S00000BGzO9QAL
DEMOLITION | 01u6S000016ZYriQAG | 01t6S00000BGmgmQAD
DRIVEWAY | 01u6S000016ZYrhQAG | 01t6S00000BGmhGQAT
DRY UTILITES | 01u6S000018BAIgQAO | 01t6S00000BhEQKQA3
DRYWALL | 01u6S000016ZYrgQAG | 01t6S00000BGmhBQAT
ELEVATOR | 01u6S000016ZYrfQAG | 01t6S00000BGmhAQAT
EXTERIOR PAINTING | 01u6S000016ZYrdQAG | 01t6S00000BGmhNQAT
EXTERIOR TRIM | 01u6S000016ZYrcQAG | 01t6S00000BGmhMQAT
EXTERIOR VENEER/STUCCO | 01u6S000016ZYrbQAG | 01t6S00000BGmh3QAD
FENCES | 01u6S00001844JtQAI | 01t6S00000BH1bcQAD
FIELD EQUIPMENT | 01u6S000016ZYraQAG | 01t6S00000BGmgdQAD
FINISH CARPENTRY/MILLWORK | 01u6S00001842qoQAA | 01t6S00000BGzOGQA1
FINISH ELECTRICAL | 01u6S000016ZYrZQAW | 01t6S00000BGmhIQAT
FINISH HARDWEAR | 01u6S00001842qpQAA | 01t6S00000BGzOFQA1
FINISH HVAC | 01u6S000016ZYrYQAW | 01t6S00000BGmhKQAT
FINISH PLUMBING | 01u6S000016ZYrXQAW | 01t6S00000BGmhHQAT
FINISH PLUMBING & ELECTRICAL | 01uRN000000K3o9YAC | 01tRN000001ORUj
FIRE SPRINKLERS | 01u6S000016ZYrWQAW | 01t6S00000BGmgzQAD
FIREPLACE | 01u6S00001842qqQAA | 01t6S00000BGzOAQA1
FIXTURES | 01u6S000018BAIhQAO | 01t6S00000BhEQcQAN
FLOORING | 01u6S000016ZYrVQAW | 01t6S00000BGmhOQAT
FOOTING AND FOUNDATIONS | 01u6S000016ZYrUQAW | 01t6S00000BGmgqQAD
FRAMING | 01u6S000016ZYrTQAW | 01t6S00000BGmgwQAD
GARAGE DOOR | 01u6S00001842qrQAA | 01t6S00000BGzOHQA1
GC FEE | 01u6S00001844JuQAI | 01t6S00000BH1bSQAT
GLASS/GLAZING | 01u6S00001842qsQAA | 01t6S00000BGzOEQA1
GRADING & EXCAVATION | 01u6S00001842qtQAA | 01t6S00000BGzO6QAL
HARDSCAPE | 01u6S000016ZYrSQAW | 01t6S00000BGmhDQAT
HARDWEAR | 01u6S00001842quQAA | 01t6S00000BGzO7QAL
HAULING/TRASH OUT/DUMPSTERS | 01u6S00001842qvQAA | 01t6S00000BGzO5QAL
INDIRECT CONSTRUCTION | 01u6S000016ZYrRQAW | 01t6S00000BGmgeQAD
INSULATION | 01u6S000016ZYrQQAW | 01t6S00000BGmh7QAD
INSURANCE | 01u6S000016ZYrPQAW | 01t6S00000BGmglQAD
INTERIOR DESIGN | 01u6S000016ZYrOQAW | 01t6S00000BGmgYQAT
INTERIOR DOORS | 01u6S00001842qwQAA | 01t6S00000BGzOCQA1
INTERIOR PAINTING | 01u6S00001842qxQAA | 01t6S00000BGzOBQA1
INTERIOR TRIM | 01u6S000016ZYrNQAW | 01t6S00000BGmhPQAT
INTERIOR/EXTERIOR PAINT | 01uRN000000K3kvYAC | 01tRN000001ONkV
KITCHEN | 01u6S000018BAIiQAO | 01t6S00000BhEQNQA3
LANDSCAPE/HARDSCAPE | 01uRN000000K3rNYAS | 01tRN000001OQs2
LANDSCAPING | 01u6S000016ZYrMQAW | 01t6S00000BGmhFQAT
LOW VOLTAGE | 01u6S00001842qyQAA | 01t6S00000BGzO8QAL
MASONRY | 01u6S000016ZYrLQAW | 01t6S00000BGmh5QAD
METALS AND GUTTER | 01u6S000016ZYrKQAW | 01t6S00000BGmh8QAD
MISCELLANEOUS | 01u6S000018BAIjQAO | 01t6S00000BhEQOQA3
ORNAMETAL IRON | 01u6S000016ZYrJQAW | 01t6S00000BGmhLQAT
OTHER | 01u6S00001844JvQAI | 01t6S00000BH1bhQAD
OVERHEAD | 01u6S000016ZYrIQAW | 01t6S00000BGmgiQAD
PERMITS AND FEES | 01u6S000016ZYrHQAW | 01t6S00000BGmgWQAT
POOL | 01u6S000016ZYrGQAW | 01t6S00000BGmhCQAT
PROJECT COMPLETION | 01uRN000000K3hhYAC | 01tRN000001OQdX
RETAINING WALLS | 01u6S000016ZYrFQAW | 01t6S00000BGmgoQAD
ROOFING | 01u6S000016ZYrEQAW | 01t6S00000BGmh4QAD
ROUGH ELECTRICAL | 01u6S000016ZYrDQAW | 01t6S00000BGmh1QAD
ROUGH HVAC | 01u6S000016ZYrCQAW | 01t6S00000BGmh2QAD
ROUGH MEP | 01uRN000000K3ubYAC | 01tRN000001OROH
ROUGH PLUMBING | 01u6S000016ZYrBQAW | 01t6S00000BGmh0QAD
ROUGH SHEET METAL | 01u6S000016ZYrAQAW | 01t6S00000BGmgyQAD
ROUGH STRUCTURE | 01u6S000016ZYr9QAG | 01t6S00000BGmguQAD
SEWER | 01u6S000018BAIkQAO | 01t6S00000BhEQSQA3
SHORING | 01u6S000016ZYrqQAG | 01t6S00000BGmgpQAD
SITE DRAINAGE | 01u6S000016ZYrrQAG | 01t6S00000BGmgsQAD
SITE WORK | 01u6S000016ZYrsQAG | 01t6S00000BGmgcQAD
SOFT COST | 01uRN000000K3xpYAC | 01tRN000001OO5T
SOLAR | 01u6S000016ZYrtQAG | 01t6S00000BGmhJQAT
SPECIALTIES | 01u6S00001842qzQAA | 01t6S00000BGzOIQA1
STAIRS | 01u6S000016ZYruQAG | 01t6S00000BGmh9QAD
STEEL | 01u6S000016ZYrvQAG | 01t6S00000BGmgvQAD
STONE & COUNTERTOPS | 01u6S000016ZYrwQAG | 01t6S00000BGmgTQAT
SUPERVISION & MANAGEMENT | 01u6S000016ZYrxQAG | 01t6S00000BGmgjQAD
TAXES | 01u6S000016ZYryQAG | 01t6S00000BGmgkQAD
TEMP FACLITIES | 01u6S000016ZYrzQAG | 01t6S00000BGmgaQAD
TEMP UTILITIES | 01u6S000016ZYs0QAG | 01t6S00000BGmgZQAT
TENANT IMPROVMENTS/COMMON AREA RENOVATIONS | 01u6S00001842r0QAA | 01t6S00000BGzOKQA1
TENNANT RELOCATION | 01u6S000018BAIlQAO | 01t6S00000BhEQDQA3
TERMITE PROTECTION | 01u6S000016ZYs1QAG | 01t6S00000BGmgtQAD
TILE | 01u6S00001842r1QAA | 01t6S00000BGzODQA1
UNIT | 01u6S00001842r2QAA | 01t6S00000BGzOLQA1
UTILITY CONNECTIONS | 01u6S000016ZYs2QAG | 01t6S00000BGmgbQAD
WALK THROUGH INSPECTION COSTS | 01u6S000016ZYs3QAG | 01t6S00000BGmghQAD
WATERPROOFING | 01u6S000016ZYs4QAG | 01t6S00000BGmgrQAD
WINDOW COVERINGS | 01u6S00001842r3QAA | 01t6S00000BGzOJQA1
WINDOWS AND DOORS | 01u6S000016ZYs5QAG | 01t6S00000BGmh6QAD

## Arixa SOV
Price Book Entry ID | Product ID | Product DO NOT MAP | Opportunity ID | z
[5 empty] | Property Address: | 1075 Century Drive, Ogden, UT 84404 | [11 empty] | Construction Loan Amount: | 16921419.26 |  |  | Expected Completion Date:
[5 empty] | Borrower Name: | Hunter's Landing North, LLC - Aubrey Palmer (PALMER AUBREY) | [7 empty] | Phone: | (801) 400-8452 |  |  | Remaining Balance Post Draw: | 1347133.978 |  |  | Draw Reimbursement % |  | 100%
[5 empty] | Draw Point Of Contact | - | [7 empty] | Phone: |  |  |  | Lock Box |  |  |  | Draw Fee Adjusted: |  | 500
[5 empty] | General Contractor: | [8 empty] | License: |  |  |  | Project Square Footage | 82227
[5 empty] | Inspectors Name: | [8 empty] | Phone: |  |  |  | Draw Processing Fee: | 500
|  |  |  | Item | Description | Budget | Pre-Funding | Approved | Reallocation | Revised Ready for Draw 16 | % | $ PSF | Balance | Draw #1 | Draw #2 | Draw #3 | Draw #4 | Draw #5 | Draw #6 | Draw #7 | Draw #8 | Draw #9 | Draw #10 | Draw #11 | Draw #12 | Draw #13 | Draw #14 | Draw #15 | Draw #16 | Draw #17 | Draw #18 | Draw #19 | Draw #20 | Draw #21 | Draw #22 | Draw #23 | Retainage | Costs-to-Date | %
|  |  |  | # |  | Amount | Costs-to-Date & Contributed costs | Current | (+/-) | Budget | Of | Of | Remaining | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) |  |  | Drawn
[7 empty] | (Non Reimbursable) | Budget |  |  | Revised | Revised
|  |  |  | 1 | Survey | 7000 | 0 | 3000 | 0 | 3000 | 0.02158% | 0.036484 | 117.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 679.25 | 0 | 1489.13 | 0 | 0 | 0 | 114.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2882.5 | 96.08%
|  |  |  | 2 | Excavation of building and site, backfill, sewer & water connections, elec service, asphalt | 1197367.29 | 300000 | 990748.23 | 0 | 990748.23 | 7.128% | 12.0489 | -0.03 | 109733.64 | 0 | 161975 | 132681.75 | 32262 | 0 | 0 | 267412.31 | 66040.68 | 43324.94 | 0 | 128248.05 | 0 | 0 | 0 | 49069.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990748.26 | 100%
|  |  |  | 3 | Footings & Foundations M&L & site M&L | 408552 | 216541.42 | 192010.58 | 0 | 192010.58 | 1.381% | 2.3351 | 5375.52 | 7268.96 | 0 | 2457.93 | 4200 | 2501.06 | 0 | 0 | 205.61 | 0 | 22608.58 | 41994.69 | 36906.25 | 10945.75 | 22124.34 | 0 | 17921.89 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186635.06 | 97.2%
|  |  |  | 4 | ALL FENCING | 44475 | 0 | 44475 | 0 | 44475 | 0.32% | 0.54088 | -163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24695.25 | 0 | 0 | 9942.75 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44638 | 100.4%
|  |  |  | 5 | TURNKEY FRAMING, | 2063122 | 100000 | 1963122 | 2497.86 | 1965619.86 | 14.14% | 23.9048 | -3986.42 | 479698.7 | 779032.3 | 236538.97 | 0 | 0 | 314493.69 | 0 | 0 | 28833.09 | 0 | 262.09 | 7395.77 | 8402 | 0 | 0 | 100963.25 | 13986.42 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 1969606.28 | 99.69%
|  |  |  | 6 | Roofing Labor and Materials | 235254.4 | 0 | 232828.4 | -66504.9 | 166323.5 | 1.197% | 2.0227 | 14275.1 | 0 | 0 | 0 | 80750 | 0 | 0 | 32694.82 | 0 | 0 | 0 | 0 | 23173.16 | 5000 | 0 | 0 | 10430.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152048.4 | 91.42%
|  |  |  | 7 | DECK COATINGS | 72445 | 0 | 72445 | 2300 | 74745 | 0.5377% | 0.90901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35625 | 0 | 0 | 0 | 39120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74745 | 100%
|  |  |  | 8 | Structural steel (Covered parking) | 35813.74 | 0 | 35813.74 | 0 | 35813.74 | 0.2577% | 0.43555 | 48.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16912.28 | 0 | 160 | 0 | 8456.14 | 0 | 10236.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35764.8 | 99.86%
|  |  |  | 9 | ALL OTHER STEEL FEATURES | 196050 | 0 | 196050 | 1477 | 197527 | 1.421% | 2.4022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1472.5 | 3132.15 | 0 | 84793.75 | 0 | 0 | 0 | 42096.87 | 0 | 66031.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197527 | 100%
|  |  |  | 10 | Windows | 170000 | 0 | 170000 | -42137.37 | 127862.63 | 0.9199% | 1.555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112463.49 | 0 | 0 | 0 | 0 | 0 | 9480 | 0 | 0 | 5919.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127862.63 | 100%
|  |  |  | 11 | Store Front L&M | 95488 | 0 | 95488 | 0 | 95488 | 0.687% | 1.1613 | 6926.52 | 0 | 0 | 0 | 0 | 0 | 0 | 44077.99 | 8374.81 | 34780.82 | 0 | 0 | 0 | 0 | 0 | 0 | 1327.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88561.48 | 92.75%
|  |  |  | 12 | ELEVATOR | 255500 | 0 | 255500 | 0 | 255500 | 1.838% | 3.1073 | -32197.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121362.5 | 0 | 0 | 0 | 0 | 0 | 0 | 109226.25 | 57108.75 | 0 | 0 | 0 | 0 | 0 | 0 | 12136.25 | 287697.5 | 107.9%
|  |  |  | 13 | HM door labor | 18575 | 0 | 18575 | 0 | 18575 | 0.1336% | 0.2259 | 7075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 11500 | 61.91%
|  |  |  | 14 | Plumbing | 1125000 | 338750 | 786250 | -72852.35 | 713397.65 | 5.132% | 8.676 | 20368.85 | 0 | 59375 | 106875 | 106875 | 0 | 85500 | 120705.28 | 53493.75 | 0 | 0 | 95000 | 0 | 14250 | 0 | 0 | 45954.77 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693028.8 | 97.14%
|  |  |  | 15 | HVAC | 1395000 | 150000 | 1395515 | 40956.5 | 1436471.5 | 10.33% | 17.4696 | -10300 | 0 | 0 | 114000 | 0 | 0 | 0 | 0 | 394842.8 | 104500 | 47500 | 118750 | 285000 | 216496.45 | 44650 | 0 | 110732.25 | 10300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1446771.5 | 100.7%
|  |  |  | 16 | Electric | 1186352 | 400000 | 901424.02 | 136124.96 | 1037548.98 | 7.464% | 12.6181 | -14521.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323729.12 | 99572.37 | 48997.2 | 46449.3 | 59850 | 138902.35 | 138852.48 | 0 | 129318.712 | 66398.45 | 0 | 0 | 0 | 0 | 0 | 0 | 51877.45 | 1052069.982 | 96.4%
|  |  |  | 17 | SPRINKLER SYSTEM | 156271 | 0 | 264734.34 | 12413.4 | 277147.74 | 1.994% | 3.3705 | -3897.33 | 0 | 0 | 0 | 41478.34 | 0 | 0 | 59452.5 | 76043.87 | 49774.13 | 12443.53 | 12443.52 | 0 | 12443.53 | 0 | 0 | 16965.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9346.66 | 281045.07 | 98.03%
|  |  |  | 18 | FIRE CAULKING | 10000 | 0 | 2000 | 0 | 2000 | 0.01439% | 0.024323 | 1141.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 858.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 858.16 | 42.91%
|  |  |  | 19 | GYPCRETE | 77757.03 | 0 | 77757.03 | 0 | 77757.03 | 0.5594% | 0.94564 | 12496.03 | 0 | 0 | 0 | 0 | 0 | 0 | 48014.97 | 4750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12496.03 | 0 | 0 | 0 | 0 | 0 | 0 | 2777.1 | 65261 | 80.36%
|  |  |  | 20 | Insulation | 232552 | 2600.62 | 229951.38 | 0 | 229951.38 | 1.654% | 2.7965 | 3532.3775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133591.14 | 19769.5 | 0 | 0 | 0 | 73058.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.88 | 226419.0025 | 98.4%
|  |  |  | 21 | Sheetrock | 850750 | 0 | 869045.96 | 45611.25 | 914657.21 | 6.58% | 11.1236 | -55847.9975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97970.35 | 244925.88 | 293910.65 | 146955.52 | 42000.37 | 0 | 0 | 88893.9375 | 55848.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 970505.2075 | 106.1%
|  |  |  | 22 | 2 layers of dens glass | 120000 | 0 | 25733.97 | -3611.25 | 22122.72 | 0.1592% | 0.26904 | 22122.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 23 | FINISH MATERIALS MISC | 325000 | 0 | 325000 | -42000 | 283000 | 2.036% | 3.4417 | -9794.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283000 | 0 | 0 | 0 | 0 | 9794.04 | 0 | 0 | 0 | 0 | 0 | 0 |  | 292794.04 | 103.5%
|  |  |  | 24 | Finish Labor | 95000 | 0 | 27942 | -24305.01 | 3636.99 | 0.02617% | 0.044231 | 3547.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 |  | 89 | 2.447%
|  |  |  | 25 | Interior Paint | 213852.35 | 213852.35 | 0 | 0 | 0 | 0% | 0 | -6800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6800 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6800
|  |  |  | 26 | CABINETS | 461324.15 | 261324.15 | 200000 | 14965.78 | 214965.78 | 1.547% | 2.6143 | -15964.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14217.49 | 0 | 82925 | 0 | 0 | 111221.25 | 22566.23 | 0 | 0 | 0 | 0 | 0 | 0 | 6602.04 | 230929.97 | 104.4%
|  |  |  | 27 | EQUIPMENT FOR CABINETS | 6000 | 0 | 862.94 | 0 | 862.94 | 0.006208% | 0.010495 | 862.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 28 | unit entry doors | 125000 | 0 | 125000 | -9569.38 | 115430.62 | 0.8304% | 1.4038 | 9021.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 0 | 9.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 106409.61 | 92.18%
|  |  |  | 29 | FLOOR PREP | 10000 | 0 | 10000 | 0 | 10000 | 0.07194% | 0.12161 | 8784.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1215.49 | 12.15%
|  |  |  | 30 | Hardware labor | 47550 | 0 | 47550 | -35550 | 12000 | 0.08633% | 0.14594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12000 | 100%
|  |  |  | 31 | Hardware & HM frames & doors | 58110.22 | 0 | 81264.95 | 0 | 81264.95 | 0.5846% | 0.9883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2625 | 0 | 0 | 0 | 0 | 0 | 78639.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 81264.95 | 100%
|  |  |  | 32 | FIRE EXTINGUSHERS | 7850 | 0 | 7850 | 0 | 7850 | 0.05647% | 0.095467 | -8993.75 | 0 | 0 | 0 | 228.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6941.5 | 0 | 328.5 | 9345.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16843.75 | 214.6%
|  |  |  | 33 | MIRRORS | 34000 | 0 | 30252 | 899.33 | 31151.33 | 0.2241% | 0.37885 | -0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11494.05 | 5799.31 | 0 | 13858.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.1 | 31151.43 | 100%
|  |  |  | 34 | All flooring & wall tile M&L | 312858 | 0 | 312858 | 0 | 312858 | 2.251% | 3.8048 | 18088.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92688.22 | 0 | 0 | 0 | 0 | 202081.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15514.19 | 294769.56 | 89.26%
|  |  |  | 35 | Brick, Stucco, Soffit & fascia | 748952 | 0 | 872347.22 | 0 | 872347.22 | 6.276% | 10.609 | -10275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33330.46 | 227221.47 | 122350.02 | 165070.98 | 165070.95 | 116255.53 | 0 | 0 | 0 | 53322.81 | 0 | 0 | 0 | 0 | 0 | 0 | 43047.81 | 882622.22 | 96.24%
|  |  |  | 36 | GUTTER | 14500 | 0 | 14500 | 0 | 14500 | 0.1043% | 0.17634 | 14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 37 | PLASTER FOUNDATION | 4250 | 0 | 4250 | 0 | 4250 | 0.03058% | 0.051686 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 38 | ROOF HATCH | 1600 | 0 | 4026 | 0 | 4026 | 0.02896% | 0.048962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3824.7 | 0 | 0 | 0 | 201.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4026 | 100%
|  |  |  | 39 | PICKLEBALL | 35000 | 0 | 35000 | 0 | 35000 | 0.2518% | 0.42565 | -932.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23328.19 | 0 | 2304 | 10300 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 35932.19 | 102.7%
|  |  |  | 40 | 2 VAC STATIONS | 7500 | 0 | 7500 | 0 | 7500 | 0.05396% | 0.091211 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 41 | MAILBOXES | 16000 | 0 | 16000 | 0 | 16000 | 0.1151% | 0.19458 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15460 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15810 | 98.81%
|  |  |  | 42 | DOG WASH STATION | 5000 | 0 | 5000 | 0 | 5000 | 0.03597% | 0.060807 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 43 | BLINDS | 25000 | 0 | 25000 | 0 | 25000 | 0.1799% | 0.30404 | 4048.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9701.2 | 0 | 0 | 0 | 0 | 11250.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20951.57 | 83.81%
|  |  |  | 44 | 2 FIRE PITS | 6000 | 0 | 201.99 | 0 | 201.99 | 0.001453% | 0.0024565 | 201.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 45 | CLUB HOUSE PERGULA | 30000 | 0 | 30000 | 0 | 30000 | 0.2158% | 0.36484 | 7529.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663.84 | 646.14 | 20102.36 | 0 | 1058.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22470.36 | 74.9%
|  |  |  | 46 | KNOX BOX & FIRE LIDS | 2450 | 0 | 2450 | 0 | 2450 | 0.01763% | 0.029796 | 1148.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1301.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1301.04 | 53.1%
|  |  |  | 47 | LANDSCAPE | 125000 | 0 | 215058 | 0 | 215058 | 1.547% | 2.6154 | -17170.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7980 | 0 | 196325.1 | 0 | 420 | 27503.15 | 0 | 0 | 0 | 0 | 0 | 0 | 10332.9 | 232228.25 | 103.2%
|  |  |  | 48 | APPLIANCES | 264800 | 0 | 354892.58 | 994.21 | 355886.79 | 2.56% | 4.3281 | -497.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181042.42 | 173850.16 | 0 | 994.21 | 497.64 | 0 | 0 | 0 | 0 | 0 | 0 |  | 356384.43 | 100.1%
|  |  |  | 49 | SIGNAGE | 7500 | 0 | 7500 | 0 | 7500 | 0.05396% | 0.091211 | 2608.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 391.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4891.96 | 65.23%
|  |  |  | 50 | EXTERIOR FFE | 10000 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 51 | CONTINGENCY | 1243628.52 | 0 | 547801 | -14275.1 | 533525.9 | 3.838% | 6.4885 | 527525.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6000 | 1.125%
|  |  |  | 52 | EQUIPMENT | 25000 | 0 | 63036.46 | 5578.47 | 68614.93 | 0.4936% | 0.83446 | -994.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10706.69 | 23046.13 | 17137.06 | 12146.58 | 0 | 5578.47 | 994.21 | 0 | 0 | 0 | 0 | 0 | 0 |  | 69609.14 | 101.4%
|  |  |  | 53 | HONEY BUCKET | 7000 | 565.69 | 14540.37 | 479.2 | 15019.57 | 0.1081% | 0.18266 | -996.55 | 373.54 | 239.79 | 1457.96 | 592.9 | 592.9 | 0 | 1334.04 | 861.13 | 1593.68 | 1316.13 | 1717.59 | 1597.58 | 1677.21 | 1185.92 | 0 | 479.2 | 996.55 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16016.12 | 106.6%
|  |  |  | 54 | DUMPSTER | 22000 | 0 | 38489.21 | 1388.02 | 39877.23 | 0.2869% | 0.48497 | -1271.99 | 75 | 1042.4 | 1415.85 | 3129.78 | 1820.77 | 0 | 1951.42 | 2735.84 | 2614.21 | 5830.81 | 6241.38 | 6071.65 | 2957.54 | 2602.56 | 0 | 1388.02 | 1271.99 | 0 | 0 | 0 | 0 | 0 | 0 |  | 41149.22 | 103.2%
|  |  |  | 55 | TEMP FENCE | 25000 | 14030 | 7395.45 | 0 | 7395.45 | 0.0532% | 0.089939 | 2817.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052.88 | 0 | 1052.88 | 1757.3 | 107.3 | 107.3 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4577.66 | 61.9%
|  |  |  | 56 | CLEAN-UP LABOR | 25000 | 0 | 25000 | 4244.57 | 29244.57 | 0.2104% | 0.35566 | -3490 | 0 | 0 | 0 | 0 | 0 | 0 | 1667.03 | 4855.18 | 2340 | 2040 | 1643.41 | 0 | 7048.95 | 5250 | 0 | 4400 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32734.57 | 111.9%
|  |  |  | 57 | FINAL CLEAN | 27000 | 0 | 27000 | 0 | 27000 | 0.1942% | 0.32836 | -2374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13396.6 | 0 | 6744.25 | 9233.15 | 0 | 0 | 0 | 0 | 0 | 0 |  | 29374 | 108.8%
|  |  |  | 58 | STREET SWEEPING | 4000 | 0 | 4000 | 0 | 4000 | 0.02878% | 0.048646 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 59 | CONC WASH OUT | 4000 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 60 | SWPPP weekly inspection | 9000 | 0 | 9005.75 | 675 | 9680.75 | 0.06965% | 0.11773 | 0 | 900 | 450 | 900 | 450 | 450 | 355.75 | 1900 | 900 | 450 | 450 | 450 | 450 | 450 | 450 | 0 | 675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9680.75 | 100%
|  |  |  | 61 | TEMP POWER | 7500 | 0 | 7782.64 | 48.06 | 7830.7 | 0.05634% | 0.095233 | 0 | 243.49 | 1797.51 | 304.14 | 432.3 | 428.07 | 2409.34 | 0 | 527.92 | 155.79 | 195.03 | 216.44 | 346.66 | 388.29 | 337.66 | 0 | 48.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 7830.7 | 100%
|  |  |  | 62 | OFFICE TRAILER | 13500 | 0 | 17061.64 | 0 | 17061.64 | 0.1227% | 0.20749 | 0 | 3299.17 | 203.3 | 2122.76 | 1231.89 | 0 | 0 | 0 | 3184.14 | 1061.38 | 1061.38 | 1061.38 | 1061.38 | 1163.26 | 1611.6 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 17061.64 | 100%
|  |  |  | 63 | SECURITY CAMERAS | 35000 | 0 | 40902 | 321.75 | 41223.75 | 0.2966% | 0.50134 | 0 | 2750 | 2750 | 2750 | 4550 | 500 | 5500 | 600 | 8850 | 5265 | 3050 | 3050 | 321.75 | 321.75 | 643.5 | 0 | 321.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 41223.75 | 100%
|  |  |  | 64 | SPECIAL INSPECTIONS | 10000 | 4538 | 7767 | 0 | 7767 | 0.05588% | 0.094458 | -1752.8 | 74.8 | 3720.8 | 260.8 | 252.8 | 0 | 0 | 0 | 2003.8 | 0 | 1201.2 | 0 | 0 | 252.8 | 0 | 0 | 0 | 1752.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9519.8 | 122.6%
|  |  |  | 65 | SAFTEY | 7500 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 66 | GENERAL CONDITIONS | 30000 | 0 | 12792.62 | 0 | 12792.62 | 0.09203% | 0.15558 | 2264.4 | 0 | 0 | 0 | 471.87 | 0 | 0 | 0 | 511.88 | 1587.51 | 1148.63 | 0 | 2165.53 | 0 | 0 | 0 | 461.28 | 4181.52 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10528.22 | 82.3%
|  |  |  | 67 | Insurance | 180000 | 171331 | 8669 | 3830 | 12499 | 0.08992% | 0.15201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12499 | 100%
|  |  |  | 68 | SITE SUPERVISION, PM, SUPER | 260000 | 27000 | 272000 | 36000 | 308000 | 2.216% | 3.7457 | -30000 | 29000 | 17000 | 17000 | 17000 | 17000 | 34000 | 0 | 34000 | 17000 | 18000 | 18000 | 18000 | 18000 | 18000 | 0 | 36000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 338000 | 109.7%
|  |  |  | 69 | Construction Profit | 667000 | 200000 | 467000 | 0 | 467000 | 3.36% | 5.6794 | 117000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 50000 | 0 | 100000 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 350000 | 74.95%
|  |  |  | 70 | Soft Cost | 588368.19 | 588368.19 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 71 | CM Fee | 765501.37 | 32517.84 | 732983.53 | 0 | 732983.53 | 5.273% | 8.9141 | 732983.53 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0 | 0%
|  |  |  | 72 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 73 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 74 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 75 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 76 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 77 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 78 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 79 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 80 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 81 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 82 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 83 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 84 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 85 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 86 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 87 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 88 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 89 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 90 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 91 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 92 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 93 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 94 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 95 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 96 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 97 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 98 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 99 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 101 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 102 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 103 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 104 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 105 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 106 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 107 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 108 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 109 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 110 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 111 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 112 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 113 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 114 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 115 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 116 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 117 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 118 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 119 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 120 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 121 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 122 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 123 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 124 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 125 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 126 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 127 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 128 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 129 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 130 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 131 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 132 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 133 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 134 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 135 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 136 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 137 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 138 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 139 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 140 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 141 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 142 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 143 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 144 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 145 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 146 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 147 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 148 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 149 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 150 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 151 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 152 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 153 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 154 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 155 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 156 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 157 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 158 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 159 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 160 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 161 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 162 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 163 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 164 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 165 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 166 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 167 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 168 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 169 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 170 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 171 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 172 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 173 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0
|  |  |  | 174 | DRAW FEE | 12000 | 0 | 12000 | 0 | 12000 | 0.08633% | 0.14594 | 12000 | Draw #20: 0; Draw #21: 0; Draw #22: 0; Draw #23: 0 |  | 0 | 0%
|  |  |  | 175 | Total | 16921419.26 | 3021419.26 | 13900000 | 0 | 13900000 | 100% | 169.0442 | 1347133.978 | 633417.3 | 865611.1 | 648058.41 | 394325.31 | 55554.8 | 442258.78 | 426334.04 | 1227585.26 | 864634.02 | 678828.61 | 1099679.05 | 1259929.85 | 1124483 | 973298.12 | 0 | 1412092.062 | 446776.31 | 0 | 0 | 0 | 0 | 0 | 0 | 161772.68 | 12552866.02 | 89.14%
|  |  |  | 176 | Total Reimbursable | 16921419.26 |  | 13900000 |  | 13900000 | 100% | #DIV/0! | 1347133.978 | 633417.3 | 865611.1 | 648058.41 | 394325.31 | 55554.8 | 442258.78 | 426334.04 | 1227585.26 | 864634.02 | 678828.61 | 1099679.05 | 1259929.85 | 1124483 | 973298.12 | 0 | 1412092.062 | 446776.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
|  |  |  | 177 | Total Equity (Non Reimbursable) | 0 | 3021419.26 | 0 |  | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161772.68 | 12552866.02
-47164.41

## INTERNAL VERSION
Price Book Entry ID | Product ID | Product DO NOT MAP | Opportunity ID
[5 empty] | Property Address: | 1075 Century Drive, Ogden, UT 84404 | [11 empty] | Construction Loan Amount: | 16921419.26 |  |  | Expected Completion Date:
[5 empty] | Borrower Name: | Hunter's Landing North, LLC - Aubrey Palmer (PALMER AUBREY) | [7 empty] | Phone: | (801) 400-8452 |  |  | Remaining Balance Post Draw: | 239473.2569 |  |  | Draw Reimbursement % |  | 100%
[5 empty] | Draw Point Of Contact | - | [7 empty] | Phone: |  |  |  | Lock Box |  |  |  | Draw Fee Adjusted: |  | 500
[5 empty] | General Contractor: | [8 empty] | License: |  |  |  | Project Square Footage | 82227
[5 empty] | Inspectors Name: | [8 empty] | Phone: |  |  |  | Draw Processing Fee: | 500
|  |  |  | Item | Description | Budget | Pre-Funding | Approved | Reallocation | Revised Ready for Draw 16 | % | $ PSF | Balance | Draw #1 | Draw #2 | Draw #3 | Draw #4 | Draw #5 | Draw #6 | Draw #7 | Draw #8 | Draw #9 | Draw #10 | Draw #11 | Draw #12 | Draw #13 | Draw #14 | Draw #15 | Draw #16 | Draw #17 | Draw #18 | Draw #19 | Draw #20 | Draw #21 | Draw #22 | Draw #23 | Retainage | Costs-to-Date | %
|  |  |  | # |  | Amount | Costs-to-Date & Contributed costs | Current | (+/-) | Budget | Of | Of | Remaining | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) | Amount(s) |  |  | Drawn
[7 empty] | (Non Reimbursable) | Budget |  |  | Revised | Revised
|  |  |  | 1 | Survey | 7000 | 0 | 3000 | 0 | 3000 | 0.02158% | 0.036484 | 117.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 679.25 | 0 | 1489.13 | 0 | 0 | 0 | 114.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2882.5 | 96.08%
|  |  |  | 2 | Excavation of building and site, backfill, sewer & water connections, elec service, asphalt | 1197367.29 | 300000 | 990748.23 | 0 | 990748.23 | 7.128% | 12.0489 | -0.03 | 109733.64 | 0 | 161975 | 132681.75 | 32262 | 0 | 0 | 267412.31 | 66040.68 | 43324.94 | 0 | 128248.05 | 0 | 0 | 0 | 49069.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990748.26 | 100%
|  |  |  | 3 | Footings & Foundations M&L & site M&L | 408552 | 216541.42 | 192010.58 | 0 | 192010.58 | 1.381% | 2.3351 | 5375.52 | 7268.96 | 0 | 2457.93 | 4200 | 2501.06 | 0 | 0 | 205.61 | 0 | 22608.58 | 41994.69 | 36906.25 | 10945.75 | 22124.34 | 0 | 17921.89 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186635.06 | 97.2%
|  |  |  | 4 | ALL FENCING | 44475 | 0 | 44475 | 0 | 44475 | 0.32% | 0.54088 | -163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24695.25 | 0 | 0 | 9942.75 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44638 | 100.4%
|  |  |  | 5 | TURNKEY FRAMING, | 2063122 | 100000 | 1963122 | 2497.86 | 1965619.86 | 14.14% | 23.9048 | -3986.42 | 479698.7 | 779032.3 | 236538.97 | 0 | 0 | 314493.69 | 0 | 0 | 28833.09 | 0 | 262.09 | 7395.77 | 8402 | 0 | 0 | 100963.25 | 13986.42 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 1969606.28 | 99.69%
|  |  |  | 6 | Roofing Labor and Materials | 235254.4 | 0 | 232828.4 | -66504.9 | 166323.5 | 1.197% | 2.0227 | 14275.1 | 0 | 0 | 0 | 80750 | 0 | 0 | 32694.82 | 0 | 0 | 0 | 0 | 23173.16 | 5000 | 0 | 0 | 10430.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152048.4 | 91.42%
|  |  |  | 7 | DECK COATINGS | 72445 | 0 | 72445 | 2300 | 74745 | 0.5377% | 0.90901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35625 | 0 | 0 | 0 | 39120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74745 | 100%
|  |  |  | 8 | Structural steel (Covered parking) | 35813.74 | 0 | 35813.74 | 0 | 35813.74 | 0.2577% | 0.43555 | 48.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16912.28 | 0 | 160 | 0 | 8456.14 | 0 | 10236.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35764.8 | 99.86%
|  |  |  | 9 | ALL OTHER STEEL FEATURES | 196050 | 0 | 196050 | 1477 | 197527 | 1.421% | 2.4022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1472.5 | 3132.15 | 0 | 84793.75 | 0 | 0 | 0 | 42096.87 | 0 | 66031.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197527 | 100%
|  |  |  | 10 | Windows | 170000 | 0 | 170000 | -42137.37 | 127862.63 | 0.9199% | 1.555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112463.49 | 0 | 0 | 0 | 0 | 0 | 9480 | 0 | 0 | 5919.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127862.63 | 100%
|  |  |  | 11 | Store Front L&M | 95488 | 0 | 95488 | 0 | 95488 | 0.687% | 1.1613 | 6926.52 | 0 | 0 | 0 | 0 | 0 | 0 | 44077.99 | 8374.81 | 34780.82 | 0 | 0 | 0 | 0 | 0 | 0 | 1327.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88561.48 | 92.75%
|  |  |  | 12 | ELEVATOR | 255500 | 0 | 255500 | 0 | 255500 | 1.838% | 3.1073 | -32197.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121362.5 | 0 | 0 | 0 | 0 | 0 | 0 | 109226.25 | 57108.75 | 0 | 0 | 0 | 0 | 0 | 0 | 12136.25 | 287697.5 | 107.9%
|  |  |  | 13 | HM door labor | 18575 | 0 | 18575 | 0 | 18575 | 0.1336% | 0.2259 | 7075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 11500 | 61.91%
|  |  |  | 14 | Plumbing | 1125000 | 338750 | 786250 | -72852.35 | 713397.65 | 5.132% | 8.676 | 20368.85 | 0 | 59375 | 106875 | 106875 | 0 | 85500 | 120705.28 | 53493.75 | 0 | 0 | 95000 | 0 | 14250 | 0 | 0 | 45954.77 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693028.8 | 97.14%
|  |  |  | 15 | HVAC | 1395000 | 150000 | 1395515 | 40956.5 | 1436471.5 | 10.33% | 17.4696 | -10300 | 0 | 0 | 114000 | 0 | 0 | 0 | 0 | 394842.8 | 104500 | 47500 | 118750 | 285000 | 216496.45 | 44650 | 0 | 110732.25 | 10300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1446771.5 | 100.7%
|  |  |  | 16 | Electric | 1186352 | 400000 | 901424.02 | 136124.96 | 1037548.98 | 7.464% | 12.6181 | -14521.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323729.12 | 99572.37 | 48997.2 | 46449.3 | 59850 | 138902.35 | 138852.48 | 0 | 129318.712 | 66398.45 | 0 | 0 | 0 | 0 | 0 | 0 | 51877.45 | 1052069.982 | 96.4%
|  |  |  | 17 | SPRINKLER SYSTEM | 156271 | 0 | 264734.34 | 12413.4 | 277147.74 | 1.994% | 3.3705 | -3897.33 | 0 | 0 | 0 | 41478.34 | 0 | 0 | 59452.5 | 76043.87 | 49774.13 | 12443.53 | 12443.52 | 0 | 12443.53 | 0 | 0 | 16965.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9346.66 | 281045.07 | 98.03%
|  |  |  | 18 | FIRE CAULKING | 10000 | 0 | 2000 | 0 | 2000 | 0.01439% | 0.024323 | 1141.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 858.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 858.16 | 42.91%
|  |  |  | 19 | GYPCRETE | 77757.03 | 0 | 77757.03 | 0 | 77757.03 | 0.5594% | 0.94564 | 12496.03 | 0 | 0 | 0 | 0 | 0 | 0 | 48014.97 | 4750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12496.03 | 0 | 0 | 0 | 0 | 0 | 0 | 2777.1 | 65261 | 80.36%
|  |  |  | 20 | Insulation | 232552 | 2600.62 | 229951.38 | 0 | 229951.38 | 1.654% | 2.7965 | 3532.3775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133591.14 | 19769.5 | 0 | 0 | 0 | 73058.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.88 | 226419.0025 | 98.4%
|  |  |  | 21 | Sheetrock | 850750 | 0 | 869045.96 | 45611.25 | 914657.21 | 6.58% | 11.1236 | -55847.9975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97970.35 | 244925.88 | 293910.65 | 146955.52 | 42000.37 | 0 | 0 | 88893.9375 | 55848.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 970505.2075 | 106.1%
|  |  |  | 22 | 2 layers of dens glass | 120000 | 0 | 25733.97 | -3611.25 | 22122.72 | 0.1592% | 0.26904 | 22122.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 23 | FINISH MATERIALS MISC | 325000 | 0 | 325000 | -42000 | 283000 | 2.036% | 3.4417 | -9794.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283000 | 0 | 0 | 0 | 0 | 9794.04 | 0 | 0 | 0 | 0 | 0 | 0 |  | 292794.04 | 103.5%
|  |  |  | 24 | Finish Labor | 95000 | 0 | 27942 | -24305.01 | 3636.99 | 0.02617% | 0.044231 | 3547.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 |  | 89 | 2.447%
|  |  |  | 25 | Interior Paint | 213852.35 | 213852.35 | 0 | 0 | 0 | 0% | 0 | -6800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6800 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6800
|  |  |  | 26 | CABINETS | 461324.15 | 261324.15 | 200000 | 14965.78 | 214965.78 | 1.547% | 2.6143 | -15964.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14217.49 | 0 | 82925 | 0 | 0 | 111221.25 | 22566.23 | 0 | 0 | 0 | 0 | 0 | 0 | 6602.04 | 230929.97 | 104.4%
|  |  |  | 27 | EQUIPMENT FOR CABINETS | 6000 | 0 | 862.94 | 0 | 862.94 | 0.006208% | 0.010495 | 862.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 28 | unit entry doors | 125000 | 0 | 125000 | -9569.38 | 115430.62 | 0.8304% | 1.4038 | 9021.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 0 | 9.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 106409.61 | 92.18%
|  |  |  | 29 | FLOOR PREP | 10000 | 0 | 10000 | 0 | 10000 | 0.07194% | 0.12161 | 8784.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1215.49 | 12.15%
|  |  |  | 30 | Hardware labor | 47550 | 0 | 47550 | -35550 | 12000 | 0.08633% | 0.14594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12000 | 100%
|  |  |  | 31 | Hardware & HM frames & doors | 58110.22 | 0 | 81264.95 | 0 | 81264.95 | 0.5846% | 0.9883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2625 | 0 | 0 | 0 | 0 | 0 | 78639.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 81264.95 | 100%
|  |  |  | 32 | FIRE EXTINGUSHERS | 7850 | 0 | 7850 | 0 | 7850 | 0.05647% | 0.095467 | -8993.75 | 0 | 0 | 0 | 228.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6941.5 | 0 | 328.5 | 9345.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16843.75 | 214.6%
|  |  |  | 33 | MIRRORS | 34000 | 0 | 30252 | 899.33 | 31151.33 | 0.2241% | 0.37885 | -0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11494.05 | 5799.31 | 0 | 13858.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.1 | 31151.43 | 100%
|  |  |  | 34 | All flooring & wall tile M&L | 312858 | 0 | 312858 | 0 | 312858 | 2.251% | 3.8048 | 18088.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92688.22 | 0 | 0 | 0 | 0 | 202081.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15514.19 | 294769.56 | 89.26%
|  |  |  | 35 | Brick, Stucco, Soffit & fascia | 748952 | 0 | 872347.22 | 0 | 872347.22 | 6.276% | 10.609 | -10275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33330.46 | 227221.47 | 122350.02 | 165070.98 | 165070.95 | 116255.53 | 0 | 0 | 0 | 53322.81 | 0 | 0 | 0 | 0 | 0 | 0 | 43047.81 | 882622.22 | 96.24%
|  |  |  | 36 | GUTTER | 14500 | 0 | 14500 | 0 | 14500 | 0.1043% | 0.17634 | 14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 37 | PLASTER FOUNDATION | 4250 | 0 | 4250 | 0 | 4250 | 0.03058% | 0.051686 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 38 | ROOF HATCH | 1600 | 0 | 4026 | 0 | 4026 | 0.02896% | 0.048962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3824.7 | 0 | 0 | 0 | 201.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4026 | 100%
|  |  |  | 39 | PICKLEBALL | 35000 | 0 | 35000 | 0 | 35000 | 0.2518% | 0.42565 | -932.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23328.19 | 0 | 2304 | 10300 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 35932.19 | 102.7%
|  |  |  | 40 | 2 VAC STATIONS | 7500 | 0 | 7500 | 0 | 7500 | 0.05396% | 0.091211 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 41 | MAILBOXES | 16000 | 0 | 16000 | 0 | 16000 | 0.1151% | 0.19458 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15460 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15810 | 98.81%
|  |  |  | 42 | DOG WASH STATION | 5000 | 0 | 5000 | 0 | 5000 | 0.03597% | 0.060807 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 43 | BLINDS | 25000 | 0 | 25000 | 0 | 25000 | 0.1799% | 0.30404 | 4048.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9701.2 | 0 | 0 | 0 | 0 | 11250.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20951.57 | 83.81%
|  |  |  | 44 | 2 FIRE PITS | 6000 | 0 | 201.99 | 0 | 201.99 | 0.001453% | 0.0024565 | 201.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 45 | CLUB HOUSE PERGULA | 30000 | 0 | 30000 | 0 | 30000 | 0.2158% | 0.36484 | 7529.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663.84 | 646.14 | 20102.36 | 0 | 1058.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22470.36 | 74.9%
|  |  |  | 46 | KNOX BOX & FIRE LIDS | 2450 | 0 | 2450 | 0 | 2450 | 0.01763% | 0.029796 | 1148.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1301.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1301.04 | 53.1%
|  |  |  | 47 | LANDSCAPE | 125000 | 0 | 215058 | 0 | 215058 | 1.547% | 2.6154 | -17170.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7980 | 0 | 196325.1 | 0 | 420 | 27503.15 | 0 | 0 | 0 | 0 | 0 | 0 | 10332.9 | 232228.25 | 103.2%
|  |  |  | 48 | APPLIANCES | 264800 | 0 | 354892.58 | 994.21 | 355886.79 | 2.56% | 4.3281 | -497.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181042.42 | 173850.16 | 0 | 994.21 | 497.64 | 0 | 0 | 0 | 0 | 0 | 0 |  | 356384.43 | 100.1%
|  |  |  | 49 | SIGNAGE | 7500 | 0 | 7500 | 0 | 7500 | 0.05396% | 0.091211 | 2608.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 391.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4891.96 | 65.23%
|  |  |  | 50 | EXTERIOR FFE | 10000 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 51 | CONTINGENCY | 1243628.52 | 0 | 547801 | -14275.1 | 533525.9 | 3.838% | 6.4885 | 227525.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 306000 | 57.35%
|  |  |  | 52 | EQUIPMENT | 25000 | 0 | 63036.46 | 5578.47 | 68614.93 | 0.4936% | 0.83446 | -994.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10706.69 | 23046.13 | 17137.06 | 12146.58 | 0 | 5578.47 | 994.21 | 0 | 0 | 0 | 0 | 0 | 0 |  | 69609.14 | 101.4%
|  |  |  | 53 | HONEY BUCKET | 7000 | 565.69 | 14540.37 | 479.2 | 15019.57 | 0.1081% | 0.18266 | -996.55 | 373.54 | 239.79 | 1457.96 | 592.9 | 592.9 | 0 | 1334.04 | 861.13 | 1593.68 | 1316.13 | 1717.59 | 1597.58 | 1677.21 | 1185.92 | 0 | 479.2 | 996.55 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16016.12 | 106.6%
|  |  |  | 54 | DUMPSTER | 22000 | 0 | 38489.21 | 1388.02 | 39877.23 | 0.2869% | 0.48497 | -1271.99 | 75 | 1042.4 | 1415.85 | 3129.78 | 1820.77 | 0 | 1951.42 | 2735.84 | 2614.21 | 5830.81 | 6241.38 | 6071.65 | 2957.54 | 2602.56 | 0 | 1388.02 | 1271.99 | 0 | 0 | 0 | 0 | 0 | 0 |  | 41149.22 | 103.2%
|  |  |  | 55 | TEMP FENCE | 25000 | 14030 | 7395.45 | 0 | 7395.45 | 0.0532% | 0.089939 | 2817.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052.88 | 0 | 1052.88 | 1757.3 | 107.3 | 107.3 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4577.66 | 61.9%
|  |  |  | 56 | CLEAN-UP LABOR | 25000 | 0 | 25000 | 4244.57 | 29244.57 | 0.2104% | 0.35566 | -3490 | 0 | 0 | 0 | 0 | 0 | 0 | 1667.03 | 4855.18 | 2340 | 2040 | 1643.41 | 0 | 7048.95 | 5250 | 0 | 4400 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32734.57 | 111.9%
|  |  |  | 57 | FINAL CLEAN | 27000 | 0 | 27000 | 0 | 27000 | 0.1942% | 0.32836 | -2374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13396.6 | 0 | 6744.25 | 9233.15 | 0 | 0 | 0 | 0 | 0 | 0 |  | 29374 | 108.8%
|  |  |  | 58 | STREET SWEEPING | 4000 | 0 | 4000 | 0 | 4000 | 0.02878% | 0.048646 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
|  |  |  | 59 | CONC WASH OUT | 4000 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 60 | SWPPP weekly inspection | 9000 | 0 | 9005.75 | 675 | 9680.75 | 0.06965% | 0.11773 | 0 | 900 | 450 | 900 | 450 | 450 | 355.75 | 1900 | 900 | 450 | 450 | 450 | 450 | 450 | 450 | 0 | 675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9680.75 | 100%
|  |  |  | 61 | TEMP POWER | 7500 | 0 | 7782.64 | 48.06 | 7830.7 | 0.05634% | 0.095233 | 0 | 243.49 | 1797.51 | 304.14 | 432.3 | 428.07 | 2409.34 | 0 | 527.92 | 155.79 | 195.03 | 216.44 | 346.66 | 388.29 | 337.66 | 0 | 48.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 7830.7 | 100%
|  |  |  | 62 | OFFICE TRAILER | 13500 | 0 | 17061.64 | 0 | 17061.64 | 0.1227% | 0.20749 | 0 | 3299.17 | 203.3 | 2122.76 | 1231.89 | 0 | 0 | 0 | 3184.14 | 1061.38 | 1061.38 | 1061.38 | 1061.38 | 1163.26 | 1611.6 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 17061.64 | 100%
|  |  |  | 63 | SECURITY CAMERAS | 35000 | 0 | 40902 | 321.75 | 41223.75 | 0.2966% | 0.50134 | 0 | 2750 | 2750 | 2750 | 4550 | 500 | 5500 | 600 | 8850 | 5265 | 3050 | 3050 | 321.75 | 321.75 | 643.5 | 0 | 321.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 41223.75 | 100%
|  |  |  | 64 | SPECIAL INSPECTIONS | 10000 | 4538 | 7767 | 0 | 7767 | 0.05588% | 0.094458 | -1752.8 | 74.8 | 3720.8 | 260.8 | 252.8 | 0 | 0 | 0 | 2003.8 | 0 | 1201.2 | 0 | 0 | 252.8 | 0 | 0 | 0 | 1752.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9519.8 | 122.6%
|  |  |  | 65 | SAFTEY | 7500 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 66 | GENERAL CONDITIONS | 30000 | 0 | 12792.62 | 0 | 12792.62 | 0.09203% | 0.15558 | 2264.4 | 0 | 0 | 0 | 471.87 | 0 | 0 | 0 | 511.88 | 1587.51 | 1148.63 | 0 | 2165.53 | 0 | 0 | 0 | 461.28 | 4181.52 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10528.22 | 82.3%
|  |  |  | 67 | Insurance | 180000 | 171331 | 8669 | 3830 | 12499 | 0.08992% | 0.15201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12499 | 100%
|  |  |  | 68 | SITE SUPERVISION, PM, SUPER | 260000 | 27000 | 272000 | 36000 | 308000 | 2.216% | 3.7457 | -30000 | 29000 | 17000 | 17000 | 17000 | 17000 | 34000 | 0 | 34000 | 17000 | 18000 | 18000 | 18000 | 18000 | 18000 | 0 | 36000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 338000 | 109.7%
|  |  |  | 69 | Construction Profit | 667000 | 200000 | 467000 | 0 | 467000 | 3.36% | 5.6794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 50000 | 0 | 100000 | 117000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 467000 | 100%
|  |  |  | 70 | Soft Cost | 588368.19 | 588368.19 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 71 | CM Fee | 765501.37 | 32517.84 | 732983.53 | 0 | 732983.53 | 5.273% | 8.9141 | 50322.8089 | 31670.865 | 45486.89 | 56446.59 | 33096.9445 | 6277.74 | 22112.94 | 21316.7 | 61379.263 | 47231.701 | 49166.9805 | 54983.9525 | 62996.4925 | 56224.15 | 48664.91 | 15000 | 70604.6021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 682660.7211 | 93.13%
|  |  |  | 72 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 73 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 74 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 75 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 76 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 77 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 78 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 79 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 80 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 81 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 82 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 83 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 84 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 85 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 86 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 87 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 88 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 89 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 90 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 91 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 92 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 93 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 94 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 95 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 96 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 97 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 98 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 99 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 101 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 102 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 103 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 104 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 105 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 106 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 107 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 108 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 109 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 110 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 111 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 112 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 113 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 114 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 115 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 116 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 117 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 118 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 119 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 120 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 121 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 122 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 123 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 124 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 125 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 126 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 127 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 128 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 129 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 130 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 131 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 132 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 133 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 134 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 135 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 136 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 137 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 138 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 139 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 140 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 141 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 142 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 143 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 144 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 145 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 146 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 147 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 148 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 149 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 150 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 151 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 152 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 153 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 154 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 155 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 156 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 157 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 158 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 159 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 160 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 161 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 162 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 163 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 164 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 165 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 166 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 167 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 168 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 169 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 170 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 171 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 172 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 173 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 174 | DRAW FEE | 12000 | 0 | 12000 | 0 | 12000 | 0.08633% | 0.14594 | 4000 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8000 | 66.67%
|  |  |  | 175 | Total | 16921419.26 | 3021419.26 | 13900000 | 0 | 13900000 | 100% | 169.0442 | 239473.2569 | 665588.165 | 911597.99 | 705005 | 427922.2545 | 62332.54 | 464871.72 | 448150.74 | 1289464.523 | 912365.721 | 728495.5905 | 1155163.003 | 1323426.343 | 1181207.15 | 1022463.03 | 315500 | 1483196.664 | 563776.31 | 0 | 0 | 0 | 0 | 0 | 0 | 161772.68 | 13660526.74 | 97.11%
|  |  |  | 176 | Total Reimbursable | 16921419.26 |  | 13900000 |  | 13900000 | 100% | #DIV/0! | 239473.2569 | 665588.165 | 911597.99 | 705005 | 427922.2545 | 62332.54 | 464871.72 | 448150.74 | 1289464.523 | 912365.721 | 728495.5905 | 1155163.003 | 1323426.343 | 1181207.15 | 1022463.03 | 315500 | 1483196.664 | 563776.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
|  |  |  | 177 | Total Equity (Non Reimbursable) | 0 | 3021419.26 | 0 |  | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161772.68 | 13660526.74

## Sheet1
Contract Analysis
Contract Amount | 14846921.18
Contributions | -1549324.15
Change Orders | 468980.74
Landscape Allowance Overage | 58658
Revised Contract Amount | 13825235.77
Payments Made
Draws 1-3 | 650356.74
Arixa Draws | 12552866.02
Less Developer Costs in Draws | -21166
Arixa Draw 16 | 300000
Total Paid | 13482056.76
Amount Under Budget (Revised Contract Amount-Total Paid) | 343179.01

## Sheet2
Contributions
SCS | 261324.15
Kap | 300000
Shade Tree Ranch/Salmon | 150000
Fox and Hound | 400000
Infinite Pines/PPC | 213000
Beaver Construction | 100000
Abrams Plumbing | 125000
1549324.15
Developer Costs in Draws
Draw 19 | Ambient | 19521
Draw 15 | Ogden Fees | 1645
Draw 4 | Ogden Fees |  | 9350.94
21166